## SetupTracking
Release: | 34.10 | Release-34.10 | [5 empty] | Update if Needed |  | 1. Click Cell A1 2. Press Ctrl+F > push the 3 dots 3. Find the string "CHECKLIST_VERSION" and replace it with the real value a. ex. Find: CHECKLIST_VERSION Replace with 32.00 ^Checklist dot Version^ 4. Select the "Replace All" button to swap all instances 4. Repeat steps 3-4 by replacing PREVIOUS_VERSION with 31.40 ^Previous Version^ 5. Repeat steps 3-4 by replacing CHECKLIST-VERSION with 32-00 ^Checklist dash Version^ 6. Repeat steps 3-4 by replacing NEXT_VERSION with 32.10 ^Next Version^ 7. Repeat steps 3-4 by replacing NEXT_MAJOR_VERSION with 33.00 ^Next Major Version (.00)^ You will know it worked if all red text in this cell/sheet has been updated to the set values
Branch Open Date: | 2025-07-17 | Jira Ticket: |  |  |  |  | CHECKLIST_VERSION | 34.10 | Do if Replace Button does not work! -->>
Hard Lock: | 2025-07-18 | ROS Sheet: |  |  |  |  | PREVIOUS_VERSION | 34
Pencils Down: | 2025-07-19 | ROS Zoom: |  |  |  |  | NEXT_VERSION | 34.2
Cert Submission: | 2025-07-20 | JIRA DASHBOARD: |  |  |  |  | NEXT_MAJOR_VERSION | 35
ROW Deploy: | 2025-07-21 | Slack Channel: | https://slack.com/app_redirect?channel=fn-release-34-10-ext
Outstanding Issues:
Ops: |  |  | Production: |  |  | Submisions:
2025-07-10 | TODO | Branching Dates Slack Email Kickoff | 2025-07-10 | TODO | Replacing template text in this checklist | 2025-07-16 | TODO | Request Patches: Create New Release for Nintendo
2025-07-13 | TODO | Branching Email - Go Ahead and Sync Reply | 2025-07-10 | TODO | Add this sheet's ID to the Workato checklist sheet | 2025-07-16 | TODO | Request Patches: Fill out and submit new OMAS for Nintendo
2025-07-17 | TODO | Branching Email - Branch is now fully open! AND Update [Release-Archive-Hardcore] section in lockdown_config.ini | 2025-07-12 | TODO | Send Slack Review For Untriaged Pre-SH & QA High Risk JIRAs: Keep this checklist item open until closer to CERT to continue to refresh and escalate issues added | 2025-07-16 | TODO | Request Patches: SIEA (07022) (07022) - WIKI
2025-07-17 | TODO | Ensure "Time Offset" is set to the main branches' season start date | 2025-07-12 | TODO | Send Slack Review For Untriaged Escaped Crashes / Asserts / Ensures JIRAs: Keep this checklist item open until closer to CERT to continue to refresh and escalate issues added | 2025-07-16 | TODO | Request Patches: SIEE (07669) (07669) - WIKI
2025-07-17 | TODO | Check that UGS banner is updated to include Release Schedule & JIRA filter link | 2025-07-15 | TODO | Release Content Legal Approval has Started | 2025-07-16 | TODO | Request Patches: PS5 Shared
2025-07-17 | TODO | Update DEV-FN-XX MOTD to notify it is being sunset and to stop working in it | 2025-07-17 | TODO | Send Slack Review For Untriaged Pre-SH & QA High Risk JIRAs: Keep this checklist item open until closer to CERT to continue to refresh and escalate issues added | 2025-07-16 | TODO | Create Version on App Store Connect and check if any Publishing metadata updates are needed
2025-07-17 | TODO | Verify UGS MOTD in Main Shows Updated Information | 2025-07-17 | TODO | Send Slack Review For Pre-SH & QA High Risk that are assigned to the current release: Keep this checklist item open until closer to CERT to continue to refresh and escalate issues added | 2025-07-17 | TODO | Ensure Sony publishing tools are up to date
2025-07-17 | TODO | Enable Scheduled Horde Jobs | 2025-07-17 | TODO | Release Content Legal Approval (FN and UEFN content) Cosmetic Content Assets Sheet | 2025-07-17 | TODO | Make sure PS4 SIEE (07669) packages are being built
2025-07-17 | TODO | Create Season Run of Show sheet for orchestrating the teams | 2025-07-17 | TODO | Create fn-release-CHECKLIST-VERSION-ext Slack channel and invite groups/users listed in Columns H/I | 2025-07-18 | TODO | Get engineer sign off of patch Sizes
2025-07-17 | TODO | Inform the slack channel of the bookmarked links | 2025-07-17 | TODO | Create Release Request | 2025-07-18 | TODO | Review the Cert issues filter to make sure nothing egregious still needs to be fixed
2025-07-17 | TODO | Create Deploy Tracker sheet and bookmark in release channel | 2025-07-17 | TODO | Create Release JIRA Dashboard | 2025-07-19 | TODO | FortniteContentBuilds: - This is Content On Demand (downloading additional stuff in the background which is only present on some platforms) Verify platforms below have been updated correctly: - PC/Windows - Android - PS4 - PS5 - Switch - XB1 - XSX - iOS Old Wiki
2025-07-17 | TODO | Ensure code only builds are working properly including verification it can be successfully promoted | 2025-07-17 | TODO | Generate Release Controller Permalink | 2025-07-19 | TODO | Verify that the PS5/PS4 versioning is correct for the release.
2025-07-18 | TODO | All Remaining Build Errors/Warnings Have Been Approved To Ship With | 2025-07-17 | TODO | Set Slack channel Topic to Release Manager and Dashboard Link | 2025-07-19 | TODO | Make sure SwitchEngine version has been incremented.
2025-07-18 | TODO | Verify Android version number has been updated in perforce | 2025-07-17 | TODO | Setup Release Dashboard's Top Widget | 2025-07-19 | TODO | Verify that LatestPatch folder contains last released patches
2025-07-18 | TODO | Verify iOS version number has been updated in perforce | 2025-07-17 | TODO | Cross check Fortnite Release Calendar below dates are accurate for all versions from this checklist's season and the following season found in the FN Release Schedule and populated from the Air Table - Row 16: Branch Opening - Row 17: Development Complete - Row 18: Hard Lock - Row 19: Pencils Down - Row 20: Cert Sub - Row 5: Live - Row 5 of next column(s): HF(s) Live | 2025-07-19 | TODO | Verify the file system captures for Nintendo have been gathered by QA
2025-07-18 | TODO | Verify Version Locking AND that the Net Version locked to is different than the currently live branch | 2025-07-17 | TODO | Create a Jira for BR Calendar/Store/Shop to be update/reviewed | 2025-07-20 | TODO | Create a cert thread in the Release channel.
2025-07-18 | TODO | Set NetCL Version Number | 2025-07-17 | TODO | Verify BranchFoundIn in JIRA is already populated for CHECKLIST_VERSION if not, request it be done in #fn-jira-admins-ext | 2025-07-20 | TODO | Update Release Log and Release Request
2025-07-18 | TODO | Add Temporary Allowlisters to lockdown file | 2025-07-17 | TODO | Schedule Google Calendar Meeting: Stability Sync | 2025-07-20 | TODO | Make local copies to your station for all platforms going to certification
2025-07-18 | TODO | Update MOTD in UGS for Hardlock | 2025-07-17 | TODO | Schedule Google Calendar Meeting: Post Mortem | 2025-07-20 | TODO | Add build info to the relevant cert backends. (CCA/ CCB / MobileCert)
2025-07-18 | TODO | Release Owner: Log into all deploy-related tools | 2025-07-17 | TODO | Schedule Calendar Events: - Hard Lock - Pencils Down | 2025-07-20 | TODO | Set up the above cert environments to have the correct: - Server (CCA / CCB / DPQ / MobileCert) - MCP (CCA / CCB / DPQ / MobileCert)
2025-07-19 | TODO | Get Folder Comparison sign off from Anticheat for PC and UEFN | 2025-07-17 | TODO | Determine Deploy Time with the below teams: - Live Ops - Competitive - Publishing/Marketing | 2025-07-20 | TODO | Ensure cert backends are online (CCA / CCB / DPQ / MobileCert)
2025-07-19 | TODO | Update the metastream UE robomerge connection to point to NEXT_VERSION | 2025-07-17 | TODO | For XX.00 Deploys Only: Reminder messaging for seasonal Hotfix clean up | 2025-07-20 | TODO | CertSub Candidate: Patch Sizes
2025-07-19 | TODO | Lock the DAD CL | 2025-07-18 | TODO | Send Release Strategy email Confluence Wiki (need to merge all the things) Wiki on creating the meeting calendar event Template (if not copied from a previous email) | 2025-07-20 | TODO | Send Akamai early estimate of patch sizes - Email
2025-07-19 | TODO | Ensure Modes & Tags are setup in DS Portal for Release QA Whiteglove | 2025-07-18 | TODO | Redundancy: Make sure zoom links are still valid for all meetings related to CHECKLIST_VERSION | 2025-07-20 | TODO | Notify Nvidia of the upcoming patch date and time - Email
2025-07-19 | TODO | Remove Temporary Allow Listed - 8PM ET | 2025-07-18 | TODO | Coordinate Discovery surface and link updates for any new playlists | 2025-07-20 | TODO | Notify AWS of the upcoming patch date, time, and sizes - Email
2025-07-19 | TODO | Enable Robomerge Gate - 8PM ET | 2025-07-18 | TODO | Verify Final DOT Links for WG testing are accurate and no changes are expected. https://epicenter.on.epicgames.com/?tools=all | 2025-07-20 | TODO | Notify Fastly of the upcoming patch date, time, and patch sizes - Slack Post
2025-07-19 | TODO | Move Festival CMS job to the next Release | 2025-07-18 | TODO | Ensure Final Shop is in for WG testing | 2025-07-20 | TODO | Notify Akamai of the upcoming patch date, time, and patch sizes - Slack Post
2025-07-19 | TODO | Identify team for release day and update Release Request | 2025-07-19 | TODO | Make sure Disallow List has Started (Data Encryption) | 2025-07-20 | TODO | Notify Cloudflare channel of the upcoming patch date, time, and patch sizes - Slack Post
2025-07-19 | TODO | Kick Cert Build | 2025-07-19 | TODO | Confirm the final loc commit job successfully makes it into P4 Need to ask for: - Fortnite - UEFN - Lego - Festival - Rocket Racing | 2025-07-20 | TODO | Notify ISP email group alias of the upcoming patch date, time and patch sizes - Email
2025-07-19 | TODO | Update Scheduled Builds. SSB Current and Next | 2025-07-19 | TODO | Request Final DAD revision for pre whiteglove https://epicenter.on.epicgames.com/?tools=all For reference: https://epicgames.slack.com/archives/C08DLJG51L7/p1742565116008119 | 2025-07-20 | TODO | Request Patches: Email Xbox Account Manager
2025-07-20 | TODO | Generate Optimized Patches (chunkdbs) for all platforms delpoying | 2025-07-19 | TODO | 1st touchpoint with Calendar owners Typically you get sign off from all but BR (Shop & Non-Shop) | 2025-07-20 | TODO | Update DevNet Thread with Incoming Patch Information
2025-07-20 | TODO | Final Client Build Protection | 2025-07-19 | TODO | Send Last Call bump for callouts in the Release Strategy Email. WIKI | 2025-07-20 | TODO | Upload Nintendo ROM and complete pre-submit waiver requests
2025-07-20 | TODO | Final Server Build Protection | 2025-07-19 | TODO | Determine Ship List (using the below Airtable) and pin it in Slack New Hotness: Deliverables Roadmap Build View | 2025-07-20 | TODO | Submit Switch the Switch build to lotcheck
2025-07-20 | TODO | Disable remaining unneeded builds | 2025-07-19 | TODO | Whiteglove has been completed on INITIAL release candidate (aka crit checks) and issues called out have been threaded/escalated for triage Note: We will never be releasing this build. There will always be another CL for our final candidate (THIS LINE) | 2025-07-20 | TODO | Submit IOS for Notarization
2025-07-20 | TODO | Verify no new client CLs have been introduced between Final Client WhiteGlove and Final Server/MCP WhiteGlove tests. | 2025-07-19 | TODO | Whiteglove has been completed on FINAL release candidate (aka Cert Checks) and issues called out have been threaded for triage | 2025-07-20 | TODO | Upload SIEA (07022) build
2025-07-20 | TODO | Confirm with Discovery team that the Analytics Stuff revision has been deployed to Live | 2025-07-19 | TODO | Confirm Release QA is patched up and ready for the morning | 2025-07-20 | TODO | Upload SIEE (07669) build
2025-07-20 | TODO | Verify Release Request is accurate | 2025-07-20 | TODO | Make sure Disallow List was reviewed (FN, FNE (Creative+UEFN), JUNO, DelMar, Sparks terms) | 2025-07-20 | TODO | Upload PS5 shared binary
2025-07-20 | TODO | Pre-upload symbols for the following (Within 24 hours of deployment) | 2025-07-20 | TODO | Aegis Prewarm (Final Client and Server CL) | 2025-07-20 | TODO | Upload the Luna Client and send it to certification
|  |  | 2025-07-20 | TODO | 2nd touchpoint with Calendar owners | 2025-07-20 | TODO | Upload XB builds, verify the validator logs, and submit to cert.
|  |  | 2025-07-20 | TODO | Release Strategy Async Post Example Post: LINK | 2025-07-20 | TODO | Complete and save final MDT (PS5)
[6 empty] | 2025-07-20 | TODO | Update MDT: SIEA
[6 empty] | 2025-07-20 | TODO | Update MDT: SIEE
[6 empty] | 2025-07-20 | TODO | Rapid patch Submission: SIEA (07022)
[6 empty] | 2025-07-20 | TODO | Rapid patch Submission: SIEE (07669)
[6 empty] | 2025-07-20 | TODO | Rapid patch Submission: PS5
[6 empty] | 2025-07-20 | TODO | Final Scheduling: Xbox One / XSX
[6 empty] | 2025-07-20 | TODO | Final Scheduling PS5
[6 empty] | 2025-07-20 | TODO | Final Scheduling PS4
[6 empty] | 2025-07-20 | TODO | Upload PS4 Symbols to devnet
[6 empty] | 2025-07-20 | TODO | Upload PS5 Symbols to devnet
[6 empty] | 2025-07-20 | TODO | Upload XB1/XSX crash symbols through Xbox Send
[6 empty] | 2025-07-20 | TODO | Final Scheduling: Switch
[6 empty] | 2025-07-20 | TODO | Submit Build to One Store
[6 empty] | 2025-07-20 | TODO | Upload the Digital Turbine Candidate
[6 empty] | 2025-07-20 | TODO | Submit Android build to Oppo
[6 empty] | 2025-07-20 | TODO | Confirm with Luna that we're through certification.
[6 empty] | 2025-07-20 | TODO | Remove Cert Redirects
[6 empty] | 2025-07-20 | TODO | Spindown Cert Servers
[6 empty] | 2025-07-20 | TODO | Live: Update PS4/PS5/XB1/XSX/IOS fake Build Info
[6 empty] | 2025-07-20 | TODO | Live: Update Switch Build Info
[6 empty] | 2025-07-20 | TODO | Live: Update Android Build Info
[6 empty] | 2025-07-20 | TODO | Prep AltStore Stage Source
[6 empty] | 2025-07-20 | TODO | Schedule Lightswitch Down in Admin Portal - Scheduling MUST happen at least 1 hour before the downtime start
[6 empty] | 2025-07-20 | TODO | Internal Release Email Template
[6 empty] | 2025-07-20 | TODO | External Release Email Template
[6 empty] | 2025-07-20 | TODO | Send "Release is a GO" email
REPLACE

## Integrations Checklist (hidden)
Is there a JIRA marked on the correct Fix Version?
Does the JIRA have Production involvement? (comments, history, etc.)
Do included files seem reasonable for the change being requested?
Is there a generic/master shader file being touched? If yes then ask about invalidation expectations.
Is the shelve in the correct/expected branch?
If there is a code change included is there proper code review?
Is question "What testing has already been performed? What risks remain?" answered
Is question: "Does this change or add new strings/have a localization impact?" answered
Is question: "Will it cause a large set of files to be invalidated and recooked?" answered
Is question: "Will it cause a large spike in patch sizes?" answered

## Checkins Since PD (hidden)
CL | User | Description | Date | Steps to Pull
Look in calendar for PD date / time
Copy 1st CL after that date in P4
Copy Latest CL in branch
Go to Swarm and filter that CL range and intented release branch
- Might be a better way to do it with this
copy the data and paste in cell 2A
Highlight data and sort by column B to group buildmachine CLs
Delete those rows
Highlight data and sort by column D to order by date
Highlight backout CLs to indicate CLs that came back out

## Point of Contacts (hidden)
Point of Contacts
Area of Expertise | Primary | Secondary
Production | Heather Hazen | Josh Harr
Staging/Promotion | Joseph Sozio/Michael Moretti | Alex Conner
MCP/MMS Deployment | Joseph Sozio/Michael Moretti | Alex Conner
Builder Issues | Chad Garyet | Jeff Williams/Ben Marsh
Staging/Promotion Issues | Chad Garyet | Jeff Williams/Ben Marsh
Server Issues | Evan Kinney | Tyler Cole
Team City Issues | Greg Latcovich | Rudy Marks/Tyler Cole
MMS Issues | Paul Moore | ---
Hotfixes | Joseph Sozio/Michael Moretti
CMS | Stacey Conley | Chris Sierra/Boomer Gurney
Calendar | Joel Stalica/Patrick Malloy | Tim Tillotson
QA | TristanA/JaymeeS/JoshuaD | Cody Briggs
LiveQA | Tyler Orban | Will Sutherland/LiveQA Alias

## Data (hidden)
ActionStatus
TODO
IN PROGRESS
DONE
N/A
BLOCKED

## Operations Checklist
| Item | Status | Due by | Completed by | Temp-Notes | Steps To Complete | Suggested Slack Post Text (unless otherwise stated) | Suggested Slack Thread Text (unless otherwise stated) | Automation? | Additional Notes
| Pre-Candidate Build - MUST DO |  |  |  |  | 77
| By Hard Lock: | IN PROGRESS
| By Pencils Down: | IN PROGRESS
OPS | All Remaining Build Errors/Warnings Have Been Approved To Ship With | TODO | 2025-07-18 |  | Tracking Sheet Here Last Update: - MONTH_DAY | 1.Go to the Tracking Sheet and dupe the template and rename to this checklists version 2. Go to the Builds tab of the Horde Branch for the checklist's version 2. Go to latest completed Nightly and SSB builds. 3. Go through any Red/Yellow badges in the Clients, Servers, UEFN columns and enter information into the tracker sheet. a. You can ignore the Test Content Worker Docker Image Win64/Linux badges in the UEFN section 4. Go through any Red/Yellow badges in the Nightly Data Rebuild & World Partition Build builds and enter information into the tracker sheet. 5. Once you have entered all Errors/Warnings into the tracker sheet, spin up build health threads (as normal for BH) in the #fn-build-health-ext channel and escalate to the appropriate people for sign off - template in 1st tab of sheet a. Ensure all issues have a JIRA for tracking so these can be addressed at some point 6. Spin up a general World Partition Build thread and tag Sébastien Lussier for review (example here)
OPS | Verify Android version number has been updated in perforce | TODO | 2025-07-18 |  | Commit CL: 12345 | 1. Open P4 and navigate to the below file //Fortnite/Release-CHECKLIST_VERSION/FortniteGame/Config/DefaultEngine.ini 2. Search file for the string: VersionDisplayName a. Should live under the [/Script/AndroidRuntimeSettings.AndroidRuntimeSettings] header 3. Verify this is set to CHECKLIST_VERSION.0
OPS | Verify iOS version number has been updated in perforce | TODO | 2025-07-18 |  | Commit CL: 12345 | 1. Open P4 and navigate to the below file //Fortnite/Release-CHECKLIST_VERSION/FortniteGame/Config/IOS/IOSEngine.ini 2. Search file for the string: VersionInfo a. Should live under the [/Script/IOSRuntimeSettings.IOSRuntimeSettings] header 3. Verify this is set to CHECKLIST_VERSION (should not have a .0)
OPS | Verify Version Locking AND that the Net Version locked to is different than the currently live branch | TODO | 2025-07-18 |  | PREVIOUS_VERSION: 12345 CHECKLIST_VERSION: 12345 Reviewed by: PERSON | 1. Open P4 and navigate to the below file path //Fortnite/release-PREVIOUS_VERSION/Engine/Source/Runtime/Core/Public/Misc/NetworkVersion.h 2. Search file for the string: ENGINE_NET_VERSION 3. Note the listed CL in Column F 4. Repeat steps 1-3 using the below file path //Fortnite/release-CHECKLIST_VERSION/Engine/Source/Runtime/Core/Public/Misc/NetworkVersion.h a. If the ENGINE_NET_VERSION is not set to 0, verify the set CL is higher than the previous release's CL b. If the ENGINE_NET_VERSION is set to 0, set it to a CL that is higher than the previous release's CL i. Can use the last successful Nightly Build CL & make sure to deadend your commit using the suggested text in Column H 5. Once submitted, have someone else on the team review your commit. | Setting NetCL after CHECKLIST_VERSION Hardlock #jira none #okforgithub public #rnx #robomerge -NEXT_VERSION #submittool bypass
| By Cert Submission: | IN PROGRESS
OPS | Get Folder Comparison sign off from Anticheat for PC and UEFN | TODO | 2025-07-19 |  | Keep In Progress until final build, but track latest approval | 1. Check email for Folder Comparison 2. Find the email associated with the latest approved PC candidate (ex. ++Fortnite+Release-26.30-CL-28509302) 3. Ensure there are links to the diff (current live CL vs candidate) for the Game Client & UEFN 4. Ensure we get sign off (Ben Temple, Joe Barrett or Lukasz currently) | CHECKLIST_VERSION Folder Comparison Sign Off :thread: | Hello @ben.temple @joe.barrett @lukasz
Preparation
| Item | Status | Due by | Completed by | Temp-Notes | Steps To Complete | Suggested Slack Post Text (unless otherwise stated) | Suggested Slack Thread Text (unless otherwise stated)
| By Branch: | IN PROGRESS
OPS | Branching Dates Slack Email Kickoff | TODO | 2025-07-10 |  |  | 1. Spin up a thread titled ":thread: CHECKLIST_VERSION Branching" in #buildfarm-support-ext and use the suggested text in column H for the thread messaging 2. Search for previous email (from a similar version number) titled: "[Branch News]" 2. Copy the formatting into a new email and swap in the appropriate information gleaned from the buildfarm thread | Thread Title: :thread: CHECKLIST_VERSION Branching! :yesyes: ------------------------------------------------------ Thread Body: Based on the roadmap: - Branch Operation/Creation: DAY_DATE from BRANCH - Branch Opening/Work Cutover (9am ET): DAY_DATE Sending out initial email NEXT day afternoon for wider knowledge. @release-team @buildfarmsupport @p4admins @fn-buildhealthqa | Thread Title: :thread: CHECKLIST_VERSION Branching! :yesyes: ---------------------------------------------------------------------- Hello! It's about that time again. CHECKLIST_VERSION/Dev-FN-XX Branch Operation is DAY_DATE and officially opens for business DAY_DATE morning per the roadmap. Based on the roadmap: Dev-FN-XX - Branch Operation/Creation: DAY_DATE from BRANCH - Branch Opening/Work Cutover (9am ET): DAY_DATE XX.00: - Branch Operation/Creation: DAY_DATE from BRANCH - Branch Opening/Work Cutover (9am ET): DAY_DATE Sending out initial email Tuesday afternoon for wider knowledge. Will be pushing extra hard on proxy servers. Has there been changes to the proxy server process and is the wiki up to date? @release-team @buildfarmsupport @p4admins @fn-buildhealthqa | Yes | Replace with Pre-Pop
OPS | Branching Email - Go Ahead and Sync Reply | TODO | 2025-07-13 |  | Should be done on the friday the week prior to branch open | 1. Reply to Branch News email with a "branch is now fully open" message 2. Search for previous email (from a similar version number) titled: "[Branch News]" 3. Copy the formatting into a reply to the original email from from row 34 and swap in the appropriate information | see Stan's 30.30 for text |  | Yes | Replace with Pre-Pop
OPS | Branching Email - Branch is now fully open! AND Update [Release-Archive-Hardcore] section in lockdown_config.ini | TODO | 2025-07-17 |  |  | 1. Reply to Branch News email with a "branch is now fully open" message 2. Search for previous email (from a similar version number) titled: "[Branch News]" 3. Copy the formatting into a reply to the original email from from row 34 and swap in the appropriate information ----- 1. Go to this P4 file path //Fortnite/Main/FortniteGame/Build/p4lockdown/lockdown_config.ini 2. Check out the file and Open 3. In the file, search for [Release-Archive-Hardcore] 4. Navigate to the section and ADD the version corresponding to this checklist version: '-//Fortnite/Release-XX.XX...' Add it before the -//Fortnite/*/ lines start 5. Save and commit. |  |  | Yes | Replace with Pre-Pop
OPS | Ensure "Time Offset" is set to the main branches' season start date | TODO | 2025-07-17 | SH | Adjusted offset by XX days ONLY RUN IF THIS IS A XX.00 CHECKLIST (otherwise N/A) | 1. Go to the below file in p4 > get latest > checkout and open https://epicenter.on.epicgames.com/fortnite/backends/latest-gamedev 2. Determine the deploy date for NEXT_MAJOR_VERSION (which main is currently representing) in the release calendar or FN Release Schedule 3. Using the built in calculator, calculate the number of days from today till that date 4. Search for the following and swap that value in for the value that is currently set in the file > save config.com.epicgames.modules.profile.time_offset_days: 5. Click on the days cell on the right to copy to clipboard 6. Update the value on the left window 7. Save Don't need to kick it in manually as its scheduled to kick every time a main build finishes as well as every hour 8. Check back in TeamCity to ensure the pending change is now a real boy
OPS | Check that UGS banner is updated to include Release Schedule & JIRA filter link | TODO | 2025-07-17 |  | Commit CL: 12345 Robo Resolve CL: 12345 | Check the UGS banner first, there may be no edits needed (need to import the project's .uproject file). See example in cell 20 I *Milestone dates have been deprecated, only edit this file if needed 1. Go to the following file in P4 while in the same workspace //Fortnite/release-CHECKLIST_VERSION/FortniteGame/Build/UnrealGameSync.ini 2. Get Latest > Checkout and Open 3. Find the CHECKLIST_VERSION section and update the banner text 4. Save and commit CL using the submit tool You will run into a robomerge conflict. Here is how to resolve that: 1. Use robomerge to make a shelf in the downstream branch of the conflict 2. Unshelve the file in this new pending CL 3. Get latest on the file 4. RC > Resolve 5. Run Merge Tool 6. Scroll down to the conflict (or use the red arrows at the top) and remove the Yellow & Green blocks of text (leaving the blue one). 7. Save and open the file to ensure the intended changes are there 8. Once satisfied, commit the file, and hit retry on the robomerge blocker to ensure that is resolved correctly. | Updated JIRA Filter Link on UGS banner for CHECKLIST_VERSION #jira none #rnx #fyi stan.hormell | (*be mindful of the branch populated text) Message=[FN Release Schedule](https://epic.gm/schedule) ¦ [Jira Dashboard](https://epic.gm/CHECKLIST-VERSION) ¦ Branch Cut Over from Dev-FN-34 @ 39512793 StatusPanelColor=#9b49cc
OPS | Update DEV-FN-XX MOTD to notify it is being sunset and to stop working in it | TODO | 2025-07-17 |  | Commit CL: 12345 Robo Resolve CL: 12345 Do this checklist item if this checklist is for a version immediately before a XX.00 version (as the Dev-FN-XX branch is no longer valid for work - Since it should be done in the explicit Release-CHECKLIST_VERSION branch) | 1. Go to the following file in P4 while in the same workspace //Fortnite/Dev-FN-XX/FortniteGame/Build/UnrealGameSync.ini 2. Get latest > Checkout and Open 3. Create a pending CL using the suggested P4 Description in Column H --> 4. Scroll to the bottom of file 5. Copy text from column i and overwrite the "Message=.... text currently in the file" 6. Save and commit CL using the submit tool You will run into a robomerge conflict. Here is how to resolve that: 1. Use robomerge to make a shelf in the downstream branch of the conflict 2. Unshelve the file in this new pending CL 3. Get latest on the file 4. RC > Resolve 5. Run Merge Tool 6. Scroll down to the conflict (or use the red arrows at the top) and remove the Yellow & Green blocks of text (leaving the blue one). 7. Save and open the file to ensure the intended changes are there 8. Once satisfied, commit the file, and hit retry on the robomerge blocker to ensure that is resolved correctly. | Updated Dev-FN-XX MOTD to note this branch is no longer valid for work. All work moving forward should be done in CHECKLIST_VERSION #jira none #rnx #fyi stan.hormell | Message=:alert: THIS BRANCH IS NOW DEPRECATED AND SHOULD NOT BE COMMITTED TO MOVING FORWARD! Please commit previously associated work into the new explicit CHECKLIST_VERSION branch. StatusPanelColor=#ff0000
OPS | Verify UGS MOTD in Main Shows Updated Information | TODO | 2025-07-17 |  | Completed by #buildfarm-support-ext - Main is now NEXT_MAJOR_VERSION - Target Release-NEXT_MAJOR_VERSION+ - Branch Creation Date - Branch Open Date | 1. Open UGS 2. Go to the Main Tab (need to import the project's .uproject file) 3. Verify you see the correct information
OPS | Enable Scheduled Horde Jobs | TODO | 2025-07-17 |  | Commit CL: 12345 | 1. Go to here in P4: //Fortnite/Main/FortniteGame/Build/Streams/fortnite-release-CHECKLIST_VERSION.stream.json 2. Get Latest & Check out and open file 3. Create a shelf using the suggested P4 Description in Column H --> 4. Find "Nightly Build with Build Health" 5. In the "schedule" section > change "enabled": false to "enabled": true 6. Repeat steps 4-5 for: a. "Nightly Data Rebuild" b. "World Partition Build" c. "Juno Limited Build" d. "Export Item Shop" `nightly-export-item-shop` (Does not need to be enabled on Dev-FN-XX) e. "Build Tests - Weekly" f. "Build Tests - Twice Weekly" g. "Build Tests - Thrice Weekly" h. "Nightly UEFN Data Rebuild" i. "compatlabnightly" 7. Save and commit in P4 8. Send courtesy message in Slack to #buildfarm-support-ext using the suggested P4 Description in Column I --> If this checklist is for a XX.00 version, also enable these for the Dev-FN-NN branch | Enabling the below jobs for Release-CHECKLIST_VERSION: - Nightly Build with Build Health, Nightly Data Rebuild, World Partition Build, Juno Limited Build, Export Item Shop, Build Tests - Weekly, Build Tests - Twice Weekly, Build Tests - Thrice Weekly, Nightly UEFN Data Rebuild, CompatLabNightly #jira none #rnx #fyi stan.hormell, swarm-ue-build-reviews | Hi Build Farm, just wanted to inform you that we enabled the below jobs for CECKLIST_VERSION at CL XXXXX. - Nightly Build with Build Health, Nightly Data Rebuild, World Partition Build, Juno Limited Build, Export Item Shop, Build Tests - Weekly, Build Tests - Twice Weekly, Build Tests - Thrice Weekly, Nightly UEFN Data Rebuild, CompatLabNightly That's all!
OPS | Create Season Run of Show sheet for orchestrating the teams | TODO | 2025-07-17 |  | ROS Sheet - (also add to Setup/Tracking D3) ROS Zoom - (also add to Setup/Tracking D4) | Before running through the following, check the season folder to see if the RoS has already been created. If so, skip to Step 3 1. Duplicate the Master TEMPLATE 2. Rename to CHECKLIST_VERSION Run of Show & set the deploy date in cell I1 3. Duplicate previous instance(s) of the Run Of Show Calendar Events in the Fortnite Release Team Calendar and set to dates outlined in column B 4. Remove existing zoom link and re-add to ensure they work properly. Add the same zoom link to all instances of the 2 or 3 calendar events as well as adding the link to Cell E1 in the RoS 5. Search the list for anyone that may not be with the company and remove them to avoid bounce back emails a. Look for blank profile pics and first.last@epicgames.com OR by searching for the * character and remove those if they don't exist in slack 6. Search google calendar for a previous instance of the Launch Room (previously War Room) calendar event and duplicate it (ensure its set to the Fortnite Release Calendar) and set to the day of deploy. Remove its zoom link and add the same one used for the RoS meetings a. Ensure Jamie Domach, Zach Moore & Jonathan Titus Are included b. Go to https://epicgames.zoom.us/ and sign into account i. Scroll down to the bottom section's Alternative Hosts and add Stan Hormell and Nick Bentham ii. Select the Breakout Room pre-assign and click the "+" icon 10x and save 7. Go to the Release-CHECKLIST_VERSION slack channel and create a Bookmark Folder titled Run of Show. a. Add a link to the RoS Sheet b. Add a link to the Deploy Day Launch Zoom c. Add a link to the Deploy Day Launch Zoom Calendar Event 8. Reach out to publishing to let them know the RoS has been created a. Currently Paris Nourmohammadi Laura Stone Michael Micholic | :fyi: @Paris Nourmohammadi @Laura Stone @Michael Micholic The CHECKLIST_VERSION Run of Show has been created for both Fortnite & Publishing coordination and links have been added to the Run of Show folder in this channel. Please let us know if you were planning on tracking work elsewhere as we would like to avoid potential "thread splitting" :ty: in advance! |  | Yes
OPS | Inform the slack channel of the bookmarked links | TODO | 2025-07-17 |  | Slack: LINK Links - Run of Show Sheet - War/Launch Room Zoom Link - War/Launch Room Calendar Link | 1. Go to fn-release-CHECKLIST-VERSION-ext channel in slack 2. Send message using the suggested text in Column H If the War/Launch Zoom/Calendar Event doesn't exist, create one and put it in the Run of Show | :announcement-1: Just a heads up for tomorrow: `The Run of Show, Launch Room Zoom & Calendar Invite` links are bookmarked at the top of this channel. :announcement-1: |  | Yes
OPS | Create Deploy Tracker sheet and bookmark in release channel | TODO | 2025-07-17 |  |  | Add as Bookmark to that Release Channel so it is easily visible to everyone. Shared drives > Fortnite > Release Management > Post Deploy > Tracker Sheet > Master Deploy Tracker (make a copy, move it to the correct location, and rename) XX.XX Deploy Tracker (Template): https://docs.google.com/spreadsheets/d/1L6LWocz1lolIWxtQoHjkUuvEzWFTvAb6fPtVOtVPQuY/edit?gid=1420338449#gid=1420338449 |  |  | Maybe?
| By Hard Lock: | IN PROGRESS
OPS | Set NetCL Version Number | TODO | 2025-07-18 |  | Commit CL: 12345 | 1. Go to the following file in P4 while in the same workspace //Fortnite/Release-CHECKLIST_VERSION/Engine/Source/Runtime/Core/Public/Misc/NetworkVersion.h 2. Get latest > Checkout and Open 3. Create a shelf using the suggested P4 Description in Column H --> 4. In the file, search for ENGINE_NET_VERSION (should be line 12 ish) 5. If it is currently 0, set it to the CL of the Last Successful SSB/Nightly Build in Horde a. If it is not 0, verify the set CL is the CL of the Last Successful SSB/Nightly Build in Horde 6. Save and commit CL using the submit tool (must be deadended) 7. Verify via Track Change that it did not merge - https://robomerge.epicgames.net/trackchange/####### | Setting NetCL version to CL XXXXXX #jira none #okforgithub public #rnx #robomerge -Release-NEXT_VERSION #robomerge FNONLY #submittool bypass
| AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK |  |  | AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK
OPS | Add Temporary Allowlisters to lockdown file | TODO | 2025-07-18 |  | Check Release's Hard Lock Calendar invite for additional instructions Commit CL: 12345 Slack: LINK | 1. Go to Allowlister Sheet and go to the appropriate release tab. 2. Copy names from Cell F2 at step 7. 3. Go to this P4 file path //Fortnite/Main/FortniteGame/Build/p4lockdown/lockdown_config.ini 4. Check out the file and Open. For the description, use the suggested text in Column H --> 5. In the file, search for [ReleaseA-Lockdown-Hardcore] and [ReleaseB-Lockdown-Hardcore] 6. Determine which list is setup for the upcoming release. If neither are, replace the older release with CHECKLIST_VERSION (See Step 2) 7. Paste the allowlisted names from step 2 after Stan.Hormell (ensure comma placement is retained). 8. Save and commit. 9. Post a message in the #fn-Release-CHECKLIST-VERSION-ext channel using the suggested text in column I | Adding Temporary Allow Listers & HardLocking CHECKLIST_VERSION #jira none #rnx | :announcement-1: CHECKLIST_VERSION is now Hardlocked and temporary allowlisted permissions have been set :lock: -- Please submit all changes through the Submit Tool using the standard integration process.
OPS | Update MOTD in UGS for Hardlock | TODO | 2025-07-18 |  | Commit CL: 12345 Conflict Resolve CL: 678910 | 1. Go to the following file in P4 while in the same workspace //Fortnite/Release-CHECKLIST_VERSION/FortniteGame/Build/UnrealGameSync.ini 2. Get Latest > Checkout and Open 3. Find the CHECKLIST_VERSION section and update the banner text 4. Save and commit CL using the submit tool Resolving the robo conflict: 1. Remove the conflicting yellow and green lines for the text your just changed. 2. Keep the blue text which should be exactly what you just updated in the checklist branch 3. Save and commit | Updated MOTD in UGS for CHECKLIST_VERSION Hard Lock #jira none #rnx | (*be mindful of the branch populated text) Message=:alert: THIS BRANCH IS NOW HARD LOCKED. Refer to [Branching, Lockdown, Integrations](https://epic.gm/lockdown) to submit changes ¦ [FN Release Schedule](https://epic.gm/schedule) ¦ [Jira Dashboard](https://epic.gm/CHECKLIST-VERSION) Branched Populated from Dev-FN-34 @ 38800603 StatusPanelColor=#e20000
| By Pencils Down: | IN PROGRESS
OPS | Update the metastream UE robomerge connection to point to NEXT_VERSION | TODO | 2025-07-19 |  | Slack: LINK | 1. Go to the Robomerge Bot Setup 2. Look to see if //UE5/Dev-Release is pointing to NEXT_VERSION a. if yes, DONE the check b. if no, go to #epic-release-managers-ext and post using the suggested text in Column H | @Marc Audy @release-team CHECKLIST_VERSION has been hardlocked :lock: Please update the metastream UE robomerge connection to the next FN release if that applies in this case.
OPS | Verify NetCL was set correctly and did not merge | TODO | 2025-07-21 |  | Robomerge Track Change Link: | 1. Open Robomerge Track Change and input the CL from HERE a. if the change did not merge, we are good b. if the change DID merge, WHAT ARE THE NEXT STEPS HERE?? c. if someone forgot to add the commit CL to the original task (shame on them and), run through the steps HERE
OPS | Ensure code only builds are working properly including verification it can be successfully promoted | TODO | 2025-07-17 |  | Code Only Build: LINK ++CL: 123456 Android Promotion to ReleaseStaging: LINK All Platform Promotion Job: LINK Link(s) to Error/Warning Thread(s): - Link 1 - Link 2 Be sure to include iOS for build and promotion steps | PART 1: 1. Navigate to //Fortnite/Release-CHECKLIST_VERSION's Builds tab in HORDE 2. Copy the CL of the last passing build 3. New Job > Minimal Code Only Build 4. Set the Base Change to the last passing build you copied 5. Set the Change CL to a green incremental's CL 6. Go to the Advanced Tab and in the JOB NAME input: CHECKLIST_VERSION MCO Creation TEST 7. Start Job a. escalate errors/warnings to #fn-build-health-ext or #buildfarm-support-ext (if applicable) for fixes 8. Once complete, move onto the next part where we will promote Android to FortniteReleaseStage PART 2: 1. Copy the ++CL from the above job and go to THIS link (which will retain all the necessary setup parameters) > Select JOB > RUN AGAIN a. Remove the CL from the CHANGE field b. Remove the ++CL from the BUILD VERSION and paste in the correct one from part 1 c. Go to the Advanced Tab and in the JOB NAME input: CHECKLIST_VERSION MCO Android Promotion TEST 2. Start Job a. escalate errors/warnings to #fn-build-health-ext or #buildfarm-support-ext (if applicable) for fixes 3. Once complete, move onto the final part where we will promote All Clients to a test backend PART 3: 1. Reach out to RQA or the Apps Team Reps on RM (currently Keaton Stewart Edwin Maynard) to see which backend to promote to for this test. a. If RQA is not in the loop, make a post in the fn-release-team channel informing them you are doing this test using the suggested text in Column I 2. Once you have an approved backend, Copy the ++CL from part 1 and go to THIS link (which will retain all the necessary setup parameters) > Select JOB > RUN AGAIN a. The link above contains all platforms. If a platform failed to build in part 1, unselect it from the PROMOTE PLATFORMS field 3. Repeat Step 1 from Part 2 with the addition of a. Select the approved backend to deploy to from the TO APP NAME dropdown b. Go to the Advanced Tab and in the JOB NAME input: CHECKLIST_VERSION MCO All Client Promotion TEST 4. Start Job a. escalate errors/warnings to #fn-build-health-ext or #buildfarm-support-ext (if applicable) for fixes 5. Once testing is complete, follow up with the person who gave you the backend to see if you need to rollback/revert your changes to restore it to its previous configuration | Need to see examples to create escalation | Hello friends! Just wanted to give you a heads up that I will be promoting a minimum code only build to `INSERT_APPROVED_BACKEND` as part of our release checklist. Please let me know if you have any questions or concerns.
OPS | Lock the DAD CL | TODO | 2025-07-19 |  | Slack: LINK | 1. Go to the Data Asset Directory and select CHECKLIST_VERSION 2. Click on the newest (top of the list) CL's Blue Lock button which will turn it red and unlocked (yes it seems backwards) as well as the CL turning green 3. Once complete, spin up a post in #fn-release-CHECKLIST-VERSION-ext using the suggested text in Column H | :announcement-1: RM has locked the DAD for CHECKLIST_VERSION to CL XXXXX :lock:
OPS | Ensure Modes & Tags are setup in DS Portal for Release QA Whiteglove | TODO | 2025-07-19 |  | Slack: LINK | Release Configs for Modes and Tags are now found in GitHub (via Deckard-Config). Check if the Release version folder has been created. If it's not present, request that the DS team create the configs. 1. Go to #ds-support-ext channel 2. Post the suggested request message (found in Column H, Slack Message 1) to request the setup of Tags and Modes configurations for the upcoming release. 3. Wait for confirmation that the configurations have been added to DSPortal. 4. Once confirmed, send a message to #fn-release-team using the suggested text in Column H, Slack Message 2 to inform them of the update. | Slack Message 1: Hi DS. We need to set up the configuration for Modes and Tags in DSPortal in preparation for Release QA Whiteglove for the upcoming (RELEASE VERSION) release. Slack Message 2: :announcement-1: Just a heads up, we have set up (RELEASE VERSION) Modes & Tags in DSPortal in preparation of WhiteGloves on the weekend. |  |  | Must be done before PD, ideally the day of PD.
|  | AFTER 8PM ET PENCILS DOWN |  |  | AFTER 8PM ET PENCILS DOWN | AFTER 8PM ET PENCILS DOWN | AFTER 8PM ET PENCILS DOWN | AFTER 8PM ET PENCILS DOWN
OPS | Remove Temporary Allow Listed - 8PM ET | TODO | 2025-07-19 |  | Commit CL: 12345 Slack: LINK | 1. Go to this P4 file path //Fortnite/Main/FortniteGame/Build/p4lockdown/lockdown_config.ini 2. Check out the file and Open. For the description, use the suggested text in Column H --> 3. In the file, search for [ReleaseA-Lockdown-Hardcore] and [ReleaseB-Lockdown-Hardcore] 4. Find the list that corresponds to CHECKLIST_VERSION 5. Delete the names that come after Stan.Hormell (ensure there is no comma after Stans name). 6. Navigate to the [Release-Archive-Hardcore] section and remove the version corresponding to this checklist 7. Save and commit. 8. Post in the #fn-Release-CHECKLIST-VERSION-ext Slack Channel using the suggested text in column I | 1. Removing Temporary Allow Listers for CHECKLIST_VERSION Pencils Down 2. Removing CHECKLIST_VERSION from [Release-Archive-Hardcore] #jira none #rnx | :announcement-1: CHECKLIST_VERSION is now Pencils Down and temporary allowlisted permissions have been revoked:pencilsdown: -- Everyone must now submit any changes through the Submit Tool using the standard integration process.
OPS | Enable Robomerge Gate - 8PM ET | TODO | 2025-07-19 |  | Commit CL: 12345 This will create a post in the integrations channel if someone attempts to robomerge a change up to the Pencils Down branch | 1. Go to this P4 file path //GamePlugins/Main/Programs/RoboMerge/data/fortnite.branchmap.json 2. Check out the file and Open. For the description, use the suggested text in Column H --> 3. In the file, search for EDGES 4. Set "from" to NEXT_VERSION 5. Set "to" to the CHECKLIST_VERSION 6. Use the Robomerge preview feature to ensure that there are no parsing issues (right click the pending CL in p4v and choose Robomerge Preview Graph from UE Toolbox) eg. https://robomerge.epicgames.net/preview/33192043 7. Save and commit. [example] | Adding CHECKLIST_VERSION <~~ NEXT_VERSION Robomerge Gate Alert #jira none #rnx #fyi stan.hormell, swarm-ue-build-reviews
OPS | Move Festival CMS job to the next Release | TODO | 2025-07-19 |  |  | Update the Scheduled builds and move the `update-local-cms` to the next release. This job should only be running in one branch at a time. [Thread] 1. Checkout and open //Fortnite/Main/FortniteGame/Build/Streams/fortnite-release-CHECKLIST_VERSION.stream.json 2. Set the schedule to false for "Update local CMS data" 3. Checkout and open //Fortnite/Main/FortniteGame/Build/Streams/fortnite-release-NEXT_VERSION.stream.json 4. Set the schedule to true for "Update local CMS data" | Disabling update-local-cms schedule in CHECKLIST_VERSION, and enabling in NEXT_VERSION #jira none #rnx #fyi stan.hormell, swarm-ue-build-reviews
Pre-Candidate Build
| By Cert Submission: | IN PROGRESS
OPS | Identify team for release day and update Release Request | TODO | 2025-07-19 |  | Slack Links: LiveOps ReleaseQA Community Tech Console | 1. Message the below groups using the suggested text in Column H. a. LiveOps b. ReleaseQA c. Community d. Release Management - Row 24 e. Tech Console | Hey INSERT_GROUP Team! Who is your representative for the upcoming CHECKLIST_VERSION release? Once you know, please add the name(s) to the corresponding place in the `People On Duty` section of REAL-1234 's description. :ty: in advance! | Release Managers: Hey PERSON_LISTED_IN_SHEET: You all good to own the upcoming CHECKLIST_VERSION release? Looks like you are on the FN Release Schedule for it. If so, I'll make sure to get you added to our REAL-XXX ticket for tracking. Thanks! | Yes
OPS | Kick Cert Build | TODO | 2025-07-19 |  | Last Committed CL: 12345 WPB CL: 12345 NDR CL: 12345 Nightly CL: 12345 | 1. Commit remaining changes 2. Ensure World Partition Build & Nightly Data Rebuild jobs have been kicked at a CL AFTER the last committed change a. If they kicked too early, cancel and rekick using their templates b. Make sure the canceled jobs have completed before kicking the new jobs or issues can arise 3. Ensure both jobs complete with no issues a. if errors/warnings, escalate (WPB - Sebastian Lussier, NDR - INSERT) 4. Kick Nightly build at a CL AFTER the 2 above jobs
OPS | Update Scheduled Builds. SSB Current and Next | TODO | 2025-07-19 |  | Commit CL: 12345 Slack: LINK Nightly is generally Cert build. This action to disable branch SSB should occur by EOD before Cert. We've seen that the SBB can stomp builds if we had critical rebuilds needed on Cert Sub day. | Wiki: https://confluence.it.epicgames.com/display/FORT/Enabling+and+Disabling+Scheduled+Horde+Builds 1. Go to here in P4: //Fortnite/Main/FortniteGame/Build/Streams/fortnite-release-CHECKLIST_VERSION.stream.json 2. Select this file as well as the 2 .json files for the following 2 branch versions 3. Check out and open file 4. Create a shelf using the suggested P4 Description in Column H --> 5. Find: Scheduled Standard Build with Build Health 6 In the ""schedule"" section, change ""enabled"": true to ""enabled"": false 7. Save and commit in P4 8. Send courtesy message in Slack to #buildfarm-support-ext using the suggested P4 Description in Column I --> | Disabling Scheduled Standard Build job for Release-CHECKLIST_VERSION Enabling Scheduled Standard Build job for Release-NEXT_VERSION & Release-NEXT+1_VERSION #jira none #rnx #fyi stan.hormell, swarm-ue-build-reviews | Hi Build Farm! Just wanted to inform you that we disabled the Scheduled Standard Build job for CHECKLIST_VERSION and enabled it for NEXT_VERSION & NEXT+1_VERSION at CL XXXXX. That's all!
Release Candidate Build (Locked in)
IN PROGRESS
OPS | Generate Optimized Patches (chunkdbs) for all platforms delpoying | TODO | 2025-07-20 |  | Horde Job(s): LINK | Wiki: https://confluence-epicgames.atlassian.net/wiki/spaces/ERM/pages/98213590/Generate+Optimized+Patches 1. Go to the Patching tab of Main-Horde 2. Select the 'New Job' button, and choose the Generate Optimized Patches (chunkdbs) template. 3. Set the Build Version to the ++CL that is being released (from the REAL-XXXX ticket) 4. Check Generate ChunksDBs Against Rollback Labels. 5. Set Platforms to any of the platforms that apply to the ++CL in step 3. a. Process update – run this for all platforms that are patching 6. Start Job 7. Re-run steps until all 4 platforms and their corresponding ++CLs are captured a. escalate errors/warnings to #fn-tech-ext (if applicable) for fixes | Hi INSERT_PERSON I'm getting some errors while running the Optimized Patch Job for our CHECKLIST_VERSION INSERT_ERRORING_PLATFORMS clients. Wondering if someone can take a look and advise on next steps.
OPS | Final Client Build Protection | TODO | 2025-07-20 |  | CL(s) Protected: - 12345 | Wiki: https://confluence.it.epicgames.com/display/FORT/Build+Protection 1. Go to the Build Protection Sheet, duplicate the Template and rename the copy to CHECKLIST_VERSION 2. Populate the following fields for each unique CL we intend of releasing a. Version/Team = CHECKLIST_VERSION. Only use a team name if another team asks to protect a certain build (ex. winterbreak) b. Platform = Platform (All or individual platforms) c. Build Version = ++CL (from Horde / Release Ticket) d. Stage Job (Android) = Link to Android Promotion Job from Main Horde e. Keep Release Candidate Script = Link to the job from Main Horde (Clients Only) 3. Check the corresponding box once complete For UEFN Client Protection: - Rerun the UEFN Client CL with Windows checked off
OPS | Final Server Build Protection | TODO | 2025-07-20 |  | CL(s) Protected: - 12345 | Wiki: https://confluence.it.epicgames.com/display/FORT/Build+Protection 1. Go to the Build Protection Sheet, duplicate the Template and rename the copy to CHECKLIST_VERSION 2. Populate the following fields for each unique CL we intend of releasing a. Version/Team = CHECKLIST_VERSION. Only use a team name if another team asks to protect a certain build (ex. winterbreak) b. Platform = Linux c. Build Version = ++CL (from Horde / Release Ticket) d. Stage Job (Android) = Link to Android Promotion Job from Main Horde e. Keep Release Candidate Script = Link to the job from Main Horde (Clients Only) 3. Check the corresponding box once complete For UEFN Server Protection: - Rerun the UEFN Client CL with Windows checked off | <--- This is a straight dupe of client... need to update for server
OPS | Copy entire build(s) to Milestone Archive | TODO | 2025-07-21 |  |  | Wiki: https://horde.devtools.epicgames.com/stream/fortnite-main?tab=Misc This is a copy of the entire build as it appears in the build folder to keep from having to rebuild if it is needed. Archive Fortnite Build CLs (New Job > Archive Fortnite Build > add in the ++CLs > Start Job). For Clients archive the clients and the Content Worker. This can later be found at : P:\Builds\Archive\Fortnite-Releases\Milestone++Fortnite+Release-CHECKLIST_VERSION-CL-12345678 |  |  | Maybe?
OPS | Disable remaining unneeded builds | TODO | 2025-07-20 |  | DO THIS THE DAY BEFORE RELEASE Commit CL: 12345 | 1. Go to here in P4: //Fortnite/Main/FortniteGame/Build/Streams/fortnite-release-CHECKLIST_VERSION.stream.json 2. Check out and open file 3. Create a shelf using the suggested P4 Description in Column H --> 4. Find "Nightly Build with Build Health" 5. In the "schedule" section > change "enabled": true to "enabled": false 6. Repeat steps 4-5 for: a. "Nightly Data Rebuild" b. "World Partition Build" c. "Juno Limited Build" d. "Export Item Shop" `nightly-export-item-shop` (Does not need to be enabled on Dev-FN-XX) f. "Build Tests - Twice Weekly" g. "Build Tests - Thrice Weekly" h. "Nightly UEFN Data Rebuild" i. "compatlabnightly" 7. Save and commit in P4 9. Send courtesy message in Slack to #buildfarm-support-ext using the suggested P4 Description in Column I --> | Disabling the below jobs for Release-CHECKLIST_VERSION: - Nightly Build with Build Health, Nightly Data Rebuild, World Partition Build, Juno Limited Build, Export Item Shop, Build Tests - Weekly, Build Tests - Twice Weekly, Build Tests - Thrice Weekly, Nightly UEFN Data Rebuild, CompatLabNightly #jira none #fyi stan.hormell, swarm-ue-build-reviews #rnx | Hi Build Farm, just wanted to inform you that we disabled the below jobs for CHECKLIST_VERSION at CL XXXXXX. - Nightly Build with Build Health, Nightly Data Rebuild, World Partition Build, Juno Limited Build, Export Item Shop, Build Tests - Weekly, Build Tests - Twice Weekly, Build Tests - Thrice Weekly, Nightly UEFN Data Rebuild, CompatLabNightly That's all!
Signoff and Submission
IN PROGRESS
OPS | Verify no new client CLs have been introduced between Final Client WhiteGlove and Final Server/MCP WhiteGlove tests. | TODO | 2025-07-20 |  | Swarm Delta: https://p4-swarm.epicgames.net/files/Fortnite/release-CHECKLIST_VERSION?range=@FINAL_CLIENT_CL,@FINAL_SERVER_CL#commits | 1. Go to the Final Client WG in the #fn-release-CHECKLIST-VERSION-ext channel and note the CL(s) being tested 2. Go to the Final Server/MCP WG in the #fn-release-CHECKLIST-VERSION-ext channel and note the CL(s) being tested a. Ensure these are the intended CLs when comparing with the REAL-XXXX ticket 3. Go to Swarm and edit the link to point to the checklist version and bookend the 2 CLs above. /release-CHECKLIST_VERSION?range=@CLIENT_CL,@SERVER_MCP_CL#commits 4. Ensure all CLs have a Release Manager upvote (which means we have approved and they are not snuck in). a. You can ignore submissions from "Build Machine" 5. If there are any Client CLs, escalate in the #fn-release-mgmt-team-ext immediately
Pre-Release
IN PROGRESS
OPS | Confirm with Discovery team that the Analytics Stuff revision has been deployed to Live | TODO | 2025-07-20 |  | Slack: LINK | 1. Using the DAD request thread, confirm with Disco team that the Analytics Stuff was updated appropriately for the pending release | Hello again! Just have a checklist item for today to confirm that the Analytics Stuff revision has been deployed to Live and there is no further work expected to finalize for our CHECKLIST_VERSION deploy tomorrow? We all set and ready to :rock: & :rollcat: ? |  | Yes
OPS | Verify Release Request is accurate | TODO | 2025-07-20 |  |  | 1. Look at REAL-XXXX Ticket to ensure everything is up to date and any last minute changes have been captured ex. Clients/Backends/PatchSizes, Release Callouts (migrations, etc) |  |  | Maybe?
OPS | Release Owner: Log into all deploy-related tools | TODO | 2025-07-18 |  | Set a scheudled reminder for the deploy owner 2 days prior during their core hours (or if they are OOO at that time, find a time when they are available before the deployment) | 1. Log into the following services to ensure their platform is functioning and that you have access and will not be blocked at the last minute. Internal a. Swarm b. LightSwitch2 c. DS Portal d. Horde e. Grafana f. Analytics g. Data Asset Directory (DAD) External a. PlayStation i. PlayStation 5 ii. PlayStation 4 b. Microsoft Partner Center c. Nintendo Content Management System d. Nintendo Developer Portal e. NVIDIA GeForce Now f. Amazon Luna g. Android OPPO
___ ___ __ __ ___ _ __ _ _ _ ¦ _ \ / _ \ \ \ / / o O O ¦ \ ___ ¦ '_ \ ¦ ¦ ___ ¦ ¦¦ ¦ ¦ / ¦ (_) ¦ \ \/\/ / o ¦ ¦) ¦ / -_) ¦ .__/ ¦ ¦ / _ \ \_, ¦ ¦_¦_\ \___/ \_/\_/ TS__[O] ¦___/ \___¦ ¦_¦__ _¦_¦_ \___/ _¦__/ _¦"""""¦_¦"""""¦_¦"""""¦ {======¦_¦"""""¦_¦"""""¦_¦"""""¦_¦"""""¦_¦"""""¦_¦ """"¦ "`-0-0-'"`-0-0-'"`-0-0-'./o--000'"`-0-0-'"`-0-0-'"`-0-0-'"`-0-0-'"`-0-0-'"`-0-0-'
Lead-up to Downtime - Deployment Owner
| Item | Status | Due buy | Done by | Temp-Notes | Perma-Notes
OPS | Set up Crash Reporter prior to release for Switch (does not apply for Switch 2) | TODO | 2025-07-21 |  |  | Wiki: https://confluence.it.epicgames.com/display/FORT/Change+Switch+Crash+Reporter+Version 1. Navigate to the below file on the P drive (easily done on a Remote Machine) P:\Symbols\Switch\LiveSymbols\FortniteClient-Switch-Shipping.nsp 2. Open the file and swap in CHECKLIST_VERSION & the ++CL for the Switch Client 3. Save and you are done
OPS | Final review of Release Request information | TODO | 2025-07-21 |  |  | 1. Make sure all build artifacts match expectations and what was whitegloved by Release QA 2. Make sure all checklist items were completed
OPS | Review initial build info setup | TODO | 2025-07-21 |  |  | 1. Make sure Android and Switch candidates are propped up in Live Build Info 2. Make sure Switch build info was removed from NSCert Build Info
OPS | Verify Generate Optimized Patch was run against the correct build and finished successfully. | TODO | 2025-07-21 |  |  | Wiki: https://confluence.it.epicgames.com/display/FORT/Generate+Optimized+Patches Process update – check this for all platforms that are patching, not just (Android, PC, PS4, XB1, IOS) Escalate any issues to the #fn-tech-ext channel
OPS | Tag Live Ops to Disable Alerts. | TODO | 2025-07-21 |  | [Downtime minus 40 mins] | Only LOps has access to the alerts. Ping whomever is on call to disable. Otherwise there are fireworks. |  |  | Maybe?
OPS | Disable server scaledown ("Pin" server scaling) | TODO | 2025-07-21 |  | [Downtime minus 35 mins] | Navigate to DS Portal for Live > Click the Scale Down toggle to OFF (top right) to keep servers from scaling down during downtime. Be sure to post in #fn-release-deploy-ext that this step was done.
OPS | Disable Matchmaking | TODO | 2025-07-21 |  | [Downtime minus 30 mins] | Option 1: MMS Admin Portal toggle button (Navigate to the Live MMS AP page > In the "Playlist Restrictions Configuration" section change "disableAllMatchmaking": to true > Hit the Update button) Option 2: Hotfix directly through Admin Portal System Files DefaultGame.ini [/Script/FortniteGame.FortGameInstance] bBattleRoyaleMatchmakingEnabled=false
OPS | Start downtime Aegis Prewarm | TODO | 2025-07-21 |  |  | 1. Go to https://aegis-web.bfda.live.use1a.on.epicgames.com/prewarm 2. Queue up 1000 Links for all Platforms
OPS | Start "[Thread] Updates on CHECKLIST_VERSION Fortnite release:" in #pub-fortnite slack channel | TODO | 2025-07-21 |  | Update with latest big callouts. | Example: https://epicgames.slack.com/archives/C044WR7HZDG/p1691482159647189 [Thread] Updates on CHECKLIST_VERSION Fortnite release: (post) Matchmaking Disabled at 3:30 AM ET LightSwitch Down at 4:00 AM ET Deploy started on time (4am ET) and so far things are going smoothly. Estimated uptime is ~5/5:15am ET. Will crosspost any major updates or issues here. |  |  | Yes
OPS | Check in "Go Live" Hotfix config and run Preview job | TODO | 2025-07-21 |  |  | Swarm link prepped by Release QA the night prior to release morning Hotfix Deploy Runbook
During Downtime - Deployment Owner
| Item | Status | Due Buy | Done by | Temp-Notes | Perma-Notes
OPS | Confirm FN Lightswitch down | TODO | 2025-07-21 |  |  | Validate via Login data that downtime has started properly. (Success by Region/Platform in particular)
OPS | PS4/PS5 Client Publish SIEA (07022) | TODO | 2025-07-21 |  | New process has PS4/PS5 scheduled like Switch/XB1/XSX | Tip: You might have to be on VPN AND Remote Desktop if performing from a location that does not have a allowlisted IP address. Log in to PlayStation Partners portal then follow these steps in the PS5 section.
OPS | PS4/PS5 Client Publish SIEE (07669) | TODO | 2025-07-21 |  | New process has PS4/PS5 scheduled like Switch/XB1/XSX | Tip: You might have to be on VPN AND Remote Desktop if performing from a location that does not have a allowlisted IP address. Log in to PlayStation Partners portal then follow these steps in the PS5 section.
OPS | Deploy MCP | TODO | 2025-07-21 |  |  | MCP Deploy Runbook
OPS | Confirm MCP version is reflected in Fortnite Queue Worker Prod11 | TODO | 2025-07-21 |  | Queue Worker now auto deploys when we trigger an MCP deployment. We no longer need a manual job for QW. However we need to still confirm that QW updated correctly. | Fortnite Queue Worker Prod11 in TeamCity
OPS | Deploy "Go Live" INI Hotfix config | TODO | 2025-07-21 |  | (make sure this is done before server deploy to ensure hotfix config is pulled correctly) | Swarm link prepped by Release QA the night prior to release morning Hotfix Deploy Runbook
OPS | PC Client Promotion (also select WindowsGFN/WindowsLuna if unchecked) | TODO | 2025-07-21 |  | PC/Android can be the same job if build labels match (Client deploy should align with Downtime) | Client Deploy Runbook
OPS | Android Client Promotion | TODO | 2025-07-21 |  | PC/Android can be the same job if build labels match (Client deploy should align with Downtime) | Client Deploy Runbook
OPS | iOS Client Promotion (wiki linked) | TODO | 2025-07-21 |  |  | 1. Update the Live-IOS build label to the new ADPID version in Admin Portal. 2. Ensure that the ++ version is listed in LiveCompat. 3. Run GitHub Action Workflow to promote to AltStore 4. In App Store Connect release the App Store update
OPS | Deploy Servers | TODO | 2025-07-21 |  | Use the "Fast" option. When this is checked, hosts will immediately start the IPU process | Server Deploy Runbook
OPS | Deploy "Go Live" Discovery DAD Hotfix | TODO | 2025-07-21 |  |  | Go Live Revision is found in the Game Config sheet.
OPS | Confirm Switch/XSX/XB1/PS4/PS5 (our scheduled platforms) new versions are populating | TODO | 2025-07-21 |  | (Client deploy should align with Downtime)
OPS | Run Live promotion job for iOS, PS4, PS5, XB1, XSX, and Switch (no impact to Live players) | TODO | 2025-07-21 |  | Escalate any issues to the #fn-tech-ext channel | Example Thread: https://epicgames.slack.com/archives/C044TN4LVFT/p1667291267646149 Example Deploy: https://horde.devtools.epicgames.com/job/6360d85fe271e75dea797f32 22.30 Go Live PS4/PS5/XB1/XSX/Switch - Non-Player facing
OPS | Make sure Live Build Info is cleaned up (old fix versions no longer supported) before we go lightswitch up | TODO | 2025-07-21 |  | Expand Live and Live-Compatible sections making sure older releases are not present. Every major release should be a forced patch. | https://adminportal.ol.epicgames.net/launcher/buildinfo/app/Fortnite Ensure that the Promotion Labels section correctly displays the new Live versions for all platforms (This must be done before Light Switch Up) * Build Info for Windows and Shipping-Android should always be real and never fake/dummy/placeholder. * IOS, PS4, PS5, XB1, XSX, and Switch will need to be manually updated using the labels from the Live Compat section ** Be sure to delete previously live Build Info from Live Compatible labels (Excluding 13.40 for now)
OPS | Scaling servers in downtime | TODO | 2025-07-21 |  | [Uptime minus 15 mins] | Note: Servers can take 10-15 min to scale up, please plan appropriately Wiki: https://confluence-epicgames.atlassian.net/wiki/spaces/ERM/pages/98206124/Scaling+Servers+for+Deployments
OPS | Make sure all Deploy Strategy callouts are finished before we go lightswitch up | TODO | 2025-07-21 |  |  | Refer to Release Ticket
OPS | Additional checks before fully going Lightswitch Up | TODO | 2025-07-21 |  |  | "Additional checks before fully going Lightswitch Up: -Make sure patch has been caught on all platforms by Release QA and that live patch sizes were close to estimates/not egregiously big -If there are brand new non-brcore fleet LTMs going live at Lightswitch Up, confirm we are good with prescaling -Ensure that any QA callouts are okay to come LS Up with, or have a SH that we can associate to each callout as needed -Make sure Live Ops and Community owners approve going Lightswitch Up"
OPS | Re-enable Matchmaking if the MMS Admin Portal toggle approach was used to Disable Matchmaking above. | TODO | 2025-07-21 |  |  | MMS Admin Portal toggle button (Navigate to the Live MMS AP page > In the "Playlist Restrictions Configuration" section change "disable AllMatchmaking": to false > Hit the Update button)
OPS | Fortnite Lightswitch Up. Put "Fortnite is online" in the message box | TODO | 2025-07-21 |  |  | USE EXTREME CAUTION HERE: link to Lightswitch page * Status = Up (for lightswitch UP) * Message = Fortnite is online * Add Actions = Fortnite_Free_Platforms * Create Event
Post-Release - Deployment Owner
| Item | Status | Due Buy | Done by | Temp-Notes | Perma-Notes
OPS | Tag Live Ops to ReEnable Alerts. | TODO | 2025-07-21 |  | [Uptime plus 30 mins]
OPS | End of deploy callout | TODO | 2025-07-21 |  |  | Post the following message in the #fn-release-deploy channel once we are lightswitch up: "Friendly reminder that for all general weirdness callouts from this point forward that are unrelated to the live whiteglove to please use #fn-release-CHECKLIST-VERSION" |  |  | Maybe?
OPS | Monitor Live! | TODO | 2025-07-21 |  |  | Monitor the related release slack channel and thread each one with an acknowledgement (most callouts will come from EU community): -If high urgency: suggest making it a SH -If low urgency: tag appropriate producers/owners to have a look as soon as they get on in normal hours
OPS | Update Hotfix Form/Slack Webhook to new release | TODO | 2025-07-21 |  | Scroll to the "Then: Send Web Request" and edit that entry. Update the webhook, and make sure to Save the changes. Then make sure to Publish. | https://api.slack.com/apps/A044VB8SXFV/incoming-webhooks? Add webhook url to FNR automation job: https://jira.it.epicgames.com/secure/AutomationProjectAdminAction!default.jspa?projectKey=FNR#/rule/661
OPS | Add "Planned Release Slots" bookmark to slack channel | TODO | 2025-07-21 |  | We should move this to channel creation. Also probably need to review the miro content itself | Add "Planned Release Slots" bookmark to the now live release slack channel with a link to the Planned Release Slots Miro board |  |  | Yes
OPS | Create HF Jira for each HF week | TODO | 2025-07-21 |  |  | Example: ERM-26491 |  |  | Yes
OPS | Set Slack channel Topic to Hotfix Request Form | TODO | 2025-07-21 |  |  | Example: Need a Hotfix? https://epic.gm/Hotfix ~ Email `release-team-oncall` to page Release-Team outside of office hours |  |  | Yes
OPS | Do a manual post in #fn-live-updates that mentions we are up and copies in the ship list that should be pinned in the related release channel. | TODO | 2025-07-21 |  |  | Example: Good morning! We deployed CHECKLIST_VERSION this morning. Game opened up at 5:30 AM ET for players. CHECKLIST_VERSION Ship List :ship: * ship list notes here |  |  | Yes
OPS | Change JIRA Release from Unreleased to Released | TODO | 2025-07-21 |  |  | Do nothing with any issues still on the release. OOB may linger.
OPS | Update Release Log and Release Request | TODO | 2025-07-21 | [5 empty] | Yes
OPS | Enable server scaledown ("Unpin" server scaling) after server usage levels off closer to what it was pre-downtime. | TODO | 2025-07-21 |  | [Uptime plus 2 hours] Check in with LiveOps first. | Navigate to Autoscaler for Live > Click the Edit checkbox > Set "Can Scale Down?" to Yes Be sure to post in #fn-release-deploy-ext that this step was done.
OPS | Zero Out AutoScaler Scaler Capacities | TODO | 2025-07-21 |  | Do this when you unpin | https://fm-as-scale-fn-prod.ol.epicgames.net/fleet/live/scalecapacity
OPS | Send first Post-Deploy thread to #dev-roadmap-review | TODO | 2025-07-21 |  | 1. 7am 2. 11am - Contact perf and get release updates to send out. 3. Afternoon 4. Next Day *Add Slack reminders for the email updates | List of Reports Each timestamp is a reply to the original thread! |  |  | Yes
OPS | Set timed post for 2:30PM ET to: Post in #buildfarm-support-ext to remove the previous release version | TODO | 2025-07-21 |  | Make sure to use the timed post feature in slack to send it at 2:30 PM ET. | Reach out to Build Farm Support via #buildfarm-support-ext channel in slack and ask them to remove the previous branch from horde after the deploy is complete |  |  | Yes
OPS | Make sure the Post Deploy Tracker has Stability information in time for the 10:00AM ET Stability Sync | TODO | 2025-07-21 | [5 empty] | Yes
OPS | Send Day-2 Post-Deploy thread to #dev-roadmap-review | TODO | 2025-07-22 |  |  | Reply to the original thread! |  |  | Yes
Archived Tasks
| Item | Status | Due by | Done by | Temp-Notes | Perma-Notes
OPS | Pre-upload symbols for the following (Within 24 hours of deployment) | TODO | 2025-07-20 |  | *No longer needed per #on-crashreporter-ext | Wiki: https://wiki.it.epicgames.net/display/FORT/How+to+Index+Symbols+Manually+for+Crash+Reporter 1. Navigate to the CrashReporter_Symbol-Indexer folder and copy to your computer 2. Open the _Windows file by Right Click > Run With Powershell 3. Input the version number in the format XX.YY (Not XX.YY.Z) and hit enter CHECKLIST_VERSION 4. Input the CL from the REAL-XXXX Ticket (no ++) and hit enter 5. Repeat for Switch, Android, IOS & Linux
| Confirm MCP deploy percentage with OGS (tag Pete Axt & Joe Pintozzi) and Live Ops. WIKI |  | 2025-07-20 |  | Slack: LINK | 1. Make a post in #epic-live-operations-ext or #on-dbs-game-services-ext using the suggested text in Column H | @Joe Pintozzi @Pete Axt Just confirming we are targeting 50% DeployHostPercentage during downtime as usual for the CHECKLIST_VERSION MCP deploy tomorrow? |  | Yes
| Create Bug Bids Page |  | 2025-07-17 |  | Bug Bids Page: LINK | 1. Go to the previous version's Bug Bids Page (here) 2. Click "..." > Copy > Copy 3. Change title to Bug Bids for CHECKLIST_VERSION > Publish 4. Note the current values in the Issues Left column 5. Edit the page > Update the hard coded HL-1w and HL dates as per the FN Schedule 6. Clear the hardcoded values in HL-1W and HL columns (highlight and delete) This section is borked until the <> is re-added back. Need to do manually until then :((((( 7. Select the <> icon to open in source editor 8. Find the version you copied from, replace all with the version you want > Apply > Update 9. Ensure the values have changed |  |  | Yes
| Schedule Send Bug Bids Email 10 days prior to Hard Lock date at 10:30am |  | 2025-07-17 |  | Send scheduled for DATE | 1. Go to GMail and compose a new email 2. Send email using the suggested text in Column H 3. Link the bug bids page to the blue text 4. Change Day MM/DD to the date of review (monday the week of HL) 5. Once done, hit the drop down arrow on the blue Send button > Schedule Send 6. Pick a Date & Time > 10 days prior to Hard Lock date at 10:30am (See Cell F2) 7. Schedule Send 8. Go to your gmail > Scheduled (below sent) and review the preview to ensure it is all correct 9. Paste the scheduled send info in column F for reference | The CHECKLIST_VERSION Bug Bids wiki has been created and is ready for you to enter your bids! We will start reviewing at morning sync next week on DAY MM/DD. Reminder, there's a link on the top of this page you can use to look at historic fix rate data for your components, which you can use to reason about what your teams can realistically tackle leading up to CHECKLIST_VERSION. Past Bug Bid pages are also still available for review under the Release Accountability parent page. CHECKLIST_VERSION Dashboard: [Link] Doing this thinking now, ahead of the hectic bugfix stage, will help identify rational targets you can use to guide triage activities & tradeoff decisions. Thanks, Release Team | TO: Release-Team@epicgames.com CC: FN-Prod-All <FN-Prod-All@epicgames.com>, FNE Release <fne-release@epicgames.com> Subject: Bug Bids for CHECKLIST_VERSION | Yes
| (Joe) I would just completely kill this line in favor of the Build Protection line just above. Run Keep Release Candidate job for all final client candidate CLs. |  | 2025-07-19 |  | PLATFORM_1: HORDE_JOB_LINK PLATFORM_2: HORDE_JOB_LINK PLATFORM_3: HORDE_JOB_LINK | 1. Go to the REAL-XXXX ticket for this release to see the final candidate CLs 2. Go to the Promotions tab of Main Horde 3. Select the blue New Job button in top right 4. Change template dropdown to Keep Release Candidate 5. Put the first CL in the Change field and set the associated Promote Platforms field. Then Start Job. a. Re-Run for all Client CLs with their associated Promote Platforms field.
| Verify the Android APK allowlist is in the game config file |  | 2025-07-20 |  | Release Team no longer needs to send hotfixes to update CRC values when we ship new Android client builds. The 13.40 values need to stay, but the Android APK Whitelist hotfixes no longer function in 23.50+ . This is now being done on the AntiCheat side via Dragonfly. | Verify it is in the game config file
| Review Android APK allowlist syntax is included and correct in Release QA swarm link and in PredeployA files |  | 2025-07-21 |  | Release Team no longer needs to send hotfixes to update CRC values when we ship new Android client builds. The 13.40 values need to stay, but the Android APK Whitelist hotfixes no longer function in 23.50+ . This is now being done on the AntiCheat side via Dragonfly.
| Create a Jira for StW Calendar/Store to be update/reviewed (CN/RoW) |  | 2025-07-17 |  |  | Assign to Dav Harnish and CC Henry Meredith in comments https://jira.it.epicgames.net/browse/FORT-247162
| Check Android APK size and make sure it is under 150 MB |  | 2025-07-19 |  |  | Look at APK in the build folder
| Create a tab in FN Playlist Planning sheet and let stakeholders know in #fn-release-playlistplanning-ext that it now exists |  | 2025-07-17 |  |  | https://confluence.it.epicgames.com/display/FORT/Playlist+Planning Note: If its a .10 release, spin up a thread. If its not, then mark this task as N/A.
| Schedule Meeting: Release Notes Signoff |  | 2025-07-18 |  | No Release Notes! | Thurs. of CertSub week
| Release Notes: Initial Setup and Email Sent |  | 2025-07-18 |  | No Release Notes!
| Schedule Calendar Reminders: Release Notes Section Owners |  | 2025-07-18 |  | No Release Notes! | 1 each day for 2 document days of release notes
| Order breakfast for morning of publish day |  | 2025-07-16 |  | Please bring this back!!!
| Send initial IOS Submission email |  | 2025-07-16
| Update Google Play Roadmap email (if applicable) |  | 2025-07-16 |  |  | to: Dan Song <mtd@google.com(opens in new tab)> Lawrence Koh <lawrencekoh@google.com(opens in new tab)> CC release-team Jocelyn Hans
| Send Release Notes 1st Draft to FN-Release-Updates |  | 2025-07-16 |  | No Release Notes!
| Forward CN patch notes to EGC |  | 2025-07-19 |  | No Release Notes! | Forward version patch notes for China to Martin Yu. Martin will review and deliver to Tencent.
| Add IOS Whitelist Hotfix to MobileCert |  | 2025-07-20
| Check iOS Compressed File Size |  | 2025-07-18 |  | Compressed File Size: MB Previously in 13.40 Release flagged if greater than 200 MB. Compressed sizes have increased in allowance from Apple. We should still note what the size is and report to tech-mobile Jira for investigations is FORT-772296 This process may be something we can remove, but need to keep an eye out for a few releases. [thread] | 1. Go to https://appstoreconnect.apple.com/apps 2. Select Fortnite 3. Select TestFlight 4. Select the RC candidate Version and Build 5. View the Build Metadata for Compressed File Size 6. Record the size and pass along to Tech-Mobile
| Audit MobileCert environment config for potential cert blockers |  | 2025-07-19
| Configure MobileCert Build Info |  | 2025-07-19
| MobileCert: MCP Update |  | 2025-07-19
| MobileCert: Server Promote |  | 2025-07-19
| Cert Submission: iOS |  | 2025-07-19
| Send email notifying Apple contacts that build is uploaded |  | 2025-07-19
| Send email notifying Google contacts that build is uploaded |  | 2025-07-19
| Remove MobileCert Redirect |  | 2025-07-20
| Live: Update iOS Build Info |  | 2025-07-20
| Remove Android Build Info from MobileCert |  | 2025-07-20
| Live: Update LiveCN Build Info |  | 2025-07-20 |  |  | Deploy will be coordinated with TC in #ext-fncn-live in Slack. TC will flip WeGame switches. THIS STEP IS ONLY NEEDED IF STAGING THE CN BUILD FAILED.
| Update Apple Cert Timing Tracker |  | 2025-07-21
| Update EULA if requested by Legal |  | 2025-07-18
VVV To be Re-Added Once iOS comes back VVV
| Make sure PredeployA Hotfix Files are set back to appropriate Android Whitelist and IOS Banning syntax for LOPS to copy at time of release |  | 2025-07-20 |  | Only Android? | Android: Whitelist syntax needs to be added IOS: Remove the following: [/Script/FortniteGame.FortGameModeZone] BanCodeAction_20=(AnyReason=2, UnsignedIPA=0) BanCodeAction_28=(AnyReason=2, NoIOSCryptInfo=0)
| Make sure PredeployA Hotfix Files are set back to appropriate Android Whitelist and IOS Banning syntax for QA to not be blocked |  | 2025-07-21 |  |  | Android: Whitelist synatx needs to be removed IOS: Add the following: [/Script/FortniteGame.FortGameModeZone] BanCodeAction_20=(AnyReason=2, UnsignedIPA=0) BanCodeAction_28=(AnyReason=2, NoIOSCryptInfo=0
| Determine if release breaks Replays and/or if we should whitelist any old CLs |  | 2025-07-18 |  | https://wiki.it.epicgames.net/pages/viewpage.action?spaceKey=FORT&title=Replay+Whitelisting | Should be considered if we are breaking replays of a major Live event from the previous release Ask Shak or Matt Grandstaff
| Test verify PS4 remaster jobs have no errors or warnings |  | 2025-07-18 |  |  | Nightly Job "Publish PS4 Remaster Submission Packages (SIEA (07022) Only)"
| Confirm all Non-Unity warnings and errors are fixed or benign |  | 2025-07-18
| PS4: Update R:\Analytics\sony_version.csv |  | 2025-07-21 |  | I refuse | Instruction Doc
| Make sure PredeployA Hotfix Files are set back to appropriate Android Whitelist and IOS Banning syntax for QA to not be blocked |  | 2025-07-21 |  |  | Android: Whitelist synatx needs to be removed IOS: Add the following: [/Script/FortniteGame.FortGameModeZone] BanCodeAction_20=(AnyReason=2, UnsignedIPA=0) BanCodeAction_28=(AnyReason=2, NoIOSCryptInfo=0
| [24 hrs before] Inform Tencent and Community |  | #REF! |  |  | 24 hrs before - Inform in #ext-fncn-live @Sula Yu and CN QA deply captain Check EGC QA Checklist > Captain tab for additional @ https://docs.google.com/spreadsheets/d/1nUx7qP1aLLU6D1VVv0Q4mx18aMMG_tz5vmQC0Z9wxgc/edit?usp=sharing
| [24 hrs before] Release JIRA |  | #REF! |  |  | Link Release management Jira ticket here
| [2 hours befire] Hotfixes Checked In and Previewed |  | #REF! |  | Check fn-release-team around 4PM ET | RQA will provide a Swarm shelf to approve and merge around 4PM ET https://docs.google.com/spreadsheets/d/1w5PQcnciR-lbbU6H6m0aaqgiFWNRbttSr7uEoCmKUzk/edit#gid=2063781583
| [2 hours before] Schedule Downtime (Fortnite) |  | #REF! |  | Schedule sometime before 4:40pm | https://adminportal-website-management.ol.epicgames.net/lightswitch2/schedule/fortnitelivecn?server=Lightswitch&moduleName=lightswitch
| [1 hrs before] Verify Client, Server, and MCP for release |  | #REF! |  |  | Pinged in Release Private if unsure of any changes
| [1 hrs before] Internal Release Email |  | #REF! |  |  | fncn-live@epicgames.com, fn-live, online-infra, global-live-deployments
| [35 min before] Turn off FN CN Alerts |  | #REF! |  | Poke liveOPS at MMS disable | Request liveOPS pause FN Grafana integration in OpsGenie https://epicgames.app.opsgenie.com/teams/dashboard/76f730d9-7346-4f83-b599-ab3589ba2fce/integrations
| [35 min before] Alternatively, Set False to True for Playlist Restrictions Configuration section at https://adminportal.ol.epicgames.net/fortnite/profileProxy?server=Fortnite%20China&moduleName=fortnite Click MMS at top and scroll down to Playlist Restrictions Configuration Set disableAllMatchmaking to true |  | #REF! |  |  | 35mins before LS down Edit directly under Admin Portal https://adminportal-website-management.ol.epicgames.net/fortnite/systemFiles Make sure you are in "Fortnite China" Notify fn-release-deploy (FN-Deploy Public) and Mission Control slack channels |  | For Old Hotfix Method: DefaultGame.ini [/Script/FortniteGame.FortGameInstance] bBattleRoyaleMatchmakingEnabled=false
| Item | Status | Due by | Done by | Temp-Notes | Perma-Notes
| Confirm Lightswitch down status |  | #REF! |  |  | Check status has switched to DOWN - https://adminportal-website-management.ol.epicgames.net/lightswitch2/schedule/fortnitelivecn?server=Lightswitch&moduleName=lightswitch
| Lightswitch down notifications |  | #REF! |  |  | Post message in fn-release-deploy and Mission Control slack channels
| We Games access disabled |  | #REF! |  |  | Notify ext-fncn-live to disable access for we games. More often than not this is Sula, but confirm it isn't a different Tencent employee
| Deploy "Go Live" INI Hotfix config (make sure this is done before server deploy to ensure hotfix config is pulled correctly) |  | #REF! |  |  | Can move on to MCP and Client deploys until Hotfix is done. Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy internal
| Deploy MCP |  | #REF! |  |  | Deploy %: 50% Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy internal
| Deploy MMS |  | #REF! |  |  | Done by MMS team after matcmaking is disabled - confirm with them during release sync if a deployment is being done. Loop them in when light switch down
| PC Client Deploy - Use Promotion Job (Client) |  | #REF! |  |  | Whole build string, LiveCN, only Windows. Allow Live Promotions and BPT checked Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy Public
| Server Deploy |  | #REF! |  | Make sure Hotfix is underway before Deploying Server. Otherwise servers won't get new hotfixes for possibly 4 hours. | Start immediately after hotfix deploy, due to server prep time, hotfixes should be live just prior to sessions starting Fleet: LiveCN Cohort: Main Use fast deploy option for downtime releases. Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy internal
| Item | Status | Due by | Done by | Temp-Notes | Perma-Notes
| Nvidia: reply to already existing corresponding release thread in #ue-partner-nvidia-ext with courtesy status updates |  | 2025-07-21 |  |  | Usually Douglas Valkenaar, Alexander Gustev or Andrew Saritsky - #external-nvidia channel |  |  | Maybe?
| StW Whiteglove |  | #REF! |  |  | Poke ext-fccn-live with @s to start whiteglove
| BR Whiteglove |  | #REF! |  |  | Whiteglove is completed by both Epic CN and Tencent teams separately - need confirmation from both teams of a successful check.
| If help is needed flushing buckets |  | #REF! |  | Click "Direct control panel link" in next link | https://adminportal-website-management.ol.epicgames.net/fortnite/profileProxy?server=Fortnite%20China&moduleName=fortnite
| Re-enable Light Switch Up |  | #REF! |  |  | Ready once the whiteglove has been confirmed and without any issues Update status message to Fortnite is up! Notify Sula - Access has been re-enabled. @Sula Yu please re-enable from wegames side as well Notify in Mission Control and FN-Release-Deploy - No whiteglove callout and lightswitch up
| Re-enable CN alerts |  | #REF! |  |  | Unpause FN Grafana integration in OpsGenie https://epicgames.app.opsgenie.com/teams/dashboard/76f730d9-7346-4f83-b599-ab3589ba2fce/integrations
| Post in #buildfarm-support to remove the previous release version |  | #REF! |  |  | Reach out to Build Farm Support via #buildfarm-support channel in slack and ask them to remove the previous branch from horde after CN deploy is complete
| Archive previous release Slack channel |  | #REF!

## Production Checklist
| Item | Status | Due by | Completed by | Temp-Notes | Steps To Complete | Suggested Slack Post Text (unless otherwise stated) | Suggested Slack Thread Text (unless otherwise stated) | Automation? | Additional Notes
| Pre-Candidate Build - MUST DO |  |  |  |  | 77
| By Hard Lock: | IN PROGRESS
PROD | Send Slack Review For Untriaged Pre-SH & QA High Risk JIRAs: Keep this checklist item open until closer to CERT to continue to refresh and escalate issues added | TODO | 2025-07-17 |  | Slack: LINK Last Update: - MONTH_DAY | 1. Go to the following FILTER and set the affectedVersion=CHECKLIST_VERSION 3. Spin up a thread in the #fn-release-CHECKLIST-VERSION-ext slack channel using the suggested text in column H/I --> a. Tag in the Tech component owner (currently Chris Tran / Jay Chaney) and the seasonal prod owner (row 1) b. Tag in Component owners for each JIRA in the filter c. Copy the links to the 2 filters and link them over their associated blue text Example: LINK Steps for how to easily add jiras into message in this cells note (This task would certainly benefit from an already existing workato recipe... someone just needs to set it up) | CHECKLIST_VERSION Untriaged Pre-SH & QA High Risk Review :thread: | Hi @PROD_OWNER & @Chris Tran If y'all have time in the next couple days, RM would appreciate your review of various Untriaged QA High Risk & Pre-SH JIRAs affecting CHECKLIST_VERSION. Please ensure these JIRAs have an appropriate Priority, Fix Version & Assignee set so they do not fall through the cracks. The goal of this ask is to make sure these crashes get visibility and review now, instead of potentially in a post-release shit happens. We will be doing a sweep of this dashboard periodically leading up to CERT. :ty: in Advance! PreShitHappens and QAHighRisk XXX | Yes | Workato - Component Lookup
PROD | Send Slack Review For Pre-SH & QA High Risk that are assigned to the current release: Keep this checklist item open until closer to CERT to continue to refresh and escalate issues added | TODO | 2025-07-17 |  | Slack: LINK Last Update: - MONTH_DAY | 1. Go to the following FILTER and set the FixVersion = CHECKLIST_VERSION 2. Update the thread that you created above with this filter and ask the seasonal/tech owners to review the current filter and get a pulse check on where we stand with Issues that we plan to fix in this release Example: LINK |  |  | Yes | Workato - Component Lookup
PROD | Release Content Legal Approval has Started | TODO | 2025-07-15 |  | Leave this task as In Progress until we have the final sign-off on all items in the sheet Slack: LINK | 1. Navigate to the #fn-legal-publishing-approvals-ext slack channel 2. Look for thread containing Ready For Review a. Currently by Ben Massoglia (Adam Baxter if Ben is OOO) 3. If thread is not present, send a DM to Ben Massoglia/Chris Oneil asking when that will happen
PROD | Make sure Disallow List has Started (Data Encryption) | TODO | 2025-07-19 |  | Leave this task as In Progress until we have confirmation that all items from the encryption pass have been properly encrypted or SHs have been spun up to account for leaks Slack: LINK | 1. Navigate to the #fn-encryptedassets-ext slack channel 2. Look for the thread containing Datamine Results a. Currently by Ben Massoglia (Adam Baxter if Ben is OOO) 3. If thread is not present, send a DM to Ben Massoglia asking when that will happen 4. Reminder to confirm that All FN, FNE (Creative+UEFN), JUNO, DelMar, Sparks terms are being checked
| By Pencils Down: | IN PROGRESS
PROD | Send Slack Review For Untriaged Pre-SH & QA High Risk JIRAs: Keep this checklist item open until closer to CERT to continue to refresh and escalate issues added | TODO | 2025-07-12 |  | Slack: LINK Last Update: - MONTH_DAY | 1. Go to the following FILTER and set the affectedVersion=CHECKLIST_VERSION 3. Spin up a thread in the #fn-release-CHECKLIST-VERSION-ext slack channel using the suggested text in column H/I --> a. Tag in the Tech component owner (currently Chris Tran / Jay Chaney) and the seasonal prod owner (row 1) b. Tag in Component owners for each JIRA in the filter c. Copy the links to the 2 filters and link them over their associated blue text Example: LINK Steps for how to easily add jiras into message in this cells note (This task would certainly benefit from an already existing workato recipe... someone just needs to set it up) | CHECKLIST_VERSION Untriaged Pre-SH & QA High Risk Review :thread: | Hi @PROD_OWNER & @Chris Tran If y'all have time in the next couple days, RM would appreciate your review of various Untriaged QA High Risk & Pre-SH JIRAs affecting CHECKLIST_VERSION. Please ensure these JIRAs have an appropriate Priority, Fix Version & Assignee set so they do not fall through the cracks. The goal of this ask is to make sure these crashes get visibility and review now, instead of potentially in a post-release shit happens. We will be doing a sweep of this dashboard periodically leading up to CERT. :ty: in Advance! PreShitHappens and QAHighRisk XXX | Yes | Workato - Component Lookup
PROD | Send Slack Review For Untriaged Escaped Crashes / Asserts / Ensures JIRAs: Keep this checklist item open until closer to CERT to continue to refresh and escalate issues added | TODO | 2025-07-12 |  | Slack: LINK Keep this checklist item open until closer to CERT to continue to refresh and escalate issues added | 1. Go to the following FILTER and set the affectedVersion=CHECKLIST_VERSION 3. Spin up a thread in the #fn-release-CHECKLIST-VERSION-ext slack channel using the suggested text in column H/I --> a. Tag in the Tech component owner (currently Chris Tran / Jay Chaney) and the seasonal prod owner (row 1) b. Tag in Component owners for each JIRA in the filter c. Copy the links to the 2 filters and link them over their associated blue text Example: LINK Steps for how to easily add jiras into message in this cells note (This task would certainly benefit from an already existing workato recipe... someone just needs to set it up) | CHECKLIST_VERSION Untriaged Escaped Crashes / Asserts / Ensures Review :thread: | Hi @PROD_OWNER & @Chris Tran If y'all have time in the next couple days, RM would appreciate your review of various Untriaged Escaped Crash / Assert / Ensure JIRAs affecting CHECKLIST_VERSION. Please ensure these JIRAs have an appropriate Priority, Fix Version & Assignee set so they do not fall through the cracks. The goal of this ask is to make sure these crashes get visibility and review now, instead of potentially in a post-release shit happens. We will be doing a sweep of this dashboard periodically leading up to CERT. :ty: in Advance! Escaped Crashes / Asserts / Ensures XXX | Yes | Workato - Component Lookup
PROD | Release Content Legal Approval (FN and UEFN content) Cosmetic Content Assets Sheet | TODO | 2025-07-17 |  | Slack: LINK |  | Hi @Ben Massoglia, just checking in for CHECKLIST_VERSION readiness. Have we confirmed we are all wrapped up and ready to go on the Legal/Publishing front? If not, what is still left to do? :ty: in advance!
PROD | Make sure Disallow List was reviewed (FN, FNE (Creative+UEFN), JUNO, DelMar, Sparks terms) | TODO | 2025-07-20 |  | Slack: LINK | Reference: Term Tracker Sheet 1. Navigate to the #fn-encryptedassets-ext slack channel 2. Look for the thread containing Datamine Results a. Currently by Adam Baxter & Ben Massoglia (Ben to take over in the future) 3. If thread is not present, send a DM to Adam Baxter & Steve Allison asking when that will happen 4. Reminder to confirm that All FN, FNE (Creative+UEFN), JUNO, DelMar, Sparks terms are being checked | Hi @Ben Massoglia, just checking in for CHECKLIST_VERSION readiness. Have we confirmed we are all wrapped up and ready to go on the Encrypted Assets front? If not, what is still left to do? And also - as always - just confirming All FN, FNE (Creative+UEFN), JUNO, DelMar, Sparks terms are being checked. :ty: in advance!
| By Cert Submission: | IN PROGRESS
PROD | Confirm the final loc commit job successfully makes it into P4 Need to ask for: - Fortnite - UEFN - Lego - Festival - Rocket Racing | TODO | 2025-07-19 |  | Slack: LINK | 1. Navigate to the #fn-release-loc slack channel 2. Look for the thread around Final Loc Import and tag in the LOC POCs for all of the live products (currently FN, UEFN, Festival, Rocket Racing & Lego) a. FN is Kevin Shen UEFN is Abdul Alenezi, Festival, RR, Lego are Liza Grebenshchikova 3. If not already stated when its coming in (or past that date), poke the thread using the suggested text in Column H | Hi @loc-fn-producers @Abdul Alenezi just want to confirm the final loc commit job for CHECKLIST_VERSION is on track for all products. Will that be delivered tonight by tonight?
Preparation
| Item | Status | Due by | Completed by | Temp-Notes | Steps To Complete | Suggested Slack Post Text (unless otherwise stated) | Suggested Slack Thread Text (unless otherwise stated)
| By Branch: | IN PROGRESS
PROD | Replacing template text in this checklist | TODO | 2025-07-10 |  | This step should eliminate needing to change MOST template text in any pathing or messaging templates OPTIONAL: Alex Will Do This If You Don't Want To | 1. Click Cell A1 2. Press Ctrl+F > push the 3 dots 3. Find the string "CHECKLIST_VERSION" and replace it with the real value a. ex. Find: CHECKLIST_VERSION Replace with 32.00 ^Checklist dot Version^ 4. Select the "Replace All" button to swap all instances 4. Repeat steps 3-4 by replacing PREVIOUS_VERSION with 31.40 ^Previous Version^ 5. Repeat steps 3-4 by replacing CHECKLIST-VERSION with 32-00 ^Checklist dash Version^ 6. Repeat steps 3-4 by replacing NEXT_VERSION with 32.10 ^Next Version^ 7. Repeat steps 3-4 by replacing NEXT_MAJOR_VERSION with 33.00 ^Next Major Version (.00)^ You will know it worked if all red text in this cell/sheet has been updated to the set values
PROD | Add this sheet's ID to the Workato checklist sheet | TODO | 2025-07-10 |  | This step enables a workato recipe to automatically comb this sheet for steps that are due today or late and post them to the embedded release channel to follow up on | 1. Open the Active Release Checklists 2. If a prior checklist is complete, remove it 3. Add this sheet ID to a new row (this will be everything after docs.google.com/spreadsheets/d/ and before /edit?gid=1048475786#gid=1048475786 4. If the A and B columns are missing use the fill handle from a different row to complete their formulas 5. If you see any #REF errors, click to see if the B column cell needs access allowed and select allow
PROD | Create fn-release-CHECKLIST-VERSION-ext Slack channel and invite groups/users listed in Columns H/I | TODO | 2025-07-17 |  | Slack Channel: LINK IT Request: LINK | 1. Create a new slack channel using the naming format "fn-release-CHECKLIST-VERSION-ext" a. Type /channel and press enter to bring up the window b. Select fn for the prefix c. Channel name = release-CHECKLIST-VERSION d. Check Allow Non-Employees In the Channel e. Skip Invite Users & Topic for now f. Description = Coordination Channel for the CHECKLIST_VERSION Release g. Result should look like: fn-release-CHECKLIST-VERSION-ext 2. Add the people in columns H and I a. Cross reference with This List from Frima to ensure the list in column I is up to date. If not, please update it accordingly 3. Create an IT request to add the 'Fortnite External QA' workspace a. Send a message to it-helpdesk with the following message: Hello there, can I please have the `Fortnite External QA` Workspace added to the newly created #fn-release-CHECKLIST-VERSION-ext channel? @Andrew Lucas for vis on this request Thanks in advance! | Internal Friends To Add (can add all at once, may have to manually adjust the red ones by clicking on them and selecting the intended alias)) ---------------------------------------------------------------------- @release team @release qa @fn-perfprod @community_swat @greg.garnhart @tristan.hardy @fn-buildhealthqa @liveqa @eric.day @lusine.davtyan @sarah.shannon @competitive ops @alec.shobin @paris.nourmohammadi @Michael Micholic @chris.etuk @fn-calendar-owners @epic-liveops @ben constable | External friends need to be added with the '/user add @username' command (These are all Frima folks) NOTE: copy/pasting this list may not work. If not, add one by one (up to 15 at a time) ---------------------------------------------------------------------- Batch 1 @alison.mckenzie @amanda.perry @Ben.Massoglia @Francois.Guimond @Haley.Nelson @mathew bender @matthew.geisen @Michael.Krkuc @Scott.Sevon @steve taylor @connor allen Batch 2 - Frima @Abner Herrera @Alain Du @Alex St-Louis @Alexandre Seguin @Annick Dunn @Anthony Lamoureux @Camille Dion-Bolduc @Ciro Ivan Bolado-Palomo @Danick Carpenter @David Savard @Dominik Luissier-Marcott @Edson Goncalves @Felix Bernier @Francis Langlais Batch 3 - Frima @Guillaume Aube @JeanGabryel Caron @Jean-Simon Racine @Katheryne Bergeron @Laurie Bernard @Maryeve Boivin @Mathieu Chamberland @Mathieu Roy @Maxime Vaillancourt @Murat Balaban @Olivier Bolduc @Olivier Levesque @Pierre Ung Batch 4 - Frima @Remi Senechal @Ricardo Bourgoin-Beaulieu @Rodrigo Cordova @Samuel Carrier @Steven Comeau @Virginie Gaudreault @Alexandre Ould-Hamouda @Alexandre Turgeon @Camille Gendreau @Charles Rheaume @Dominic Charron @Eric Morneau Lepine @Genevieve Bolduc @Antoine Terrienne Batch 5 - Frima @Ismael De Souza @Marc Cossette @Mathieu Audet @Maxime Zobenbueler @Remi Lavertu @Mathieu Roy Lortie @Caleb Tremblay @Alisson Silva @Jérémi Labbé @Gustavo Totoy @Marc-Antoine Ledoux @MarieLee Bergeron @Julie Sanschagrin @Andre Andre Marier @Hugo Mckie | Maybe?
PROD | Create Release Request | TODO | 2025-07-17 |  | JIRA Ticket: LINK | 1. Go to the Release Ticket Template 2. More > Clone 3. Change name to: [FN] CHECKLIST_VERSION Release 4. Put the name+link to the ticket in cell F3 5. Set Fix Version to CHECKLIST_VERSION |  |  | Yes
PROD | Create Release JIRA Dashboard | TODO | 2025-07-17 |  | Dashboard: LINK | 1. Go to the Release Dashboard Template 2. Go to the "..." on the top right and Copy Dashboard 3. Change name to: CHECKLIST_VERSION Release Dashboard 4. Set "Add Viewers: Group to Any Logged In User and press +Add 5. Set "Add Editors" to the AD-Jira-FNRM Group +Add 6. When complete, Press Add at the bottom 7. Go to the bottom of the dashboard to the 2 Controller Widgets a. Set the RED Affect Version & BLUE Fix Version to the CHECKLIST_VERSION (there are duplicate entries but they are all the same so just select 1) 8. Add the Burndown chart using the steps in column H | Steps for adding Release Burndown Chart: ---------------------------------------------------------------------- 1. Go to the Release Burndown Template Tab > Duplicate and rename 2. Add Branch Open Date (C2) using the FN Release Schedule Sheet (row 16) 3. Adjust the other milestone gates (column A) to thier corresponding rows for their dates using the FN Release Schedule Sheet 4. In the ReleaseList Tab, copy cells B3/B4 and paste into B2 a. If B2 is currently set to a version that has NOT been deployed, DO NOT OVERWRITE IT. 5. Edit the title of the graph to this checklist's version tab (double click text) a. 3 vertical dots on graph > Publish > Link tab > copy link 6. Go back to this checklist's version Dashboard > JIRA Burndown > 3 horizontal dots > Paste in External Page Link |  | Maybe?
PROD | Generate Release Controller Permalink | TODO | 2025-07-17 |  |  | 1. Navigate to the seasonal dashboard created in the above step 2. Set the Richfilter Controller Fix Version and Affects Version to the current release version 3. Create the Permalink a. From Controller (bottom right widget) with "..." > "Generate Permalink" > Right Click & Copy Link 4. Go to Rebrandly > New Link > Paste Permalink > Leave Branded Domain > Set Signature slug to Release Version a. Final should look like epic.gm/28-10
PROD | Set Slack channel Topic to Release Manager and Dashboard Link | TODO | 2025-07-17 |  |  | 1. Go to fn-release-CHECKLIST-VERSION-ext channel 2. Select the channel name at the top 3. Enter the suggested text in Column H in the Topic Section a. Person 1/2 are row 22 of the FN Schedule Sheet 4. Attach the permalink generated in the prior step | @release-embedded ¦ Dashboard: epic.gm/CHECKLIST-VERSION ¦ Hotfix Req epic.gm/Hotfix ~ Email `release-team-oncall` to page after office hours; http://epic.gm/TeamInfo
PROD | Setup Release Dashboard's Top Widget | TODO | 2025-07-17 |  | Dashboard: LINK | 1. In the Dashboard, mouse over the Schedule section > "..." > Edit 2. Using the template in column H, replace the red text with the appropriate info a. RM owners from the Release Schedule b. Game Config from tab's link c. Copy slack channel's link | <div class="left"> <h3>Release Schedules</h3> <ul> <li> <strong>Google Sheets:</strong> <a href="https://docs.google.com/spreadsheets/d/11P9U3a6TDH-u8mR6ynIKFpqGKaMxSe-NbvfAmt42iIY/edit?gid=2068775089/" target="_blank">FN Release Schedule </a></li> <li> <strong>Air Table:</strong> <a href="https://airtable.com/appTMZnv3FFYvaEf5/pagXaUnRze2SaaSDS/" target="_blank">Milestone Calendar </a></li> <li> <strong>Google Calendar:</strong> <a href="https://calendar.google.com/calendar?cid=ZXBpY2dhbWVzLmNvbV84ZXIzOG1oZXV1djFzZXEyNzltNmg0dmQ3OEBncm91cC5jYWxlbmRhci5nb29nbGUuY29t" target="_blank"> Add To My Google Calendar</a></li> </ul></div> <div class="right"> <ul> <li> <strong>Schedule:</strong> <a target="_blank" href="https://docs.google.com/spreadsheets/d/11P9U3a6TDH-u8mR6ynIKFpqGKaMxSe-NbvfAmt42iIY/">Roadmap &amp; Release Schedule</a></li> <li> <strong>Roadmap:</strong> <a target="_blank" href="https://airtable.com/appachk0WfaFrftUG/paguCjFwcolH7Q2ye">Deliverables Roadmap</a></li> <li> <strong>Game Config:</strong> <a href="https://docs.google.com/spreadsheets/d/1w5PQcnciR-lbbU6H6m0aaqgiFWNRbttSr7uEoCmKUzk/edit#gid=XXXXXXX" target="_blank">Hotfix Game Config Tracking</a> </li> <li> <strong>Slack:</strong> <a href="https://epicgames.slack.com/archives/XXXXXXXX" target="_blank"> #fn-release-CHECKLIST-VERSION-ext</a> </li> <div><font color="red"><b>First time viewing dashboard and numbers are large: </b></font>Scroll down to bottom and update FixVersion and AffectsVersion to desired release. It will save the cookies for next view. </div> </ul></div> <style type="text/css"> table {margin-left:20px;} div.left{float:left} div.right{margin-left:350px} li {padding-bottom: 5px;} .tg {border-collapse:collapse;border-spacing:0;border-color:#ccc;} .tg td{font-family:Arial, sans-serif;font-size:14px;padding:10px 5px;border-style:solid;border-width:1px;overflow:hidden;word-break:normal;border-color:#ccc;color:#333;background-color:#fff;} .tg th{font-family:Arial, sans-serif;font-size:14px;font-weight:normal;padding:10px 5px;border-style:solid;border-width:1px;overflow:hidden;word-break:normal;border-color:#ccc;color:#333;background-color:#f0f0f0;} .tg .header{font-weight:bold;background-color:#f0f0f0;border-color:inherit;text-align:center;vertical-align:top} .tg .data{border-color:inherit;vertical-align:top} </style> |  | Maybe?
PROD | Cross check Fortnite Release Calendar below dates are accurate for all versions from this checklist's season and the following season found in the FN Release Schedule and populated from the Air Table - Row 16: Branch Opening - Row 17: Development Complete - Row 18: Hard Lock - Row 19: Pencils Down - Row 20: Cert Sub - Row 5: Live - Row 5 of next column(s): HF(s) Live | TODO | 2025-07-17 |  | Alternate AirTable Link | 1. Go to the FN Release Schedule to get the dates 2. Go to Google Calendar and search for CHECKLIST_VERSION 3. Ensure the dates from the Release Schedule are present in Google Calendar (This is driven by AirTable Automation) a. If there are any discrepancies, flag it to the release management team |  |  | Yes
PROD | Create a Jira for BR Calendar/Store/Shop to be update/reviewed | TODO | 2025-07-17 |  | JIRA Ticket: LINK | 1. Go to the JIRA Template 2. Move > Clone 3. Rename ticket in the format: ¦Shop¦ Verify ROW Store/Calendar (BR) for [CHECKLIST_VERSION] Deploy Scheduled for [MM/DD] 4. Add as "Watchers" and CC the following in the comments (copy below and paste in TEXT vs VISUAL) *CC:* [~juan.romero] [~nick.owens] [~steve.allison] [~amanda.perry] [~matthew.geisen] [~alison.mckenzie] 5. Set Fix Version to CHECKLIST_VERSION |  |  | Yes
PROD | Verify BranchFoundIn in JIRA is already populated for CHECKLIST_VERSION if not, request it be done in #fn-jira-admins-ext | TODO | 2025-07-17 |  | Slack: LINK | 1. Go to JIRA > Create (blue button at top) 2. Look for BranchFoundIn 3. Type in Release-CHECKLIST_VERSION a. If it is present, you are done. If not, go to step 4. 4. Spin up a post in #fn-jira-admins-ext using the suggested text in Column H | Hello JIRA Admins, Could you please add `Release-CHECKLIST_VERSION` as an option in the BranchFoundIn dropdown? Thanks in advance! |  | Maybe?
PROD | Schedule Google Calendar Meeting: Stability Sync | TODO | 2025-07-17 |  | Calendar Event: LINK | 1. Go to the Google Calendar 2. Search for Stability Sync and go to the previous release's event 3. Duplicate the card and update the following: a. Event Title (Set to correct version) b. Date (set to 10am the morning of release date) c. Zoom Meeting (remove and add a new one to account for duping even wonkiness) 4. If not already on the previous event when duping. ensure the following people/groups are added: a. Chris Tran, Alex Ruse, Tyler Buczek, Jay Chaney b. fn-tech-production c. Release-Team d. ReleaseQA |  |  | Yes
PROD | Schedule Google Calendar Meeting: Post Mortem | TODO | 2025-07-17 |  | Calendar Event: LINK Post Mortem Sheet: LINK | 1. Go to the Google Calendar 2. Search for Post Mortem and go to the previous release's event 3. Duplicate the card and update the following: a. Event Title (Set to correct version) b. Date (set to the Thursday following the release date) c. Zoom Meeting Use this - the link to our shared zoom where we will use the RQA break out room d. Post Mortem Sheet Link (set to applicable tab - If not created, make the tab) 4. If not already on the previous event when duping, ensure the following groups are added: a. fn-release b. Release-Team (embedded in the 4a. group) c. liveqa@epicgames.com |  |  | Yes
PROD | Schedule Calendar Events: - Hard Lock - Pencils Down | TODO | 2025-07-17 |  |  | 1. Go to the Google Calendar 2. Search for Hard Lock and go to the previous release's event (should be at 8PM ET) 3. Duplicate the card and update the following: a. Event Title (Set to correct version) 4. Repeat steps 2-3 for the Pencils Down calendar event. |  |  | Yes
PROD | Determine Deploy Time with the below teams: - Live Ops - Competitive - Publishing/Marketing | TODO | 2025-07-17 |  | Deploy Types and Times: Season Release time of `2:00am ET` Dot Release time of `4:00am ET` Unforced Emergency Patches: 8:00am ET Slack: LINK | 1. Spin up a post in the fn-release-CHECKLIST-VERSION-ext channel using the suggested text in Column H/I 2. Once agreed upon, Bold+Underline the selected time in column F to easily identify what we settled on without having to go back to the thread | Deploy Time Alignment for 34.10 on Mon Jul 21 :thread: | Hello @release-team @releaseqa @competitive-ops @epic-liveops @alec.shobin @Paris.Nourmohammadi Just wanted to get everyone together to align on the deploy time for CHECKLIST_VERSION. Any objections to going with our usual INSERT_TEXT_FROM_COL_F? | Yes
| By Hard Lock: | #N/A
PROD | For XX.00 Deploys Only: Reminder messaging for seasonal Hotfix clean up | TODO | 2025-07-17 |  | Slack: LINK | 1. Spin up a post in the fn-release-CHECKLIST-VERSION-ext channel using the suggested text in Column H/I | Seasonal Hotfix Cleanup reminder for Release-CHECKLIST_VERSION Please respond by the end of day, {Day}, {Date} 5:00PM EST, if you have hotfix syntax that needs to persist and cannot be baked in. If not, your syntax may get wiped after the clean up. (Timing in the above messaging should align with first whiteglove?) | It's time to cleanup the hotfix files with a new season release. This is to maintain a clean and minimal list of changes in the files. Teams should be proactively baking in their changes release over release and requesting clean ups in the game config sheet. Unfortunately, this does not always happen, and leaves a lot of stale changes and bloat that is no longer needed. If there are any specific changes that must be kept, please let us know so that we can flag as DO NOT PURGE in the hotfix files ;(DNP). Thanks in advance to all that do regularly bake in and request removals. This is very much appreciated. | Yes
PROD | Send Release Strategy email Confluence Wiki (need to merge all the things) Wiki on creating the meeting calendar event Template (if not copied from a previous email) | TODO | 2025-07-18 |  |  | 1. Search your email for "Release Strategy" and go to a previous release's email 2. Copy a previous email's TO:. Subject and Body (either a .00 if this checklist is a .00 or a .10/.20.30 if not) and update the following a. Version & Expected Release Timing (also confirm if downtime from 4am-5am is applicable) b. Cutoff for Deploy Strategy and Hotfix Confirm Items Date (Should be friday noon if tuesday deploy) 3. Send Email | TO: FN-Release-Updates <fn-release-updates@epicgames.com> Release Dates: FN Release Calendar | Replace with Pre-Pop | Yes
PROD | Redundancy: Make sure zoom links are still valid for all meetings related to CHECKLIST_VERSION | TODO | 2025-07-18 |  |  | 1. Search Google Calendar for the release version and check the below meetings: - Stability Sync - Post Mortem 2. Click the current zoom link to try to enter as normal. If it works, you are good. 3. If you get an error, kill the current zoom link and make a new one
PROD | Coordinate Discovery surface and link updates for any new playlists | TODO | 2025-07-18 |  | Slack: LINK | 1. Check the Epic Roadmap for the CHECKLIST_VERSION and identify any new Playlist that may need to be configured a. Identify the production owner and potentially the EmbeddedQA associated (if unknown we can ask the production owner to loop in their QA partners) 2. Spin up a thread in the #fn-release-CHECKLIST-VERSION-ext slack channel using the suggested text in column H/I --> a. Tag in the new playlist production owner and embedded QA and ask if they have properly coordinated what is needed for their new playlist. Provide them with the Reference Doc: [Discovery] Releasing New Playlist Checklist | CHECKLIST_VERSION New Playlists Coordination :thread: | Hello! We are currently tracking new playlists for the following roadmap items for this release: * PLAYLIST_MODE - @PROD_OWNER * PLAYLIST_MODE - @PROD_OWNER * PLAYLIST_MODE - @PROD_OWNER We need teams to go through the New Playlist Checklist and confirm that everything has been considered is setup prior to our release whitegloves. Production owners please coordinate with your embedded QA teams to confirm everything is functioning as expected. @release-qa for vis @release-ops for vis
| AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK |  |  | AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK
| By Pencils Down: | IN PROGRESS
PROD | Request Final DAD revision for pre whiteglove https://epicenter.on.epicgames.com/?tools=all For reference: https://epicgames.slack.com/archives/C08DLJG51L7/p1742565116008119 | TODO | 2025-07-19 |  | Slack: LINK | 1. Go to the #fn-release-CHECKLIST-VERSION-ext and spin up a post using the suggest text in Columns H/I a. Check the FN Release Schedule or Fortnite Release Calendar for the cert date 2. After links have been provided, add them to the Game Config Sheet, for all links provided 3. Ensure that RQA is able to receive the DOT revisions prior to the weekend so weekend testing can be done by external QA teams | :dad:CHECKLIST_VERSION Final DOT Revisions:dad: | Hello there @Connor Allen @Paul.Odenwaldt Checking in on final revision delivery prior to going live on INSERT_DEPLOY_DAYnDATE As a heads up, we will be starting pre-cert checks this weekend and would like the revisions to be in place ahead of that testing if possible. We go to cert on INSERT_CERT_DAY :) @releaseqa for viz | Yes
PROD | 1st touchpoint with Calendar owners Typically you get sign off from all but BR (Shop & Non-Shop) | TODO | 2025-07-19 |  | Slack: LINK | 0. Ensure the people in column I are invited to the slack channel 1. Go to the #fn-release-CHECKLIST-VERSION-ext and spin up a post using the suggested text in Columns H/I 2. Get confirmation from each calendar owner area | :calendar: Calendar Updates for CHECKLIST_VERSION | Just checking in on our calendar promotions prior to going live on INSERT_ReleaseDayandDATE. As a reminder downtime will begin for INSERT_BranchVersion at INSERT_DowntimeStartTime. Please keep that in mind as you setup and calendars that should go live at light switch up. As a heads up, we will be starting pre-cert checks this weekend and would like the final calendar promotions to be in place before that testing starts, if possible. :mag_right: Heads-up: We’ll be starting pre-cert testing this weekend, and would ideally like all final calendar promotions in place before testing begins, if possible. We’re targeting cert submission on INSERT_CertDayandDATE. >:warning: Additional Reminders for Calendar Integrations: • Remove leak-sensitive data from any calendars checked into the client-events channel. Leakers may have access to this data up to two hours before a scheduled event goes live. • If your calendar event is set to go live with INSERT_BranchVersion, ensure the start time aligns with the downtime window (INSERT_Downtime ET). Mismatched start times may disrupt internal QA coverage during deployment. We'll have a follow up check-in with calendar owners closer to deploy, but flagging now to ensure this process is on your radar. Thanks in advance! STW - @Patrick.Malott BR (Non-Shop) - @DJ.Schilens BR (Shop) - @Juan.Romero @matthew.geisen @alison.mckenzie @amanda.perry LTM - @scott.sevon @haley.nelson @michael.krkuc Juno/Sprout (need confirmation on both) - @Tyler.Yungmann @Keith.Leiker @Jason.Kanagaratnam @Steven.Tarry @Alec.Fisher-Lasky Sparks - @Kyle Wynn DelMar - @lauren.boud
| AFTER 8PM ET PENCILS DOWN | AFTER 8PM ET PENCILS DOWN |  |  | AFTER 8PM ET PENCILS DOWN | AFTER 8PM ET PENCILS DOWN | AFTER 8PM ET PENCILS DOWN | AFTER 8PM ET PENCILS DOWN
Pre-Candidate Build
| By Cert Submission: | IN PROGRESS
PROD | Verify Final DOT Links for WG testing are accurate and no changes are expected. https://epicenter.on.epicgames.com/?tools=all | TODO | 2025-07-18 |  | Final Dad CL: 12345 | 1. Follow up in the original thread from row 40 using the suggested text in Columns I |  | Checking in on final revision delivery. Anything to update since our last request above? We are starting pre-cert checks INSERT_PD_DAY and want to ensure QA is running their :whiteglove-wave: with the most accurate info. We are still targeting to go to cert on INSERT_CERT_DAY :smiley: | Maybe?
PROD | Ensure Final Shop is in for WG testing | TODO | 2025-07-18 |  | Final Shop CL: 12345 | 1. Send message in the #fn-release-CHECKLIST-VERSION-ext channel using the suggested text in Columns H/I | :shopping_bags: CHECKLIST_VERSION Final Shop Changes :shopping_bags: | Hello there @juan romero @nick.owens @Steve.Allison @amanda.perry @Matthew.Geisen @alison.McKenzie Just double checking in on final shop delivery. Anything else coming in hot? I see the last committed change on INSERT_JIRA_FROM_ROW46 is FIX_CL_FROM_JIRA We are starting pre-cert checks INSERT_DAY and want to ensure QA is running their :whiteglove-wave: against the final shop revisions if they are locked in. We are targeting to go to cert on INSERT_CERT_DAY :smiley: | Yes
PROD | Send Last Call bump for callouts in the Release Strategy Email. WIKI | TODO | 2025-07-19 |  |  | 1. Go to your email and search for the "CHECKLIST_VERSION Release Strategy" 2. Send a follow up email using the suggested text in Column H a. Deadline for a Tuesday deploy is noon on the Friday b. Deadline for a Friday deploy is noon on the Tuesday | Bumping the thread here for any last minute CHECKLIST_VERSION Call Outs Recopy the deadline line from the original email in again | Replace with Pre-Pop | Yes
PROD | Determine Ship List (using the below Airtable) and pin it in Slack New Hotness: Deliverables Roadmap Build View | TODO | 2025-07-19 |  | Slack: LINK | 1. Go to the Deliverables Roadmap and set the filter date to the deploy date 2. Compile a list of all changes going into the release using the format in Column H 3. Post to #fn-release-CHECKLIST-VERSION-ext channel and Pin the message. Example Here | CHECKLIST_VERSION Ship List :ship: - Items/Gameplay: XXX - REGS/Quests: XXX - Creative: XXX :exclamation: Disclaimer: :exclamation: If there is anything missing or incorrect with this list, please have the corresponding owners update the Airtable from which this information is taken from (Deliverables Roadmap) |  | Yes
PROD | Whiteglove has been completed on INITIAL release candidate (aka crit checks) and issues called out have been threaded/escalated for triage Note: We will never be releasing this build. There will always be another CL for our final candidate (THIS LINE) | TODO | 2025-07-19 |  | Slack WG: LINK | 1. Go to #fn-release-CHECKLIST-VERSION-ext and search for "Fortnite CHECKLIST_VERSION Whiteglove:" a. This should bring up all instances of whitegloves bring run 2. Ensure RQA completes the Client WG the day before cert submission (ideally 2 days before) a. You can track progress in TestRail (STC) if you have access 3. Ensure issues called out from the WG are appropriately threaded (outside the WG thread) and triaged in the #fn-release-CHECKLIST-VERSION-ext channel
Release Candidate Build (Locked in)
IN PROGRESS
PROD | Ensure that the Branch Tab within the Game Config Doc has been locked at Noon | TODO | 2025-07-21 |  | Slack: LINK | 1. Spin up a thread in the #fn-release-CHECKLIST-VERSION-ext slack channel using the suggested text in Column H | :airhorn-9469: Hello team! Just calling out that the release team has locked the CHECKLIST_VERSION tab of Game Config today. Any further edits to this tab should go through the `Game Config Update` Service Desk Request from this point forward! :lock: Thanks! |  | Maybe?
PROD | Aegis Prewarm (Final Client and Server CL) | TODO | 2025-07-20 |  | Slack: LINK | Follow the Aegis Prewarm User Guide to pre-warm islands in advance of any Client deployment (tag Garry Casey, Derek Burandt if any questions or issues in #fne-aegis-prewarm-reports-ext)
PROD | 2nd touchpoint with Calendar owners | TODO | 2025-07-20 |  | Slack: LINK | 1. Revisit thread in THIS and poke calendar owners with the text provided in Row H 2. Confirm with all calendar owners that relevant calendars have been published to live ahead of CHECKLIST_VERSION release |  | Happy Day Before Deploy Day! Checking in to make sure all changes have been promoted to live leading up to our deploy on INSERT_DEPLOY_DAYnDATE.
Signoff and Submission
IN PROGRESS
PROD | Whiteglove has been completed on FINAL release candidate (aka Cert Checks) and issues called out have been threaded for triage | TODO | 2025-07-19 |  | Slack: LINK_TO_WG | 1. Go to #fn-release-CHECKLIST-VERSION-ext and search for "beginning whiteglove of:" a. This should bring up all instances of whitegloves bring run 2. Ensure RQA completes the Final Client+Server+MCP WG the day of Cert Submission a. You can track progress in TestRail (STC) if you have access 3. Ensure issues called out from the WG are appropriately threaded (outside the WG thread) and triaged in the #fn-release-CHECKLIST-VERSION-ext channel
Pre-Release
IN PROGRESS
PROD | Confirm Release QA is patched up and ready for the morning | TODO | 2025-07-19 |  | Set a scheudled reminder for the deploy owners 1 days prior during their core hours (or if they are OOO at that time, find a time when they are available before the deployment) NEEDS TO HAPPEN BEFORE 12PM ET (For Ivan and Tatiana) Slack: LINK | 1. Create new thread in #release-team channel using the suggested text in Column H a. Needs to happen before 12pm ET as Ivan will be gone after then 2. Make sure you have the currently live build installed in your launcher so you can verify the Win patch size come deploy day should you need to | Friendly reminder to the morning deploy owners @RQA1 @RQA2 to ensure your devices are all patched up for the morning deploy. :thankskeanu: |  | Yes
PROD | Release Strategy Async Post Example Post: LINK | TODO | 2025-07-20 |  | Slack: LINK | 1. Create a new thread in #fn-release-CHECKLIST-VERSION-ext channel 2. Perform the steps outlined in Column I to layout the info consistently 3. Pin the post |  | 0. Begin post with the following line :announcement-1: CHECKLIST_VERSION Go Live Information Real Ticket Info 1. Add a line break using SHIFT+ENTER and then Copy all info in the BUILD INFO / PATCH SIZES section of the REAL-XXXX ticket and CTRL+SHIFT+V to paste values only into the slack post a Highlight the ++CLs and CTRL+SHIFT+C to turn them orange b. Highlight the Client / Server / Patch Size info and CTRL+SHIFT+9 to Block Quote them 2. Add a line break using SHIFT+ENTER and then Copy all info in the DESCRIPTION section of the REAL-XXX ticket and paste below the above info in the slack post a. Properly tag any people using @person if they are listed in plain text - Should we do this or leave it as plain text? Go Live Hotfix 3. Ask RQA if the final Game Config and add a line under the above section with it Major Items 4. Hit SHIFT+ENTER x3 to properly line break, then Add the following section below (BLUE TEXT indicates linking to the corresponding item). a. Copy the blue items and CTRL+SHIFT+8 to list as bullet items Major Items: INSERT_MAJOR_ITEMS_EX_PRODUCT_NEW_SEASON Run of Show related links can be found in the Run of Show bookmark Folder at the top of this channel Ship List 5. Hit SHIFT+ENTER x3 to properly line break, then lastly go to the Ship List (should be pinned in the #fn-release-CHECKLIST-VERSION-ext channel) and copy and paste that info below the major items Should result in a post like THIS
Remove on cadence, Prod to handle this by request | Record Post PD CLs (I don't see a point in doing this if nobody is looking, so setting to N/A for now. Don't waste your time with this clunky process. Justin will save us all with his airtable anyhow!) | N/A | 2025-07-20 |  | Tracker Tab: LINK | 1. Go to the Post PD Commits Tracker 2. Follow the instructions to complete the task 3. Link the tab in F103 NOTE: This an interim process. Ideally we can pull this data more efficiently through the submit tool flow
___ ___ __ __ ___ _ __ _ _ _ ¦ _ \ / _ \ \ \ / / o O O ¦ \ ___ ¦ '_ \ ¦ ¦ ___ ¦ ¦¦ ¦ ¦ / ¦ (_) ¦ \ \/\/ / o ¦ ¦) ¦ / -_) ¦ .__/ ¦ ¦ / _ \ \_, ¦ ¦_¦_\ \___/ \_/\_/ TS__[O] ¦___/ \___¦ ¦_¦__ _¦_¦_ \___/ _¦__/ _¦"""""¦_¦"""""¦_¦"""""¦ {======¦_¦"""""¦_¦"""""¦_¦"""""¦_¦"""""¦_¦"""""¦_¦ """"¦ "`-0-0-'"`-0-0-'"`-0-0-'./o--000'"`-0-0-'"`-0-0-'"`-0-0-'"`-0-0-'"`-0-0-'"`-0-0-'
Lead-up to Downtime - Deployment Owner
| Item | Status | Due buy | Done by | Temp-Notes | Perma-Notes
During Downtime - Deployment Owner
| Item | Status | Due Buy | Done by | Temp-Notes | Perma-Notes
Post-Release - Deployment Owner
| Item | Status | Due Buy | Done by | Temp-Notes | Perma-Notes
DONE
N/A
Not currently relevant (re-visit as needed)
| Item | Status | Due by | Done by | Temp-Notes | Perma-Notes
Likely remove, should fall under the teams owning testing of these | Ensure TestFlight Beta App Review has been submitted |  | 2025-07-17 |  | Slack: LINK | 1. Track review in Apple Cert Timing Tracker a. If info has not been filled out, reach out to Chris Etuk for a status update in the fn-release-CHECKLIST-VERSION-ext channel using the suggested text in column H/I Alternatively you can see if TestFlight Beta Review has been submitted by enabling notifications in sweden on your AppStore Connect profile and filtering your email for the following "has words" "Your app Fortnite (6483539426) has been approved for beta testing" | :apple-neon: CHECKLIST_VERSION TestFlight Beta App Review Status :apple-deal: | Hey @chris Etuk I noticed that we haven't submitted a CHECKLIST_VERSION build to TestFlight Beta yet. Any plan for when that will happen?
| Confirm MCP deploy percentage with OGS (tag Pete Axt & Joe Pintozzi) and Live Ops. WIKI |  | 2025-07-20 |  | Slack: LINK | 1. Make a post in #epic-live-operations-ext or #on-dbs-game-services-ext using the suggested text in Column H | @Joe Pintozzi @Pete Axt Just confirming we are targeting 50% DeployHostPercentage during downtime as usual for the CHECKLIST_VERSION MCP deploy tomorrow? |  | Yes
| Create Bug Bids Page |  | 2025-07-17 |  | Bug Bids Page: LINK | 1. Go to the previous version's Bug Bids Page (here) 2. Click "..." > Copy > Copy 3. Change title to Bug Bids for CHECKLIST_VERSION > Publish 4. Note the current values in the Issues Left column 5. Edit the page > Update the hard coded HL-1w and HL dates as per the FN Schedule 6. Clear the hardcoded values in HL-1W and HL columns (highlight and delete) This section is borked until the <> is re-added back. Need to do manually until then :((((( 7. Select the <> icon to open in source editor 8. Find the version you copied from, replace all with the version you want > Apply > Update 9. Ensure the values have changed |  |  | Yes
| Schedule Send Bug Bids Email 10 days prior to Hard Lock date at 10:30am |  | 2025-07-17 |  | Send scheduled for DATE | 1. Go to GMail and compose a new email 2. Send email using the suggested text in Column H 3. Link the bug bids page to the blue text 4. Change Day MM/DD to the date of review (monday the week of HL) 5. Once done, hit the drop down arrow on the blue Send button > Schedule Send 6. Pick a Date & Time > 10 days prior to Hard Lock date at 10:30am (See Cell F2) 7. Schedule Send 8. Go to your gmail > Scheduled (below sent) and review the preview to ensure it is all correct 9. Paste the scheduled send info in column F for reference | The CHECKLIST_VERSION Bug Bids wiki has been created and is ready for you to enter your bids! We will start reviewing at morning sync next week on DAY MM/DD. Reminder, there's a link on the top of this page you can use to look at historic fix rate data for your components, which you can use to reason about what your teams can realistically tackle leading up to CHECKLIST_VERSION. Past Bug Bid pages are also still available for review under the Release Accountability parent page. CHECKLIST_VERSION Dashboard: [Link] Doing this thinking now, ahead of the hectic bugfix stage, will help identify rational targets you can use to guide triage activities & tradeoff decisions. Thanks, Release Team | TO: Release-Team@epicgames.com CC: FN-Prod-All <FN-Prod-All@epicgames.com>, FNE Release <fne-release@epicgames.com> Subject: Bug Bids for CHECKLIST_VERSION | Yes
| (Joe) I would just completely kill this line in favor of the Build Protection line just above. Run Keep Release Candidate job for all final client candidate CLs. |  | 2025-07-19 |  | PLATFORM_1: HORDE_JOB_LINK PLATFORM_2: HORDE_JOB_LINK PLATFORM_3: HORDE_JOB_LINK | 1. Go to the REAL-XXXX ticket for this release to see the final candidate CLs 2. Go to the Promotions tab of Main Horde 3. Select the blue New Job button in top right 4. Change template dropdown to Keep Release Candidate 5. Put the first CL in the Change field and set the associated Promote Platforms field. Then Start Job. a. Re-Run for all Client CLs with their associated Promote Platforms field.
| Verify the Android APK allowlist is in the game config file |  | 2025-07-20 |  | Release Team no longer needs to send hotfixes to update CRC values when we ship new Android client builds. The 13.40 values need to stay, but the Android APK Whitelist hotfixes no longer function in 23.50+ . This is now being done on the AntiCheat side via Dragonfly. | Verify it is in the game config file
| Review Android APK allowlist syntax is included and correct in Release QA swarm link and in PredeployA files |  | 2025-07-21 |  | Release Team no longer needs to send hotfixes to update CRC values when we ship new Android client builds. The 13.40 values need to stay, but the Android APK Whitelist hotfixes no longer function in 23.50+ . This is now being done on the AntiCheat side via Dragonfly.
| Create a Jira for StW Calendar/Store to be update/reviewed (CN/RoW) |  | 2025-07-17 |  |  | Assign to Dav Harnish and CC Henry Meredith in comments https://jira.it.epicgames.net/browse/FORT-247162
| Check Android APK size and make sure it is under 150 MB |  | 2025-07-19 |  |  | Look at APK in the build folder
| Create a tab in FN Playlist Planning sheet and let stakeholders know in #fn-release-playlistplanning-ext that it now exists |  | 2025-07-17 |  |  | https://confluence.it.epicgames.com/display/FORT/Playlist+Planning Note: If its a .10 release, spin up a thread. If its not, then mark this task as N/A.
| Schedule Meeting: Release Notes Signoff |  | 2025-07-18 |  | No Release Notes! | Thurs. of CertSub week
| Release Notes: Initial Setup and Email Sent |  | 2025-07-18 |  | No Release Notes!
| Schedule Calendar Reminders: Release Notes Section Owners |  | 2025-07-18 |  | No Release Notes! | 1 each day for 2 document days of release notes
| Order breakfast for morning of publish day |  | 2025-07-16 |  | Please bring this back!!!
| Send initial IOS Submission email |  | 2025-07-16
| Update Google Play Roadmap email (if applicable) |  | 2025-07-16 |  |  | to: Dan Song <mtd@google.com(opens in new tab)> Lawrence Koh <lawrencekoh@google.com(opens in new tab)> CC release-team Jocelyn Hans
| Send Release Notes 1st Draft to FN-Release-Updates |  | 2025-07-16 |  | No Release Notes!
| Forward CN patch notes to EGC |  | 2025-07-19 |  | No Release Notes! | Forward version patch notes for China to Martin Yu. Martin will review and deliver to Tencent.
| Add IOS Whitelist Hotfix to MobileCert |  | 2025-07-20
| Check iOS Compressed File Size |  | 2025-07-18 |  | Compressed File Size: MB Previously in 13.40 Release flagged if greater than 200 MB. Compressed sizes have increased in allowance from Apple. We should still note what the size is and report to tech-mobile Jira for investigations is FORT-772296 This process may be something we can remove, but need to keep an eye out for a few releases. [thread] | 1. Go to https://appstoreconnect.apple.com/apps 2. Select Fortnite 3. Select TestFlight 4. Select the RC candidate Version and Build 5. View the Build Metadata for Compressed File Size 6. Record the size and pass along to Tech-Mobile
| Audit MobileCert environment config for potential cert blockers |  | 2025-07-19
| Configure MobileCert Build Info |  | 2025-07-19
| MobileCert: MCP Update |  | 2025-07-19
| MobileCert: Server Promote |  | 2025-07-19
| Cert Submission: iOS |  | 2025-07-19
| Send email notifying Apple contacts that build is uploaded |  | 2025-07-19
| Send email notifying Google contacts that build is uploaded |  | 2025-07-19
| Remove MobileCert Redirect |  | 2025-07-20
| Live: Update iOS Build Info |  | 2025-07-20
| Remove Android Build Info from MobileCert |  | 2025-07-20
| Live: Update LiveCN Build Info |  | 2025-07-20 |  |  | Deploy will be coordinated with TC in #ext-fncn-live in Slack. TC will flip WeGame switches. THIS STEP IS ONLY NEEDED IF STAGING THE CN BUILD FAILED.
| Update Apple Cert Timing Tracker |  | 2025-07-21
| Update EULA if requested by Legal |  | 2025-07-18
VVV To be Re-Added Once iOS comes back VVV
| Make sure PredeployA Hotfix Files are set back to appropriate Android Whitelist and IOS Banning syntax for LOPS to copy at time of release |  | 2025-07-20 |  | Only Android? | Android: Whitelist syntax needs to be added IOS: Remove the following: [/Script/FortniteGame.FortGameModeZone] BanCodeAction_20=(AnyReason=2, UnsignedIPA=0) BanCodeAction_28=(AnyReason=2, NoIOSCryptInfo=0)
| Make sure PredeployA Hotfix Files are set back to appropriate Android Whitelist and IOS Banning syntax for QA to not be blocked |  | 2025-07-21 |  |  | Android: Whitelist synatx needs to be removed IOS: Add the following: [/Script/FortniteGame.FortGameModeZone] BanCodeAction_20=(AnyReason=2, UnsignedIPA=0) BanCodeAction_28=(AnyReason=2, NoIOSCryptInfo=0
| Determine if release breaks Replays and/or if we should whitelist any old CLs |  | 2025-07-18 |  | https://wiki.it.epicgames.net/pages/viewpage.action?spaceKey=FORT&title=Replay+Whitelisting | Should be considered if we are breaking replays of a major Live event from the previous release Ask Shak or Matt Grandstaff
| Test verify PS4 remaster jobs have no errors or warnings |  | 2025-07-18 |  |  | Nightly Job "Publish PS4 Remaster Submission Packages (SIEA (07022) Only)"
| Confirm all Non-Unity warnings and errors are fixed or benign |  | 2025-07-18
| PS4: Update R:\Analytics\sony_version.csv |  | 2025-07-21 |  | I refuse | Instruction Doc
| Make sure PredeployA Hotfix Files are set back to appropriate Android Whitelist and IOS Banning syntax for QA to not be blocked |  | 2025-07-21 |  |  | Android: Whitelist synatx needs to be removed IOS: Add the following: [/Script/FortniteGame.FortGameModeZone] BanCodeAction_20=(AnyReason=2, UnsignedIPA=0) BanCodeAction_28=(AnyReason=2, NoIOSCryptInfo=0
| [24 hrs before] Inform Tencent and Community |  | #REF! |  |  | 24 hrs before - Inform in #ext-fncn-live @Sula Yu and CN QA deply captain Check EGC QA Checklist > Captain tab for additional @ https://docs.google.com/spreadsheets/d/1nUx7qP1aLLU6D1VVv0Q4mx18aMMG_tz5vmQC0Z9wxgc/edit?usp=sharing
| [24 hrs before] Release JIRA |  | #REF! |  |  | Link Release management Jira ticket here
| [2 hours befire] Hotfixes Checked In and Previewed |  | #REF! |  | Check fn-release-team around 4PM ET | RQA will provide a Swarm shelf to approve and merge around 4PM ET https://docs.google.com/spreadsheets/d/1w5PQcnciR-lbbU6H6m0aaqgiFWNRbttSr7uEoCmKUzk/edit#gid=2063781583
| [2 hours before] Schedule Downtime (Fortnite) |  | #REF! |  | Schedule sometime before 4:40pm | https://adminportal-website-management.ol.epicgames.net/lightswitch2/schedule/fortnitelivecn?server=Lightswitch&moduleName=lightswitch
| [1 hrs before] Verify Client, Server, and MCP for release |  | #REF! |  |  | Pinged in Release Private if unsure of any changes
| [1 hrs before] Internal Release Email |  | #REF! |  |  | fncn-live@epicgames.com, fn-live, online-infra, global-live-deployments
| [35 min before] Turn off FN CN Alerts |  | #REF! |  | Poke liveOPS at MMS disable | Request liveOPS pause FN Grafana integration in OpsGenie https://epicgames.app.opsgenie.com/teams/dashboard/76f730d9-7346-4f83-b599-ab3589ba2fce/integrations
| [35 min before] Alternatively, Set False to True for Playlist Restrictions Configuration section at https://adminportal.ol.epicgames.net/fortnite/profileProxy?server=Fortnite%20China&moduleName=fortnite Click MMS at top and scroll down to Playlist Restrictions Configuration Set disableAllMatchmaking to true |  | #REF! |  |  | 35mins before LS down Edit directly under Admin Portal https://adminportal-website-management.ol.epicgames.net/fortnite/systemFiles Make sure you are in "Fortnite China" Notify fn-release-deploy (FN-Deploy Public) and Mission Control slack channels |  | For Old Hotfix Method: DefaultGame.ini [/Script/FortniteGame.FortGameInstance] bBattleRoyaleMatchmakingEnabled=false
| Item | Status | Due by | Done by | Temp-Notes | Perma-Notes
| Confirm Lightswitch down status |  | #REF! |  |  | Check status has switched to DOWN - https://adminportal-website-management.ol.epicgames.net/lightswitch2/schedule/fortnitelivecn?server=Lightswitch&moduleName=lightswitch
| Lightswitch down notifications |  | #REF! |  |  | Post message in fn-release-deploy and Mission Control slack channels
| We Games access disabled |  | #REF! |  |  | Notify ext-fncn-live to disable access for we games. More often than not this is Sula, but confirm it isn't a different Tencent employee
| Deploy "Go Live" INI Hotfix config (make sure this is done before server deploy to ensure hotfix config is pulled correctly) |  | #REF! |  |  | Can move on to MCP and Client deploys until Hotfix is done. Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy internal
| Deploy MCP |  | #REF! |  |  | Deploy %: 50% Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy internal
| Deploy MMS |  | #REF! |  |  | Done by MMS team after matcmaking is disabled - confirm with them during release sync if a deployment is being done. Loop them in when light switch down
| PC Client Deploy - Use Promotion Job (Client) |  | #REF! |  |  | Whole build string, LiveCN, only Windows. Allow Live Promotions and BPT checked Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy Public
| Server Deploy |  | #REF! |  | Make sure Hotfix is underway before Deploying Server. Otherwise servers won't get new hotfixes for possibly 4 hours. | Start immediately after hotfix deploy, due to server prep time, hotfixes should be live just prior to sessions starting Fleet: LiveCN Cohort: Main Use fast deploy option for downtime releases. Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy internal
| Item | Status | Due by | Done by | Temp-Notes | Perma-Notes
| Nvidia: reply to already existing corresponding release thread in #ue-partner-nvidia-ext with courtesy status updates |  | 2025-07-21 |  |  | Usually Douglas Valkenaar, Alexander Gustev or Andrew Saritsky - #external-nvidia channel |  |  | Maybe?
| StW Whiteglove |  | #REF! |  |  | Poke ext-fccn-live with @s to start whiteglove
| BR Whiteglove |  | #REF! |  |  | Whiteglove is completed by both Epic CN and Tencent teams separately - need confirmation from both teams of a successful check.
| If help is needed flushing buckets |  | #REF! |  | Click "Direct control panel link" in next link | https://adminportal-website-management.ol.epicgames.net/fortnite/profileProxy?server=Fortnite%20China&moduleName=fortnite
| Re-enable Light Switch Up |  | #REF! |  |  | Ready once the whiteglove has been confirmed and without any issues Update status message to Fortnite is up! Notify Sula - Access has been re-enabled. @Sula Yu please re-enable from wegames side as well Notify in Mission Control and FN-Release-Deploy - No whiteglove callout and lightswitch up
| Re-enable CN alerts |  | #REF! |  |  | Unpause FN Grafana integration in OpsGenie https://epicgames.app.opsgenie.com/teams/dashboard/76f730d9-7346-4f83-b599-ab3589ba2fce/integrations
| Post in #buildfarm-support to remove the previous release version |  | #REF! |  |  | Reach out to Build Farm Support via #buildfarm-support channel in slack and ask them to remove the previous branch from horde after CN deploy is complete
| Archive previous release Slack channel |  | #REF!

## Submissions Checklist
| Item | Status | Due by | Completed by | Temp-Notes | Steps To Complete | Suggested Slack Post Text (unless otherwise stated) | Suggested Slack Thread Text (unless otherwise stated)
Pre-Candidate Build - MUST DO
| By Hard Lock: | IN PROGRESS
SUB | Ensure Sony publishing tools are up to date | TODO | 2025-07-17 |  | Slack: LINK | PS4: https://ps4.siedev.net/docs/master_submission PS5: https://p.siedev.net/docs/master_submission To find Sony Publishing Version: Look at the build logs from the "PS4 Client Full Package" step lists the version of the tools in the output Ping Luke Thatcher and/or Ben Woodhouse if you have issues
SUB | Make sure PS4 SIEE (07669) packages are being built | TODO | 2025-07-17 |  |  | //Fortnite/Release-34.10/FortniteGame/Build/FortniteBuild.xml
| By Pencils Down: | IN PROGRESS
SUB | Get engineer sign off of patch Sizes | TODO | 2025-07-18 |  | Slack: LINK | Tag fn-tech-patchreview in #fn-release-patchsizes. Try to send first prelim sizes soon after hard-lock
| By Cert Submission: | IN PROGRESS
SUB | FortniteContentBuilds: - This is Content On Demand (downloading additional stuff in the background which is only present on some platforms) Verify platforms below have been updated correctly: - PC/Windows - Android - PS4 - PS5 - Switch - XB1 - XSX - iOS Old Wiki | TODO | 2025-07-19 |  | Check the prior 3 content versions, and confirm they are present in the Rollback labels (code only versions will not appear) If the admin portal looks weird, confirm the .json file is showing the correct CLs for CONSOLES Escalate any issues to the #fn-tech-ext channel If Switch doesn't look correct, escalate to Justin Marcus to see if that is intended or not (something about Fort inquiry??) | 1. Navigate to the FortniteContentBuilds section of the Admin Portal 2. Under the Promotion Labels section, Look for the Live label (should be first) and open the dropdown 3. Open another window and go to the Release Log to see our live CLs 4. Copy the Live CL for PC/Windows and search for it in the admin portal's Live Label to verify it is correctly reflected a. Repeat this step for Android, PS4, PS5, Switch, XB1, XSX, iOS (Ignore XboxOne & XboxOneGDK) 5. Repeat steps 2-4a. This time for the Rollback label. a. Type Rollback into the filter, then hit the Label Name column header twice to find it. 6. The CL you are looking for is the CL immediately previous to the live CL. Look in Current & Previous Releases section of the Release Log 7. As a secondary check (FOR CONSOLES ONLY - NOT PC), you can navigate to the below file on the network drive (easiest to use a VM to work computer) P:\Builds\Automation\Fortnite\Config\ConsoleLiveLabels.json 8. Do a find and search of the live and immediately previous to live CLs to ensure they are present a. Can open the file in a text editor > Ctrl+F > Insert CL. It should return 5 hits (PS4, PS5, Switch, XB1, XSX)
Preparation
| Item | Status | Due by | Completed by | Temp-Notes | Steps To Complete | Suggested Slack Post Text (unless otherwise stated) | Suggested Slack Thread Text (unless otherwise stated)
| By Hard Lock: | IN PROGRESS
SUB | Review the Cert issues filter to make sure nothing egregious still needs to be fixed | TODO | 2025-07-18 |  | Double check to ensure cert impacting issues have been confirmed fixed on the current candidate | Dashboard - https://jira.it.epicgames.com/secure/Dashboard.jspa?selectPageId=25898
| AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK |  |  | AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK
| By Pencils Down: | IN PROGRESS
| AFTER 8PM ET PENCILS DOWN | AFTER 8PM ET PENCILS DOWN |  |  | AFTER 8PM ET PENCILS DOWN | AFTER 8PM ET PENCILS DOWN | AFTER 8PM ET PENCILS DOWN | AFTER 8PM ET PENCILS DOWN
SUB | Verify that the PS5/PS4 versioning is correct for the release. | TODO | 2025-07-19 |  |  | 1. Open the P drive and locate a recent build in this release branch. 2. Verify that the PS4 and PS5 build versions are correctly incremented from the previous release. *Previous release app versions can be found on the Release Log.
SUB | Make sure SwitchEngine version has been incremented. | TODO | 2025-07-19 |  |  | 1. Open the P4 navigate to the following file: Release-XX.XX > FortniteGame > Platforms > Switch > Config > SwitchEngine.ini 2. Verify that the Application Version, and ApplicationVersionString have been appropriately updated. *Previous Release version can be found on the Release Log.
SUB | Verify that LatestPatch folder contains last released patches | TODO | 2025-07-19 |  |  | 1. Navigate to the Latest Patch folder on the P drive: P:\Builds\Fortnite\MasterReleases\1.0 2. Open the appropriate folders for PS4/PS5/XB1/XSX and verify that the previous release versions have been updated to the last patch that successfully compeleted certification.
Pre-Candidate Build
| By Cert Submission: | IN PROGRESS
SUB | Request Patches: Create New Release for Nintendo | TODO | 2025-07-16
SUB | Request Patches: Fill out and submit new OMAS for Nintendo | TODO | 2025-07-16
SUB | Request Patches: SIEA (07022) (07022) - WIKI | TODO | 2025-07-16
SUB | Request Patches: SIEE (07669) (07669) - WIKI | TODO | 2025-07-16
SUB | Request Patches: PS5 Shared | TODO | 2025-07-16
SUB | Create Version on App Store Connect and check if any Publishing metadata updates are needed | TODO | 2025-07-16 |  |  | 1. Go to https://appstoreconnect.apple.com/apps 2. Select Fortnite 3. From the Distribution tab, in the left-hand column click the (+) button to add a new version if it does not already exist (Only two versions can be in at one time: the Live build and the Next build) 4. Sanity check that the metadata has carried over correctly 5. Confirm with publishing (Alex Conner/Emu Servais) if any screenshots or text need to be updated (The data present in App Store connect only appears in the App Installation Sheet, when confirming to install Fortnite. EGS metadata is found in Product Framework) * What's New in This Version -- metadata is not required as per 2.3.12 (listed as n/a for Notarization Review Guidelines Only) | :apple-bounce: CHECKLIST_VERSION App Store Connect Metadata | @Alex Conner @Ross Marabella @Zach Moore Are we planning on changing any of the screenshots or text on the iOS App Store Connect portal for CHECKLIST_VERSION? I am assuming no but would rather ask for sanity sake. :ty: in advance!
SUB | Verify the file system captures for Nintendo have been gathered by QA | TODO | 2025-07-19 |  | Slack: LINK | Details in this document https://docs.google.com/document/d/1krb18jjtEBn10duEBgaiklnLnN55RE5raKLL4acSX3c/edit#heading=h.xd3o88dyuuik Example Post
Release Candidate Build (Locked in)
IN PROGRESS
SUB | Create a cert thread in the Release channel. | TODO | 2025-07-20 |  |  | Pin it to the channel (example)
SUB | Update Release Log and Release Request | TODO | 2025-07-20 |  |  | 1. Update REAL-XXXX ticket's description with build CLs, backend CLs & patch sizes 2. Check Release Log to ensure that info is reflected in the upcoming releases section
SUB | Make local copies to your station for all platforms going to certification | TODO | 2025-07-20
SUB | Add build info to the relevant cert backends. (CCA/ CCB / MobileCert) | TODO | 2025-07-20 |  |  | Steps to Complete can be found in this WIKI
SUB | Set up the above cert environments to have the correct: - Server (CCA / CCB / DPQ / MobileCert) - MCP (CCA / CCB / DPQ / MobileCert) | TODO | 2025-07-20
SUB | Ensure cert backends are online (CCA / CCB / DPQ / MobileCert) | TODO | 2025-07-20 |  |  | 1. Go to the links in Col A "Deployments" Tab 2. Change the status drop down in the middle to "Host Limits" 3. Input desired hosts into the max header (in this case 1) 4. Hit Apply > Review > Save > Refresh Page 5. Ensure the circles are going green
SUB | CertSub Candidate: Patch Sizes | TODO | 2025-07-20 |  |  | Steps to Complete can be found in this WIKI
SUB | Send Akamai early estimate of patch sizes - Email | TODO | 2025-07-20
SUB | Notify Nvidia of the upcoming patch date and time - Email | TODO | 2025-07-20 |  |  | Email: GFN-DevOps-External@nvidia.com, ssolovyev@nvidia.com fliljegren@nvidia.com Format: MM/DD/YYYY, TIME_UTC_24H Example - 08/27/2018, 08:00 UTC
SUB | Notify AWS of the upcoming patch date, time, and sizes - Email | TODO | 2025-07-20 |  |  | epicgames-events@amazon.com
SUB | Notify Fastly of the upcoming patch date, time, and patch sizes - Slack Post | TODO | 2025-07-20 |  |  | #fastly-epicgames
SUB | Notify Akamai of the upcoming patch date, time, and patch sizes - Slack Post | TODO | 2025-07-20 |  |  | #vndr-akamai-ext
SUB | Notify Cloudflare channel of the upcoming patch date, time, and patch sizes - Slack Post | TODO | 2025-07-20 |  |  | #vndr-aws-egs-cloudfront-ext #vndr-cloudflare-ext
SUB | Notify ISP email group alias of the upcoming patch date, time and patch sizes - Email | TODO | 2025-07-20 |  |  | ext-fn-release-notify@epicgames.com
SUB | Request Patches: Email Xbox Account Manager | TODO | 2025-07-20 |  |  | "TO: Derek Russel <deruss@microsoft.com>, Epic Games WAM <epicwam@microsoft.com> CC: Release-team"
SUB | Update DevNet Thread with Incoming Patch Information | TODO | 2025-07-20 |  |  | PS4 and PS5
SUB | Upload Nintendo ROM and complete pre-submit waiver requests | TODO | 2025-07-20
SUB | Submit Switch the Switch build to lotcheck | TODO | 2025-07-20
SUB | Submit IOS for Notarization | TODO | 2025-07-20 |  |  | - Make sure to include the "test_accounts.xlsx" file - Make sure that the "FN External Testers" group is added to the build so it can be played on Live outside of the EU
SUB | Upload SIEA (07022) build | TODO | 2025-07-20
SUB | Upload SIEE (07669) build | TODO | 2025-07-20
SUB | Upload PS5 shared binary | TODO | 2025-07-20
SUB | Upload the Luna Client and send it to certification | TODO | 2025-07-20
SUB | Upload XB builds, verify the validator logs, and submit to cert. | TODO | 2025-07-20
SUB | Complete and save final MDT (PS5) | TODO | 2025-07-20
SUB | Update MDT: SIEA | TODO | 2025-07-20
SUB | Update MDT: SIEE | TODO | 2025-07-20
SUB | Rapid patch Submission: SIEA (07022) | TODO | 2025-07-20
SUB | Rapid patch Submission: SIEE (07669) | TODO | 2025-07-20
SUB | Rapid patch Submission: PS5 | TODO | 2025-07-20
Signoff and Submission
IN PROGRESS
SUB | Update Akamai with final patch sizes | N/A | 2025-07-20 |  | Only needed if we did not send RC build sizing
SUB | Final Scheduling: Xbox One / XSX | TODO | 2025-07-20
SUB | Final Scheduling PS5 | TODO | 2025-07-20
SUB | Final Scheduling PS4 | TODO | 2025-07-20
SUB | Upload PS4 Symbols to devnet | TODO | 2025-07-20
SUB | Upload PS5 Symbols to devnet | TODO | 2025-07-20
SUB | Upload XB1/XSX crash symbols through Xbox Send | TODO | 2025-07-20 |  |  | 1. Log into your Xbox Send account 2. Upload the XB1/XSX crash symbols from our RC build. 3. Send it to Sean White <seanwh@microsoft.com> and Andy Hess <andrewhess@microsoft.com> 4. Find the email titled "RE: [EXTERNAL] Re: Symbol missing on MS Partner for Xbox and XSX for Fortnite" and ping the thread letting them know that they have been sent over.
SUB | Final Scheduling: Switch | TODO | 2025-07-20
| Submit Build to One Store | TODO | 2025-07-20 |  |  | 1. Upload build to One Store. 2. Select Request for Review. 3. Copy paste the patchnotes for relevant release from row 20 of this sheet: https://docs.google.com/spreadsheets/d/1-eYN_be-_U1j34T4YW1R3NowDBHFy8pGL3YUX4Hf-Ik/edit?gid=474166268#gid=474166268&range=AP20 4. Submit.
SUB | Upload the Digital Turbine Candidate | TODO | 2025-07-20
SUB | Submit Android build to Oppo | TODO | 2025-07-20
SUB | Confirm with Luna that we're through certification. | TODO | 2025-07-20 |  |  | 1. Return to the Fortnite Overview in the Luna portal, check if the "alpha state" is set to "certified". *If the title is still certifying, ping Amazon in the submission thread to ask for an update.
SUB | Submit PC build to GFN | N/A | 2025-07-20 |  | GFN will scrape live.
Pre-Release
IN PROGRESS
SUB | Remove Cert Redirects | TODO | 2025-07-20 |  |  | DO NOT REMOVE PS4 IF WE'RE STILL IN RMT TESTING WITH SONY - CCA, CCB, DPQ, FortniteMobileCert
SUB | Spindown Cert Servers | TODO | 2025-07-20
SUB | Live: Update PS4/PS5/XB1/XSX/IOS fake Build Info | TODO | 2025-07-20 |  |  | Needs to be done otherwise you can't check Selective (MSFT)
SUB | Live: Update Switch Build Info | TODO | 2025-07-20 |  |  | NEVER REMOVE BUILDS FROM LIVE
SUB | Live: Update Android Build Info | TODO | 2025-07-20 |  |  | NEVER REMOVE BUILDS FROM LIVE
SUB | Prep AltStore Stage Source | TODO | 2025-07-20 |  |  | Can be done once cert complete - need ADP ID
SUB | Schedule Lightswitch Down in Admin Portal - Scheduling MUST happen at least 1 hour before the downtime start | TODO | 2025-07-20 |  | USE EXTREME CAUTION HERE: There is potential to bring the game down if you are not careful | 1. Go to Lightswitch 2.0 Page in the Admin Portal 2. Go to the "Add Scheduled Event" section at the bottom 3. Set Scheduled Time to the "Downtime" in the REAL-XXXX Ticket's Description a. cross-reference LS down time with the CHECKLIST_VERSION Release Strategy Email b. NOTE THIS TIME SHOULD BE SET TO EST 4. Set Status to: DOWN 5. Set Message to: Fortnite is down for maintenance 6. Set Add Actions to: Fortnite_Free_Platforms 7. Select Create Event 8. Double check the info in the new "Scheduled Events" section in the middle of the page - Processed should say No
SUB | Internal Release Email Template | TODO | 2025-07-20 |  | ALL PLATFORMS NEED TO BE THROUGH CERT BEFORE SENDING EMAIL | 1. Look up a previous email to use as a template Search for "online-infra-global@epicgames.com" to find them 2. Copy the formatting and replace content with CHECKLIST_VERSION's information a. Look at the REAL-XXXX Ticket for all info 3. Send to the recipients in Column H | TO: online-infra-global@epicgames.com, global-live-deployments@epicgames.com, FN-Live@epicgames.com | Fortnite - XX.YY Release - MM/DD @ 4:00am ET Release Ticket: REAL-XXXX Player Impact: VERIFY_AGAINST_SLACK_THREAD Fortnite matchmaking will be disabled at 03:30am ET, downtime will then begin at 04:00am and is estimated to conclude at 05:30am. When downtime begins players will be kicked from active sessions. Players may experience throttled logins as we come back online. Build Info: App: Fortnite INSERT_FROM_REAL_TICKET Clients Windows: ++Fortnite+Release-XX.YY-CL-XXXXX PS4: ^^ PS5: ^^ Xbox: ^^ XSX: ^^ Switch: ^^ Android (EG): ^^ UEFN: ^^ Backend Server: ++Fortnite+Release-XX.YY-CL-XXXXX MCP: XX.YY.nnn-rXXXXX UEFN: ++Fortnite+Release-XX.YY-CL-XXXXX Patch Sizes Windows: X.XX GB PS4: X.XX GB PS5: X.XX GB XSX: X.XX GB Xbox: X.XX GB Switch: X.XX GB Android: Low End: X.XX GB / High End: X.XX GB Testing Requirements: Whiteglove Communication: #fn-release-deploy-ext
SUB | External Release Email Template | TODO | 2025-07-20 |  | ALL PLATFORMS NEED TO BE THROUGH CERT BEFORE SENDING EMAIL | 1. Look up a previous email to use as a template Search for "partners-liveops-alerts@epicgames.com" to find them 2. Copy the formatting and replace content with CHECKLIST_VERSION's information 3. Send to the recipients in Column H | TO: partners-liveops-alerts@epicgames.com BCC: public-alerts@noa.nintendo.com, sie-noc@sony.com, xoc@microsoft.com, epic-issues@vivox.com, noc@subspace.com, release-team@epicgames.com | Fortnite - XX.YY Release - MM/DD @ 4:00am ET Player Impact: TAKE_FROM_MESSAGE_ABOVE Fortnite matchmaking will be disabled at 03:30am ET, downtime will then begin at 04:00am and is estimated to conclude at 05:30am. When downtime begins players will be kicked from active sessions. Players may experience throttled logins as we come back online.
SUB | Send "Release is a GO" email | TODO | 2025-07-20 |  | ALL PLATFORMS NEED TO BE THROUGH CERT BEFORE SENDING EMAIL | 1. Look up previous deploy email using the string "is a GO for" 2. Copy the formatting and replace content with CHECKLIST_VERSION's information a. Ship List can be found pinned in the release-CHECKLIST-VERSION-ext slack channel b. Helpful Links can be found in the google calendar c. Down Time, Morning Crew / Patch Sizes can be found in the REAL-XXXX Ticket's Description | TO: fn-release-updates@epicgames.com | Replace with Pre-Pop
___ ___ __ __ ___ _ __ _ _ _ ¦ _ \ / _ \ \ \ / / o O O ¦ \ ___ ¦ '_ \ ¦ ¦ ___ ¦ ¦¦ ¦ ¦ / ¦ (_) ¦ \ \/\/ / o ¦ ¦) ¦ / -_) ¦ .__/ ¦ ¦ / _ \ \_, ¦ ¦_¦_\ \___/ \_/\_/ TS__[O] ¦___/ \___¦ ¦_¦__ _¦_¦_ \___/ _¦__/ _¦"""""¦_¦"""""¦_¦"""""¦ {======¦_¦"""""¦_¦"""""¦_¦"""""¦_¦"""""¦_¦"""""¦_¦ """"¦ "`-0-0-'"`-0-0-'"`-0-0-'./o--000'"`-0-0-'"`-0-0-'"`-0-0-'"`-0-0-'"`-0-0-'"`-0-0-'
Lead-up to Downtime - Deployment Owner
| Item | Status | Due buy | Done by | Temp-Notes | Perma-Notes
During Downtime - Deployment Owner
| Item | Status | Due Buy | Done by | Temp-Notes | Perma-Notes
Post-Release - Deployment Owner
| Item | IN PROGRESS | Due Buy | Done by | Temp-Notes | Perma-Notes
SUB | Update the master cert timing tracker sheet | TODO | 2025-07-21 |  |  | Tracker Google Sheet -- tracking Switch / PS4 (SIEE (07669) /SIEA (07022) ) / PS5 / MSFT / Apple
SUB | Update Patch Size Tracking | TODO | 2025-07-21 |  |  | Remember to add Install time thresholds as well
SUB | Increment Switch version | TODO | 2025-07-21
SUB | Increment PlayStation versions | TODO | 2025-07-21
SUB | Increment iOS version | TODO | 2025-07-21
SUB | Update Sony LatestPatch folder to contain these patches | TODO | 2025-07-21 |  |  | MasterReleases->1.0->Create folder for appropriate app version
SUB | Update Nintendo LatestPatch folder to contain these patches | TODO | 2025-07-21
SUB | Update Xbox LatestPatchfolder to contain these patches | TODO | 2025-07-21
Not currently relevant (re-visit as needed)
| Item | Status | Due by | Done by | Temp-Notes | Perma-Notes
| Confirm MCP deploy percentage with OGS (tag Pete Axt & Joe Pintozzi) and Live Ops. WIKI |  | 2025-07-20 |  | Slack: LINK | 1. Make a post in #epic-live-operations-ext or #on-dbs-game-services-ext using the suggested text in Column H | @Joe Pintozzi @Pete Axt Just confirming we are targeting 50% DeployHostPercentage during downtime as usual for the CHECKLIST_VERSION MCP deploy tomorrow?
| Create Bug Bids Page |  | 2025-07-17 |  | Bug Bids Page: LINK | 1. Go to the previous version's Bug Bids Page (here) 2. Click "..." > Copy > Copy 3. Change title to Bug Bids for CHECKLIST_VERSION > Publish 4. Note the current values in the Issues Left column 5. Edit the page > Update the hard coded HL-1w and HL dates as per the FN Schedule 6. Clear the hardcoded values in HL-1W and HL columns (highlight and delete) This section is borked until the <> is re-added back. Need to do manually until then :((((( 7. Select the <> icon to open in source editor 8. Find the version you copied from, replace all with the version you want > Apply > Update 9. Ensure the values have changed
| Schedule Send Bug Bids Email 10 days prior to Hard Lock date at 10:30am |  | 2025-07-17 |  | Send scheduled for DATE | 1. Go to GMail and compose a new email 2. Send email using the suggested text in Column H 3. Link the bug bids page to the blue text 4. Change Day MM/DD to the date of review (monday the week of HL) 5. Once done, hit the drop down arrow on the blue Send button > Schedule Send 6. Pick a Date & Time > 10 days prior to Hard Lock date at 10:30am (See Cell F2) 7. Schedule Send 8. Go to your gmail > Scheduled (below sent) and review the preview to ensure it is all correct 9. Paste the scheduled send info in column F for reference | The CHECKLIST_VERSION Bug Bids wiki has been created and is ready for you to enter your bids! We will start reviewing at morning sync next week on DAY MM/DD. Reminder, there's a link on the top of this page you can use to look at historic fix rate data for your components, which you can use to reason about what your teams can realistically tackle leading up to CHECKLIST_VERSION. Past Bug Bid pages are also still available for review under the Release Accountability parent page. CHECKLIST_VERSION Dashboard: [Link] Doing this thinking now, ahead of the hectic bugfix stage, will help identify rational targets you can use to guide triage activities & tradeoff decisions. Thanks, Release Team | TO: Release-Team@epicgames.com CC: FN-Prod-All <FN-Prod-All@epicgames.com>, FNE Release <fne-release@epicgames.com> Subject: Bug Bids for CHECKLIST_VERSION
| (Joe) I would just completely kill this line in favor of the Build Protection line just above. Run Keep Release Candidate job for all final client candidate CLs. |  | 2025-07-19 |  | PLATFORM_1: HORDE_JOB_LINK PLATFORM_2: HORDE_JOB_LINK PLATFORM_3: HORDE_JOB_LINK | 1. Go to the REAL-XXXX ticket for this release to see the final candidate CLs 2. Go to the Promotions tab of Main Horde 3. Select the blue New Job button in top right 4. Change template dropdown to Keep Release Candidate 5. Put the first CL in the Change field and set the associated Promote Platforms field. Then Start Job. a. Re-Run for all Client CLs with their associated Promote Platforms field.
| Verify the Android APK allowlist is in the game config file |  | 2025-07-20 |  | Release Team no longer needs to send hotfixes to update CRC values when we ship new Android client builds. The 13.40 values need to stay, but the Android APK Whitelist hotfixes no longer function in 23.50+ . This is now being done on the AntiCheat side via Dragonfly. | Verify it is in the game config file
| Review Android APK allowlist syntax is included and correct in Release QA swarm link and in PredeployA files |  | 2025-07-21 |  | Release Team no longer needs to send hotfixes to update CRC values when we ship new Android client builds. The 13.40 values need to stay, but the Android APK Whitelist hotfixes no longer function in 23.50+ . This is now being done on the AntiCheat side via Dragonfly.
| Create a Jira for StW Calendar/Store to be update/reviewed (CN/RoW) |  | 2025-07-17 |  |  | Assign to Dav Harnish and CC Henry Meredith in comments https://jira.it.epicgames.net/browse/FORT-247162
| Check Android APK size and make sure it is under 150 MB |  | 2025-07-19 |  |  | Look at APK in the build folder
| Create a tab in FN Playlist Planning sheet and let stakeholders know in #fn-release-playlistplanning-ext that it now exists |  | 2025-07-17 |  |  | https://confluence.it.epicgames.com/display/FORT/Playlist+Planning Note: If its a .10 release, spin up a thread. If its not, then mark this task as N/A.
| Schedule Meeting: Release Notes Signoff |  | 2025-07-18 |  | No Release Notes! | Thurs. of CertSub week
| Release Notes: Initial Setup and Email Sent |  | 2025-07-18 |  | No Release Notes!
| Schedule Calendar Reminders: Release Notes Section Owners |  | 2025-07-18 |  | No Release Notes! | 1 each day for 2 document days of release notes
| Order breakfast for morning of publish day |  | 2025-07-16 |  | Please bring this back!!!
| Send initial IOS Submission email |  | 2025-07-16
| Update Google Play Roadmap email (if applicable) |  | 2025-07-16 |  |  | to: Dan Song <mtd@google.com(opens in new tab)> Lawrence Koh <lawrencekoh@google.com(opens in new tab)> CC release-team Jocelyn Hans
| Send Release Notes 1st Draft to FN-Release-Updates |  | 2025-07-16 |  | No Release Notes!
| Forward CN patch notes to EGC |  | 2025-07-19 |  | No Release Notes! | Forward version patch notes for China to Martin Yu. Martin will review and deliver to Tencent.
| Add IOS Whitelist Hotfix to MobileCert |  | 2025-07-20
| Check iOS Compressed File Size |  | 2025-07-18 |  | Compressed File Size: MB Previously in 13.40 Release flagged if greater than 200 MB. Compressed sizes have increased in allowance from Apple. We should still note what the size is and report to tech-mobile Jira for investigations is FORT-772296 This process may be something we can remove, but need to keep an eye out for a few releases. [thread] | 1. Go to https://appstoreconnect.apple.com/apps 2. Select Fortnite 3. Select TestFlight 4. Select the RC candidate Version and Build 5. View the Build Metadata for Compressed File Size 6. Record the size and pass along to Tech-Mobile
| Audit MobileCert environment config for potential cert blockers |  | 2025-07-19
| Configure MobileCert Build Info |  | 2025-07-19
| MobileCert: MCP Update |  | 2025-07-19
| MobileCert: Server Promote |  | 2025-07-19
| Cert Submission: iOS |  | 2025-07-19
| Send email notifying Apple contacts that build is uploaded |  | 2025-07-19
| Send email notifying Google contacts that build is uploaded |  | 2025-07-19
| Remove MobileCert Redirect |  | 2025-07-20
| Live: Update iOS Build Info |  | 2025-07-20
| Remove Android Build Info from MobileCert |  | 2025-07-20
| Live: Update LiveCN Build Info |  | 2025-07-20 |  |  | Deploy will be coordinated with TC in #ext-fncn-live in Slack. TC will flip WeGame switches. THIS STEP IS ONLY NEEDED IF STAGING THE CN BUILD FAILED.
| Update Apple Cert Timing Tracker |  | 2025-07-21
| Update EULA if requested by Legal |  | 2025-07-18
VVV To be Re-Added Once iOS comes back VVV
| Make sure PredeployA Hotfix Files are set back to appropriate Android Whitelist and IOS Banning syntax for LOPS to copy at time of release |  | 2025-07-20 |  | Only Android? | Android: Whitelist syntax needs to be added IOS: Remove the following: [/Script/FortniteGame.FortGameModeZone] BanCodeAction_20=(AnyReason=2, UnsignedIPA=0) BanCodeAction_28=(AnyReason=2, NoIOSCryptInfo=0)
| Make sure PredeployA Hotfix Files are set back to appropriate Android Whitelist and IOS Banning syntax for QA to not be blocked |  | 2025-07-21 |  |  | Android: Whitelist synatx needs to be removed IOS: Add the following: [/Script/FortniteGame.FortGameModeZone] BanCodeAction_20=(AnyReason=2, UnsignedIPA=0) BanCodeAction_28=(AnyReason=2, NoIOSCryptInfo=0
| Determine if release breaks Replays and/or if we should whitelist any old CLs |  | 2025-07-18 |  | https://wiki.it.epicgames.net/pages/viewpage.action?spaceKey=FORT&title=Replay+Whitelisting | Should be considered if we are breaking replays of a major Live event from the previous release Ask Shak or Matt Grandstaff
| Test verify PS4 remaster jobs have no errors or warnings |  | 2025-07-18 |  |  | Nightly Job "Publish PS4 Remaster Submission Packages (SIEA (07022) Only)"
| Confirm all Non-Unity warnings and errors are fixed or benign |  | 2025-07-18
| PS4: Update R:\Analytics\sony_version.csv |  | 2025-07-21 |  | I refuse | Instruction Doc
| Make sure PredeployA Hotfix Files are set back to appropriate Android Whitelist and IOS Banning syntax for QA to not be blocked |  | 2025-07-21 |  |  | Android: Whitelist synatx needs to be removed IOS: Add the following: [/Script/FortniteGame.FortGameModeZone] BanCodeAction_20=(AnyReason=2, UnsignedIPA=0) BanCodeAction_28=(AnyReason=2, NoIOSCryptInfo=0
| [24 hrs before] Inform Tencent and Community |  | #REF! |  |  | 24 hrs before - Inform in #ext-fncn-live @Sula Yu and CN QA deply captain Check EGC QA Checklist > Captain tab for additional @ https://docs.google.com/spreadsheets/d/1nUx7qP1aLLU6D1VVv0Q4mx18aMMG_tz5vmQC0Z9wxgc/edit?usp=sharing
| [24 hrs before] Release JIRA |  | #REF! |  |  | Link Release management Jira ticket here
| [2 hours befire] Hotfixes Checked In and Previewed |  | #REF! |  | Check fn-release-team around 4PM ET | RQA will provide a Swarm shelf to approve and merge around 4PM ET https://docs.google.com/spreadsheets/d/1w5PQcnciR-lbbU6H6m0aaqgiFWNRbttSr7uEoCmKUzk/edit#gid=2063781583
| [2 hours before] Schedule Downtime (Fortnite) |  | #REF! |  | Schedule sometime before 4:40pm | https://adminportal-website-management.ol.epicgames.net/lightswitch2/schedule/fortnitelivecn?server=Lightswitch&moduleName=lightswitch
| [1 hrs before] Verify Client, Server, and MCP for release |  | #REF! |  |  | Pinged in Release Private if unsure of any changes
| [1 hrs before] Internal Release Email |  | #REF! |  |  | fncn-live@epicgames.com, fn-live, online-infra, global-live-deployments
| [35 min before] Turn off FN CN Alerts |  | #REF! |  | Poke liveOPS at MMS disable | Request liveOPS pause FN Grafana integration in OpsGenie https://epicgames.app.opsgenie.com/teams/dashboard/76f730d9-7346-4f83-b599-ab3589ba2fce/integrations
| [35 min before] Alternatively, Set False to True for Playlist Restrictions Configuration section at https://adminportal.ol.epicgames.net/fortnite/profileProxy?server=Fortnite%20China&moduleName=fortnite Click MMS at top and scroll down to Playlist Restrictions Configuration Set disableAllMatchmaking to true |  | #REF! |  |  | 35mins before LS down Edit directly under Admin Portal https://adminportal-website-management.ol.epicgames.net/fortnite/systemFiles Make sure you are in "Fortnite China" Notify fn-release-deploy (FN-Deploy Public) and Mission Control slack channels |  | For Old Hotfix Method: DefaultGame.ini [/Script/FortniteGame.FortGameInstance] bBattleRoyaleMatchmakingEnabled=false
| Item | Status | Due by | Done by | Temp-Notes | Perma-Notes
| Confirm Lightswitch down status |  | #REF! |  |  | Check status has switched to DOWN - https://adminportal-website-management.ol.epicgames.net/lightswitch2/schedule/fortnitelivecn?server=Lightswitch&moduleName=lightswitch
| Lightswitch down notifications |  | #REF! |  |  | Post message in fn-release-deploy and Mission Control slack channels
| We Games access disabled |  | #REF! |  |  | Notify ext-fncn-live to disable access for we games. More often than not this is Sula, but confirm it isn't a different Tencent employee
| Deploy "Go Live" INI Hotfix config (make sure this is done before server deploy to ensure hotfix config is pulled correctly) |  | #REF! |  |  | Can move on to MCP and Client deploys until Hotfix is done. Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy internal
| Deploy MCP |  | #REF! |  |  | Deploy %: 50% Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy internal
| Deploy MMS |  | #REF! |  |  | Done by MMS team after matcmaking is disabled - confirm with them during release sync if a deployment is being done. Loop them in when light switch down
| PC Client Deploy - Use Promotion Job (Client) |  | #REF! |  |  | Whole build string, LiveCN, only Windows. Allow Live Promotions and BPT checked Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy Public
| Server Deploy |  | #REF! |  | Make sure Hotfix is underway before Deploying Server. Otherwise servers won't get new hotfixes for possibly 4 hours. | Start immediately after hotfix deploy, due to server prep time, hotfixes should be live just prior to sessions starting Fleet: LiveCN Cohort: Main Use fast deploy option for downtime releases. Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy internal
| Item | Status | Due by | Done by | Temp-Notes | Perma-Notes
| Nvidia: reply to already existing corresponding release thread in #ue-partner-nvidia-ext with courtesy status updates |  | 2025-07-21 |  |  | Usually Douglas Valkenaar, Alexander Gustev or Andrew Saritsky - #external-nvidia channel
| StW Whiteglove |  | #REF! |  |  | Poke ext-fccn-live with @s to start whiteglove
| BR Whiteglove |  | #REF! |  |  | Whiteglove is completed by both Epic CN and Tencent teams separately - need confirmation from both teams of a successful check.
| If help is needed flushing buckets |  | #REF! |  | Click "Direct control panel link" in next link | https://adminportal-website-management.ol.epicgames.net/fortnite/profileProxy?server=Fortnite%20China&moduleName=fortnite
| Re-enable Light Switch Up |  | #REF! |  |  | Ready once the whiteglove has been confirmed and without any issues Update status message to Fortnite is up! Notify Sula - Access has been re-enabled. @Sula Yu please re-enable from wegames side as well Notify in Mission Control and FN-Release-Deploy - No whiteglove callout and lightswitch up
| Re-enable CN alerts |  | #REF! |  |  | Unpause FN Grafana integration in OpsGenie https://epicgames.app.opsgenie.com/teams/dashboard/76f730d9-7346-4f83-b599-ab3589ba2fce/integrations
| Post in #buildfarm-support to remove the previous release version |  | #REF! |  |  | Reach out to Build Farm Support via #buildfarm-support channel in slack and ask them to remove the previous branch from horde after CN deploy is complete
| Archive previous release Slack channel |  | #REF!

## WIP Chrono (hidden)
V5.5 | Branch Open Date: | 2025-01-06 |  |  | Schedule Bug Bids Email To Go Out On This Date | Update In Progress
2025-07-17 | Hard Lock: | 2025-01-28 |  |  | 2025-01-18 | Information to gather
| Pencils Down: | 2025-02-07 |  |  | INSERT_REAL_TICKET
| Cert Submission: | 2025-02-13 |  |  | ROS Sheet
| ROW Deploy: | 2025-02-21 |  |  | ROS Zoom
| Item | Status | Due by | Completed by | Temp-Notes | Steps To Complete | Suggested Slack Post Text (unless otherwise stated) | Suggested Slack Thread Text (unless otherwise stated) | Automation? | Must Do
Before Branch Open |  | IN PROGRESS
RM | Branching Dates Slack Email Kickoff | TODO | 2024-12-30 |  | Slack: LINK | 1. Spin up a thread titled ":thread: Release-Version Branching" in #buildfarm-support-ext and use the suggested text in column H for the thread messaging 2. Search for previous email (from a similar version number) titled: "[Branch News]" 2. Copy the formatting into a new email and swap in the appropriate information gleaned from the buildfarm thread | Thread name in cell notes - Example for a .30 Based on the roadmap: - Branch Operation/Creation: DAY_DATE from BRANCH - Branch Opening/Work Cutover (9am ET): DAY_DATE Sending out initial email NEXTday afternoon for wider knowledge. @release-team @buildfarmsupport @p4admins @fn-buildhealthqa | Thread name in cell notes - Example for a .00 Hello! It's about that time again. CHECKLIST_VERSION/Dev-FN-XX Branch Operation is DAY_DATE and officially opens for business DAY_DATE morning per the roadmap. Based on the roadmap: Dev-FN-XX - Branch Operation/Creation: DAY_DATE from BRANCH - Branch Opening/Work Cutover (9am ET): DAY_DATE XX.00: - Branch Operation/Creation: DAY_DATE from BRANCH - Branch Opening/Work Cutover (9am ET): DAY_DATE Sending out initial email Tuesday afternoon for wider knowledge. Will be pushing extra hard on proxy servers. Has there been changes to the proxy server process and is the wiki up to date? @release-team @buildfarmsupport @p4admins @fn-buildhealthqa | Yes
RM | If Season Launch: Branching Email - Go Ahead and Sync Reply | TODO | 2025-01-02 |  | Should be done on the friday the week prior to branch open | 1. Reply to Branch News email with a "branch is now fully open" message 2. Search for previous XX.00 email titled: "[Branch News]" 3. Copy the formatting into a reply to the original email from row 34 and swap in the appropriate information |  |  | Yes
On Branch Open |  | IN PROGRESS
RM | Branching Email - Branch is now fully open! | TODO | 2025-01-06 |  |  | 1. Reply to Branch News email with a "branch is now fully open" message 2. Search for previous email (from a similar version number) titled: "[Branch News]" 3. Copy the formatting into a reply to the original email from from row 34 and swap in the appropriate information |  |  | Yes
RM | Ensure "Time Offset" is set to the main branches' season start date | TODO | 2025-01-06 |  | Commit CL: 12345 | 1. Go to the below file in p4 and open //depot/UnrealMCP4/Infrastructure/ansible/noredist/inventory/group_vars/tag_Role_fortnite-service-gamedevlatest.yml 2. Search for: config.com.epicgames.modules.profile.time_offset_days: 3. See what the value is currently and calculate what day in the calendar it relates to counting from todays date Use Date Calculator 4. Update the value to correspond to the start date of the season that main is set to (deploy day) Use FN Release Schedule to determine that day 5. Use either of the two templates to the right (depending on increasing or decreasing the offset value) for the CL description | P4 Description (if increasing offset value due to main being a new season) ---------------------------------------------------------------------- Increasing "Unreal Time Offset" to +XX days so it aligns with the start of NEXT_MAJOR_VERSION. This will avoid the DailyQuest Error for anyone working off it, as the Main MCP is now set to Season SEASON_NUMBER and it needs to be within that season's calendar window. Will remove the offset once we're naturally there. #QAReview #JIRA none #rnx | P4 Description (If decreasing offset value due to current offset value creeping into new season before main has switched) ---------------------------------------------------------------------- Reducing "Unreal Time Offset" to +XX days so it aligns with the start of NEXT_MAJOR_VERSION as it was starting to creep into the FUTURE_MAJOR_VERSION date range. This will avoid the DailyQuest Error for anyone working off it, as the Main MCP is still set to Season SEASON_NUMBER and it needs to be within that season's calendar window. Will remove the offset once we're naturally there. #QAReview #JIRA none #rnx
RM | Create fn-release-xx-xx-ext Slack channel and invite groups/users listed in Columns H/I | TODO | 2025-01-06 |  | Slack: LINK | 1. Create a new slack channel using the naming format "fn-release-xx-xx-ext" a. Type /channel and press enter to bring up the window b. Select fn for the prefix c. Channel name = release-XX-YY d. Check Allow Non-Employees In the Channel e. Skip Invite Users & Topic for now f. Description = Coordination Channel for the CHECKLIST_VERISON Release g. Result should look like: fn-release-28-20-ext 2. Add the people in columns H and I 3. Create an IT request to add the 'Fortnite External QA' workspace a. Send a message to it-helpdesk with the following message: Hello there, can I please have the `Fortnite External QA` Workspace added to the newly created #fn-release-CHECKLIST_VERSION-ext channel? Thanks in advance! | Internal Friends To Add (can add all at once, may have to manually adjust the red ones) ---------------------------------------------------------------------- @release team @release qa @fn-perfprod @blaine christine @community_swat @greg garnhart @tristan hardy @fn-buildhealthqa @liveqa @david lubell @Gaëtan Gireme @Eric Day | External friends need to be added with the '/user add @username' command (These are all Frima folks) NOTE: copy/pasting this list may not work. If not, add one by one (up to 15 at a time) ---------------------------------------------------------------------- Batch 1 @Mathieu Roy @Francois Guimond @Jonathan Fecteau @Simon Castonguay @Charles Rheaume @MarcAndre Cossette @Laurie Bernard @Maryeve Boivin @Fourat Jellouli @Maxime Vaillancourt @Danick Carpenter @Sebastien Olscamp @Steven Comeau @Michael Desharnais Batch 2 @Camille Gendreau @Samuel Carrier @Jimmy Beaubien @Annick Dunn @David Savard @JeanGabryel Caron @Katherine Bergeron @Gabriel Levac @Olivier Levesque @Jean-Simon Racine @Gabriel Desroches @Michael Coulombe @Alex St-Louis @ben massoglia | Maybe?
RM | Create Release Request | TODO | 2025-01-06 |  | JIRA Ticket: LINK | 1. Go to the Release Ticket Template 2. Move > Clone 3. Change Name in the naming format of: [FN] CHECKLIST_VERSION Release |  |  | Yes
RM | Create Release JIRA Dashboard | TODO | 2025-01-06 |  | Dashboard: LINK | 1. Go to the Release Dashboard Template 2. Go to the "..." on the top right and Copy Dashboard 3. Input the name using the format: CHECKLIST_VERSION Release Dashboard 4. Set "Add Viewers: Group to Any Logged In User and press +Add 5. Set "Add Editors" to the AD-Jira-FNRM Group +Add 6. When complete, Press Add at the bottom 7. Go to the bottom of the dashboard to the 2 Controller Widgets a. Set the red one affect version & blue fix version to the CHECKLIST_VERSION 8. Add the Burndown chart using the steps in column H | Steps for adding Release Burndown Chart: ---------------------------------------------------------------------- 1. Go to the Release Burndown Template Tab > Duplicate and rename 2. Add Branch Open Date (C2) using the FN Release Scheduele Sheet (row 16) 3. Adjust the other milestone gates (column A) to thier corresponding rows for their dates using the FN Release Scheduele Sheet 4.In the ReleaseList Tab, copy cells B3/B4 and paste into B2 5.Input this checklist's version (as a string "XX.XX") into Cell B4 6. Edit the title of the graph to this checklist's version tab (double click text) a. 3 vertical dots on graph > Publish > Link tab > copy link 7. Go back to this checklist's version Dashboard > JIRA Burndown > 3 horizontal dots > Paste in External Page Link |  | Maybe?
RM | Set Slack channel Topic to Release Manager and Dashboard Link | TODO | 2025-01-06 |  | Slack: LINK | 1. Go to fn-release-xx-xx-ext channel 2. Select the channel name at the top 3. Enter the suggested text in Column H in the Topic Section a. Person 1/2 are row 22 of the FN Schedule Sheet b. Set the Fix and Affects Version prior to creating the Dashboard Link from Controller (bottom right widget) with "..." > "Generate Permalink" > Right Click & Copy Link i. Go to Rebrandly > New Link > Paste Permalink > Leave Branded Domain > Set Signature slug to Release Version ii. Final should look like epic.gm/28-10 4. Copy the link to the REAL-XXXX ticket from step 36 a. Go back to Rebrandly > New Link > Paste REAL-XXXX JIRA Link> Leave Branded Domain > Set Signature slug to REAL-XXXX i. Final should look like epic.gm/REAL-4404 | Slack Topic: ---------------------------------------------------------------------- RM: @PERSON1 @PERSON2 ¦ Dashboard: https://epic.gm/XX-XX ¦ Release JIRA Ticket: https://epic.gm/REAL-XXXX ¦ Need a Hotfix? https://epic.gm/Hotfix ~ Email `release-team-oncall` to page Release-Team outside of office hours ~ Go here for more info: https://epic.gm/3fl
RM | Create Bug Bids Page | TODO | 2025-01-06 |  | Bug Bids Page: LINK | 1. Go to the previous version's Bug Bids Page (here) 2. Click "..." > Copy > Copy 3. Change title to "Bug Bids for CHECKLIST_VERSION > Publish 4. Note the current values in the Issues Left column 5. Edit the page > Update the hard coded HL-1w and HL dates as per the FN Schedule 6. Clear the hardcoded values in HL-1W and HL columns (highlight and delete) 7. Select the <> icon to open in source editor 8. Find the version you copied from, replace all with the version you want > Apply > Update 9. Ensure the values have changed |  |  | Yes
RM | Schedule Send Bug Bids Email 10 days prior to Hard Lock date at 10:30am | TODO | 2025-01-06 |  | Send scheduled for DATE | 1. Go to GMail and compose a new email 2. Send email using the suggested text in Column H 3. Link the bug bids page to the blue text 4. Change Day MM/DD to the date of review (monday the week of HL??) 5. Once done, hit the drop down arrow on the blue Send button > Schedule Send 6. Pick a Date & Time > 10 days prior to Hard Lock date at 10:30am 7. Schedule Send 8. Go to your gmail > Scheduled (below sent) and review the preview to ensure it is all correct 9. Paste the scheduled send info in column F for reference | EMAIL TEMPLATE: ---------------------------------------------------------------------- The CHECKLIST_VERSION Bug Bids wiki has been created and is ready for you to enter your bids! We will start reviewing at morning sync next week on DAY MM/DD. Reminder, there's a link on the top of this page you can use to look at historic fix rate data for your components, which you can use to reason about what your teams can realistically tackle leading up to CHECKLIST_VERSION. Past Bug Bid pages are also still available for review under the Release Accountability parent page. CHECKLIST_VERSION Dashboard: [Link] Doing this thinking now, ahead of the hectic bugfix stage, will help identify rational targets you can use to guide triage activities & tradeoff decisions. Thanks, Release Team | TO: Release-Team@epicgames.com CC: FN-Prod-All <FN-Prod-All@epicgames.com>, FNE Release <fne-release@epicgames.com> Subject: Bug Bids for CHECKLIST_VERSION | Yes
RM | Create tab in Game Config Sheet | TODO | 2025-01-06 |  | Game Config Sheet: LINK | 1. Go to the Automated Template (Release) tab of the Game Config Sheet 2. Duplicate and rename to the version number of this checklist |  |  | Maybe?
RM | Setup Release JIRA Dashboard's: - Schedule - Links | TODO | 2025-01-06 |  | Dashboard: LINK | 1. In the Dashboard, mouse over the Schedule section > "..." > Edit 2. Input the dates for: Branch Opening , Hard Lock, Pencils Down, Cert Sub, Publish from the FN Release Schedule (cells 16,18,19,20,5) 3. Input the RM owners from cell 22 of the FN Release Schedule (in between the name syntax) 4. Input the link to the Bug Bids page and update the text 5. Input link to the appropriate tab of the Game Config Tracker. 6. Input link to the associated release channel 7. Save |  |  | Maybe?
RM | Update MOTD in UGS to have Lockdown dates & JIRA filter link Wiki Old Wiki | TODO | 2025-01-06 |  | Commit CL: 12345 | 1. Go to the following file in P4 while in the same workspace //Fortnite/release-VERSION_NUMBER/FortniteGame/Build/UnrealGameSync.ini 2. Get latest > Checkout and Open 3. Create a pending CL using the suggested P4 Description in Column H --> 4. Scroll to the bottom of file 5. Copy text from column i and overwrite the "Message=.... text currently in the file" 6. Add the dates from FN Release Calendar 7. Edit and check the link to the dashboard to ensure its working 8. Save and commit CL using the submit tool You will run into a robomerge conflict. Here is how to resolve that: 1. Use robomerge to make a shelf in the downstream branch of the conflict 2. Unshelve the file in this new pending CL 3. Get latest on the file 4. RC > Resolve 5. Run Merge Tool 6. Scroll down to the conflict (or use the red arrows at the top) and remove the Yellow & Green blocks of text (leaving the blue one). 7. Save and open the file to ensure the intended changes are there 8. Once satisfied, commit the file, and hit retry on the robomerge blocker to ensure that is resolved correctly. | P4 Pending CL Description: ---------------------------------------------------------------------- Updated Lockdown Dates & JIRA Filter Link on MOTD in UGS for CHECKLIST_VERSION #jira none #rnx #fyi stan.hormell | Message=:alert: Hard Lock = MM/DD 8PM ET ¦ Pencils Down = MM/DD 8PM ET ¦ CertSub = MM/DD 9am ET ¦ Release = MM/DD 4am ET [Jira Dashboard](https://epic.gm/XX-XX)
RM | Verify UGS MOTD in Main shows the below information (completed by #buildfarm-support-ext) - Main is now XX.00 - Target Release-XX.XX - Branch Creation Date - Branch Open Date | TODO | 2025-01-06 |  |  | 1. Open UGS 2. Go to the Main Tab (need to import the project's .uproject file) 3. Verify you see the correct information
RM | Update Fortnite Release Calendar with the below dates for all versions from this checklist's season and the following season found in the FN Release Schedule - Row 16: Branch Opening - Row 17: Development Complete - Row 18: Hard Lock - Row 19: Pencils Down - Row 20: Cert Sub - Row 5: Live - Row 5 of next column(s): HF(s) Live | TODO | 2025-01-06 |  |  | 1. Go to the FN Release Schedule to get the dates 2. Go to Google Calendar 3. Find the listed milestones in Column A for the previous release and duplicate their events 4. Update the event name and date 5. Save |  |  | Yes
RM | Create a Jira for BR Calendar/Store/Shop to be update/reviewed | TODO | 2025-01-06 |  | JIRA Ticket: LINK | 1. Go to the JIRA Template 2. Move > Clone 3. Rename ticket in the format: Verify ROW Store/Calendar (BR) for CHECKLIST_VERSION Deploy Scheduled for DD/MM/YY 4. Assign to Juan Romero 5. CC the following in the comments & add them as "Watchers" -- CC: [~juan.romero] [~nick.owens] [~steve.allison] [~amanda.perry] [~matthew.geisen] [~alison.mckenzie] 6. Set Fix Version to the version for this checklist |  |  | Yes
RM | Verify BranchFoundIn in JIRA is already populated for this release if not, request it be done in #fn-jira-admins-ext | TODO | 2025-01-06 |  | Slack: LINK | 1. Go to JIRA > Create (blue button at top) 2. Look for BranchFoundIn 3. Type in Release- to bring up the list of available options a. If the version for this checklist is present, you are done. If not, go to step 4. 4. Spin up a post in #fn-jira-admins-ext using the suggested text in Column H | Hello JIRA Admins, Could you please add `Release-CHECKLIST_VERSION` as an option in the BranchFoundIn dropdown? Thanks in advance! |  | Maybe?
RM | Schedule Google Calendar Meeting: Stability Sync | TODO | 2025-01-06 |  | Calendar Event: LINK | 1. Go to the Google Calendar 2. Search for Stability Sync and go to the previous release's event 3. Duplicate the card and update the following: a. Event Title (Set to correct version) b. Date (set to 10am the morning of release date) c. Zoom Meeting (ensure meeting invite is working, if not, remove and add a new one) 4. If not already on the previous event when duping. ensure the following people/groups are added: a. Jay Chaney & Tyler Buczek b. Elizabeth Bunner (optional) c. fn-tech-production d. Release-Team e. ReleaseQA |  |  | Yes
RM | Schedule Google Calendar Meeting: Post Mortem | TODO | 2025-01-06 |  | Calendar Event: LINK Post Mortem Sheet: LINK | 1. Go to the Google Calendar 2. Search for Post Mortem and go to the previous release's event 3. Duplicate the card and update the following: a. Event Title (Set to correct version) b. Date (set to the Thursday following the release date) c. Zoom Meeting (We will use the shared Release Zoom (Lobby or Alt Room) d. Post Mortem Sheet Link (set to applicable tab - If not created, make the tab) 4. If not already on the previous event when duping, ensure the following groups are added: a. fn-release b. Release-Team (embedded in the 4a. group) 5. Set up a reminder in the fn-release-team slack channel using the suggested text in Column H | /remind #fn-release-team @here "Just a friendly reminder to review & add items to the CHECKLIST_VERSION Post Mortem Sheet prior to our meeting on Thursday." MM DD at 10 am ET |  | Yes
RM | Schedule Calendar Events: - Hard Lock - Pencils Down | TODO | 2025-01-06 |  |  | 1. Go to the Google Calendar 2. Search for Hard Lock and go to the previous release's event (should be at 8PM ET) 3. Duplicate the card and update the following: a. Event Title (Set to correct version) 4. Repeat steps 2-3 for the Pencils Down calendar event. |  |  | Yes
RM | Determine Deploy Time with the below teams: - Live Ops - Competitive - Publishing/Marketing | TODO | 2025-01-06 |  | Deploy Types and Times: Season Releases: 2am Dot Releases: 4am Emergency Patches: 8am Slack: LINK | 1. Spin up a post in the fn-release-xx.xx-ext channel using the suggested text in Column H/I | Deploy Time Alignment for CHECKLIST_VERSION :thread: | @release-team, @releaseqa, @competitive-ops, @epic-liveops, @laura.stone, @paris.nourmohammadi Hello everyone, Just wanted to get everyone together to align on the deploy time for CHECKLIST_VERSION. Any objections to going with our standard DEPLOY_TYPE time of `COL_F`? | Yes
RM | Enable the following Scheduled Horde Jobs 1. Nightly builds 2. Nightly Data Rebuild 3. World Partition Build WIKI | TODO | 2025-01-06 |  | Commit CL: 12345 | 1. Go to here in P4: //Fortnite/Main/FortniteGame/Build/Streams 2. Find the CHECKLIST_VERSION streams.json file for the branch you are editing 3. Check out and open file 4. Create a shelf using the suggested P4 Description in Column H --> 4. Find Nightly Build 5. In the ""schedule"" section > change ""enabled"": false to ""enabled"": true 6. Repeat steps 4-5 for: a. Nightly Data Rebuild b. World Partition Build 7. Save and commit in P4 8. Send courtesy message in Slack to #buildfarm-support-ext using the suggested P4 Description in Column I --> | Enabling the below jobs for Release-CHECKLIST_VERSION: - Nightly Build - Nightly Data Rebuild - World Partition Build #jira none #rnx #fyi stan.hormell, swarm-ue-build-reviews | Hi Build Farm, just wanted to inform you that we enabled the below jobs for CHECKLIST_VERSION at CL XXXXX. - Nightly Builds - Nightly Data Rebuild - World Partition Build That's all!
RM | If Season Launch and No Event: Create Season Run of Show sheet for orchestrating the teams | TODO | 2025-01-06 |  |  | 1. Create the Run of Show using the TEMPLATE 2. Rename the sheet to the correct name & set the deploy date in cell H1 3. Create Calendar Event for the Run Of Show in the Fortnite Release Team Calendar and put that in cell F2 of the RoS sheet 4. Add a Zoom Link to the Calendar Event and put that in cell D2 of the RoS sheet 5. Create and set the Calendar Event for the War Room to all day so it pins to the top of the calendar day 6. Bookmark the RoS, War Room & Calendar Link in the Release-XX.00 slack channel 7. Reach out to publishing to ask them to put in their RoS into Cell D1 a. Currently Paris Nourmohammadi Laura Stone |  |  | Yes
By Hard Lock |  | IN PROGRESS
RM | Release Content Legal Approval has Started | TODO | 2025-01-27 |  | Slack: LINK | 1. Navigate to the #fn-legal-publishing-approvals-ext slack channel 2. Look for thread containing Ready For Review a. Currently by Adam Baxter & Ben Massoglia (Ben to take over in the future) 3. If thread is not present, send a DM to Adam Baxter & Steve Allison asking when that will happen |  |  |  | MD
RM | Make sure Disallow List has Started (Data Encryption) | TODO | 2025-01-27 |  | Slack: LINK | 1. Navigate to the #fn-encryptedassets-ext slack channel 2. Look for the thread containing Datamine Results a. Currently by Adam Baxter & Ben Massoglia (Ben to take over in the future) 3. If thread is not present, send a DM to Adam Baxter & Steve Allison asking when that will happen 4. Reminder to confirm that All FN, FNE (Creative+UEFN), JUNO, DelMar, Sparks terms are being checked |  |  |  | MD
SUB | Ensure Sony publishing tools are up to date | TODO | 2025-01-27 |  | Slack: LINK | PS4: https://ps4.siedev.net/docs/master_submission PS5: https://p.siedev.net/docs/master_submission To find Sony Publishing Version: Look at the build logs from the "PS4 Client Full Package" step lists the version of the tools in the output Ping Luke Thatcher and/or Ben Woodhouse if you have issues |  |  |  | MD
SUB | Confirm SwitchEngine.ini updated with new Version and Release | TODO | 2025-01-27 | [6 empty] | MD
SUB | Make sure PS4 SIEE packages are being built | TODO | 2025-01-27 | [6 empty] | MD
RM | If Season Launch Reminder messaging for seasonal Hotfix clean up | TODO | 2025-01-27 |  | Slack: LINK | 1. Spin up a post in the fn-release-xx.xx-ext channel using the suggested text in Column H/I | Seasonal Hotfix Cleanup reminder for Release-CHECKLIST_VERSION Please respond by the end of day, {Day}, {Date} 5:00PM EST, if you have hotfix syntax that needs to persist and cannot be baked in. If not, your syntax may get wiped after the clean up. (Timing in the above messaging should align with first whiteglove?) | It's time to cleanup the hotfix files with a new season release. This is to maintain a clean and minimal list of changes in the files. Teams should be proactively baking in their changes release over release and requesting clean ups in the game config sheet. Unfortunately, this does not always happen, and leaves a lot of stale changes and bloat that is no longer needed. If there are any specific changes that must be kept, please let us know so that we can flag as DO NOT PURGE in the hotfix files ;(DNP). Thanks in advance to all that do regularly bake in and request removals. This is very much appreciated. | Yes
RM | Review and Raise awareness of "escaped crashes" | TODO | 2025-01-28 |  | Slack: LINK | 1. Look for the following table on the release dashboard "Escaped Crashes / Asserts / Ensures" example 2. Spin up a thread in the #fn-release-XX.XX-ext slack channel using the suggested text to the right --> a. Tag in the Tech component owner (currently Chris Tran / Jay Chaney) and the seasonal prod owner (row 1) 3. Add the following JQL for each a. Needs Triage and status = "Needs Triage" b. Affects Version and affectedVersion <= LIVE_VERSION c. Backlogged and status = "backlogged" | CHECKLIST_VERSION Escaped Crashes Review :thread: | Hi @PROD_OWNER & @Chris Tran If y'all have time in the next couple days, RM would appreciate your review of various Jiras for crashes being tracked for CHECKLIST_VERSION. These are all issues that are in various states of "Unresolved", some of which are not triaged in some capacity (Priority, Fix Version, Assignee). The goal of this ask is to make sure these crashes get visibility and review now, instead of potentially in a post-release shit happens. Thanks! JIRA FILTER *of the N issues in the above filter:..* X are in "Needs Triage" X have "Affects Versions" from LIVE_VERSION and older X are backlogged | Yes | MD
RM | Begin "OK TO SHIP WITH" Approval For All Remaining Build Errors/Warnings - Start on the 1st Nightly build after HardLock DUE BY CERT SUBMISSION | TODO | 2025-01-28 |  | Tracking Sheet Here | 1.Go to the Tracking Sheet and dupe the template and rename to this checklists version 2. Go to the Builds tab of the Horde Branch for the checklist's version 2. Go to latest completed Nightly and SSB builds. 3. Go through any Red/Yellow badges in the Clients, Servers, UEFN columns and enter information into the tracker sheet. a. You can ignore the Test Content Worker Docker Image Win64/Linux badges in the UEFN section 4. Go through any Red/Yellow badges in the Nightly Data Rebuild & World Partition Build builds and enter information into the tracker sheet. 5. Once you have entered all Errors/Warnings into the tracker sheet, spin up build health threads (as normal for BH) in the #fn-build-health-ext channel and escalate to the appropriate people for signoff - template in 1st tab of sheet a. Ensure all issues have a JIRA for tracking so these can be addressed at some point 6. Spin up a general World Partition Build thread and tag Sébastien Lussier for review (example here) |  |  |  | MD
RM | Send Release Strategy email Confluence Wiki (need to merge all the things) Wiki on creating the meeting calendar event Template (if not copied from a previous email) | TODO | 2025-01-28 |  |  | 1. Search your email for "Release Strategy" and go to a previous release's email 2. Copy a previous email's TO:. Subject and Body (either a .00 if this release is a .00 or a .10/.20.30 if not) and update the following a. Version & Expected Release Timing (also confirm if downtime from 4am-5am is applicable) b. Cutoff for Deploy Strategy and Hotfix Confirm Items Date (Should be friday noon if tuesday deploy) c. Link to calendar: Point to updated calendar event 3. Send Email | TO: FN-Release-Updates <fn-release-updates@epicgames.com> Release Dates: FN Release Calendar |  | Yes
RM | Redundancy: Make sure zoom links are still valid for all meetings related to this release | TODO | 2025-01-28 |  |  | 1. Search Google Calendar for the release version and check the below meetings: - Stability Sync - Post Mortem 2. Click the current zoom link to try to enter as normal. If it works, you are good. 3. If you get an error, kill the current zoom link and make a new one
SUB | Review the Cert issues filter to make sure nothing egregious still needs to be fixed | TODO | 2025-01-28 |  | Double check to ensure cert impacting issues have been confirmed fixed on the current candidate | Dashboard - https://jira.it.epicgames.com/secure/Dashboard.jspa?selectPageId=25898
| AFTER 8PM ET HARDLOCK |  |  |  | AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK
RM | Add Temporary Allowlisters to lockdown file | TODO | 2025-01-28 |  | Check Release's Hard Lock Calendar invite for additional instructions Commit CL: 12345 Slack: LINK | 1. Go to Allowlister Sheet and go to the appropriate release tab. 2. Copy names from Cell F2 at step 7. 3. Go to this P4 file path //Fortnite/Main/FortniteGame/Build/p4lockdown/lockdown_config.ini 4. Check out the file and Open. For the description, use the suggested text in Column H --> 5. In the file, search for [ReleaseA-Lockdown-Hardcore] and [ReleaseB-Lockdown-Hardcore] 6. Determine which list is setup for the upcoming release. If neither are, replace the older release with the one for this checklist (See Step 2) 7. Paste the allowlisted names from step 2 after Stan.Hormell (ensure comma placement is retained). 8. Save and commit. 9. Post a message in the release channel using the suggested text in column I | P4 Description: Adding Temporary Allow Listers & HardLocking CHECKLIST_VERSION #jira none #rnx | Slack Release-XXXX-ext Channel: :announcement-1: CHECKLIST_VERSION is now Hardlocked and temporary allowlisted permissions have been set :lock: -- Please submit all changes through the Submit Tool using the standard integration process.
RM | Update MOTD in UGS | TODO | 2025-01-28 |  | Commit CL: 12345 | 1. Go to the following file in P4 while in the same workspace //Fortnite/Release-CHECKLIST_VERSION/FortniteGame/Build/UnrealGameSync.ini 2. Get latest > Checkout and Open 3. Create a shelf using the suggested P4 Description in Column H --> 4. Scroll to the bottom of file 5. Copy text from column i and overwrite the "Message=.... text currently in the file" & StatusPanelColor 6. Add the dates from FN Release Calendar (or copy from current banner message) 7. Edit and check the link to the dashboard to ensure its working 8. Save and commit CL using the submit tool Resolving the robo conflict: - remove the conflicting yellow and green lines for the text your just changed. Keep the blue text which should be exactly what you just updated in the checklist branch | P4 Description: Updated MOTD in UGS for CHECKLIST_VERSION Hard Lock #jira none #rnx | Overwrite current message with below (update the red text) Message=:alert: THIS BRANCH IS NOW HARD LOCKED. Refer to [Branching, Lockdown, Integrations](https://wiki.it.epicgames.net/pages/viewpage.action?pageId=42600502) to submit changes ¦ Pencils Down = MM/DD 8PM EST ¦ CertSub = MM/DD 9am ET ¦ Release = MM/DD 3am ET [Jira Dashboard](https://epic.gm/XX-XX) StatusPanelColor=#e20000
RM | Set NetCL Version Number | TODO | 2025-01-28 |  | Commit CL: 12345 | 1. Go to the following file in P4 while in the same workspace //Fortnite/Release-CHECKLIST_VERSION/Engine/Source/Runtime/Core/Public/Misc/NetworkVersion.h 2. Get latest > Checkout and Open 3. Create a shelf using the suggested P4 Description in Column H --> 4. In the file, search for ENGINE NET VERSION (should be line 12 ish) 5. If it is currently 0, set it to the CL of the Last Successful SSB/Nightly Build in Horde a. If it is not 0, verify the set CL is the CL of the Last Successful SSB/Nightly Build in Horde 6. Save and commit CL using the submit tool (must be deadended) 7. Verify via Track Change that it did not merge - https://robomerge.epicgames.net/trackchange/####### | Setting NetCL version to CL XXXXXX #jira none #okforgithub public #rnx #robomerge -Release-NEXT_VERSION
RM | Update the metastream UE robomerge connection to the next FN release | TODO | 2025-01-28 |  | Slack: LINK | 1. Go to #epic-release-managers-ext and post using the suggested text in Column H | @Marc Audy @release-team CHECKLIST_VERSION has been hardlocked. Please update the metastream UE robomerge connection to the next FN release if that applies in this case.
RM | Send update to Escaped Crashes Thread | TODO | 2025-02-05 |  |  | Rerun the steps from Row 39 to escalate any new or outstanding issues |  |  | Yes | MD
RM | Redundancy: Row 47 Verify NetCL was set correctly and did not merge | TODO | 2025-01-30 |  | Commit CL: 12345 | 1. Go to the following file in P4 while in the same workspace //Fortnite/Release-CHECKLIST_VERSION/Engine/Source/Runtime/Core/Public/Misc/NetworkVersion.h 2. Get latest > Checkout and Open 3. Create a shelf using the suggested P4 Description in Column H --> 4. In the file, search for ENGINE NET VERSION (should be line 12 ish) 5. If it is currently 0, set it to the CL of the Last Successful SSB/Nightly Build in Horde a. If it is not 0, verify the set CL is the CL of the Last Successful SSB/Nightly Build in Horde 6. Save and commit CL using the submit tool (must be deadended) 7. Verify via Track Change that it did not merge - https://robomerge.epicgames.net/trackchange/#######
By Pencils Down |  | IN PROGRESS
RM | Lock the DAD CL | TODO | 2025-02-07 |  | Slack: LINK | 1. Go to the Data Asset Directory and go to the version for this checklist 2. Click on the newest (top of the list) CL's Blue Lock button which will turn it red and unlocked (yes it seems backwards) as well as the CL turning green 3. Once complete, spin up a post in #fn-release-CHECKLIST_VERSION-ext using the suggested text in Column H | :announcement-1: RM has locked the DAD for CHECKLIST_VERSION to CL XXXXX :lock:
RM | Request Final DAD revision for pre whiteglove (web DAD links for creative, browser, discover, and the analytics-stuff link) | TODO | 2025-02-07 |  | Slack: LINK | 1. Go to the #fn-release-CHECKLIST_VERSION-ext and spin up a post using the suggest text in Columns H/I a. Check the FN Release Schedule or Fortnite Release Calendar for the cert date 2. After links have been provided, add them to the Game Config Sheet, for all links provided | :dad: Final DAD Revisions:dad: | Hello there @Greg Garnhart @Kareem Al-Attar @Hana Zubovic Checking in on final revision delivery. We are starting pre-cert checks and it would be amazing to test against final DAD revisions if they are available. Additionally any required Analytics Stuff links would be great as well. We go to cert on INSERT_DAY :) @releaseqa for viz | Yes
RM | Set up Modes & Tags in FleetMan for Release QA Whiteglove WIKI | TODO | 2025-02-07 |  | Slack: LINK | 1. Go to the Fleetman Release page and select the version for this checklist 2. If you see a blue banner stating No Tags Defined, continue. 3. Select the Import Button (right of Mode Configurations) > Select the previous version from the dropdown 4. Select All (above ID column) to check all boxes 5. Select the Import Button (right of Tags) > Select the previous version from the dropdown 6. Select the Confirm checkbox > Import 7. Once complete, send a message to fn-release-team using the suggested text in Column H | :announcement-1: Just a heads up, we have set up Modes & Tags in FleetMan for CHECKLIST_VERSION in preparation of WhiteGloves LINK
| AFTER 8PM ET PENCILS DOWN |  |  |  | AFTER 8PM ET PENCILS DOWN | AFTER 8PM ET PENCILS DOWN | AFTER 8PM ET PENCILS DOWN | AFTER 8PM ET PENCILS DOWN
RM | Remove Temporary Allow Listed - 8PM ET WIKI | TODO | 2025-02-07 |  | Commit CL: 12345 Slack: LINK | 1. Go to this P4 file path //Fortnite/Main/FortniteGame/Build/p4lockdown/lockdown_config.ini 2. Check out the file and Open. For the description, use the suggested text in Column H --> 3. In the file, search for [ReleaseA-Lockdown-Hardcore] and [ReleaseB-Lockdown-Hardcore] 4. Find the list that corresponds to this release's version 5. Delete the names that come after Stan.Hormell (ensure there is no comma after Stans name). 6. Navigate to the [Release-Archive-Hardcore] section and remove the version corresponding to this checklist 7. Save and commit. | P4 Description: 1. Removing Temporary Allow Listers for CHECKLIST_VERSION Pencils Down 2. Removing CHECKLIST_VERSION from [Release-Archive-Hardcore] #jira none #rnx | Slack Release-XXXX-ext Channel: :announcement-1: CHECKLIST_VERSION is now Pencils Down and temporary allowlisted permissions have been revoked:pencilsdown: -- Everyone must now submit any changes through the Submit Tool using the standard integration process.
RM | Enable Robomerge Gate - 8PM ET This will create a post in the integrations channel if someone attempts to robomerge a change up to the Pencils Down branch | TODO | 2025-02-07 |  | Commit CL: 12345 | 1. Go to this P4 file path //GamePlugins/Main/Programs/RoboMerge/data/fortnite.branchmap.json 2. Check out the file and Open. For the description, use the suggested text in Column H --> 3. In the file, goto the section at the bottom for "edges" 4. Find the "from" and "to" line that corresponds to this release's version 5. Update "from" to the future branch, update "to" to the current branch 6. Use the Robomerge preview feature to ensure that there are no parsing issues (right click the pending CL in p4v and choose Robomerge Preview Graph from UE Toolbox) eg. https://robomerge.epicgames.net/preview/33192043 7. Save and commit. [example] | P4 Description: Adding XX.XX --> XX.XX Robomerge Gate alert #jira none #rnx #fyi stan.hormell, swarm-ue-build-reviews | P4 Description (example): Adding 29.40 --> 29.30 Robomerge Gate alert #jira none #rnx #fyi stan.hormell, swarm-ue-build-reviews
By Cert Sub |  | IN PROGRESS
SUB | Request Patches: Email Xbox Account Manager | TODO | 2025-02-09 |  |  | "TO: Brian Weiss <brian.weiss@microsoft.com>, Epic Games WAM <epicwam@microsoft.com> CC: Release-team"
SUB | Verify Xbox Submission Validator logs do not have any warnings or errors | TODO | 2025-02-09 |  |  | These should show up in Horde but good to double confirm just in case
SUB | Send Akamai early estimate of patch sizes | TODO | 2025-02-09
SUB | Notify Nvidia of the upcoming patch date and time via email | TODO | 2025-02-09 |  |  | Email: GFN-DevOps-External@nvidia.com, ssolovyev@nvidia.com fliljegren@nvidia.com Format: MM/DD/YYYY, TIME_UTC_24H Example - 08/27/2018, 08:00 UTC
SUB | Notify AWS of the upcoming patch date, time, and sizes via email | TODO | 2025-02-09 |  |  | epicgames-events@amazon.com
SUB | Notify Fastly of the upcoming patch date, time, and patch sizes | TODO | 2025-02-09 |  |  | #fastly-epicgames
SUB | Notify Cloudflare channel of the upcoming patch date, time, and patch sizes | TODO | 2025-02-09 |  |  | #vndr-cloudflare-ext #vndr-aws-egs-cloudfront-ext
SUB | Notify ISP email group alias of the upcoming patch date, time and patch sizes | TODO | 2025-02-09 |  |  | ext-fn-release-notify@epicgames.com
SUB | Update DevNet Thread with Incoming Patch Information | TODO | 2025-02-09 |  |  | PS4 and PS5
SUB | Request Patches: Create New Release for Nintendo | TODO | 2025-02-09
SUB | Request Patches: Fill out and submit new OMAS for Nintendo | TODO | 2025-02-09
SUB | Request Patches: SIEA | TODO | 2025-02-09
SUB | Request Patches: SIEE | TODO | 2025-02-09
SUB | Request Patches: PS5 Shared | TODO | 2025-02-09
RM | Verify Android version number has been updated in perforce | TODO | 2025-02-11 |  | Commit CL: 12345 | 1. Open P4 and navigate to the below file //Fortnite/Release-XXXX/FortniteGame/Config/DefaultEngine.ini 2. Search file for the string: VersionDisplayName a. Should live under the [/Script/AndroidRuntimeSettings.AndroidRuntimeSettings] header 3. Verify this is set to the release version in the format XX.YY.Z |  |  |  | MD
RM | Verify Version Locking AND that the Net Version locked to is different than the currently live branch | TODO | 2025-02-11 |  | Last Release (XX.YY): 12345 This Release (XX.YY): 12345 Reviewed by: PERSON | 1. Open P4 and navigate to the below file in the LAST release //Fortnite/release-XXXX/Engine/Source/Runtime/Core/Public/Misc/NetworkVersion.h 2. Search file for the string: ENGINE_NET_VERSION 3. Note the listed CL in Column F 4. Repeat steps 1-2 for THIS release a. If the ENGINE_NET_VERSION is not set to 0, verify the set CL is higher than the previous release's CL b. If the ENGINE_NET_VERSION is set to 0, set it to a CL that is higher than the previous release's CL i. Can use the last successful Nightly Build CL & make sure to deadend your commit using the suggested text in Column H 5. Once submitted, have someone else on the team review your commit. | P4 Changelist Description: ---------------------------------------------------------------------- Setting NetCL after CHECKLIST_VERSION Hardlock #jira none #okforgithub public #rnx #robomerge -NEXT_VERSION #robomerge FNONLY |  |  | MD
SUB | Get engineer sign off of patch Sizes | TODO | 2025-02-11 |  |  | Tag fn-tech-patchreview in #fn-release-patchsizes. Try to send first prelim sizes soon after hard-lock |  | Hello @fn-tech-patchreview Can you please review and sign off on the above Patch Sizes? |  | MD
RM | Confirm the final loc commit job successfully makes it into P4 | TODO | 2025-02-11 |  | Slack: LINK | 1. Navigate to the #fn-release-loc slack channel 2. Look for the thread around Final Loc Import a. FN is Kevin Shen Raúl Arol, UEFN is Asli Sokmen 3. If not already stated when its coming in (or past that date), poke the thread using the suggested text in Column I | Hi @UEFN_LOC_POC @FN_LOC_POC just want to confirm the final loc commit job is on track for both FN / UEFN loc. Is that targeting for tonight? |  |  | MD
RM | Release Content Legal Approval (FN and UEFN content) Cosmetic Content Assets Sheet | TODO | 2025-02-11 |  | Slack: LINK | 1. Navigate to the #fn-legal-publishing-approvals-ext slack channel 2. Look for thread containing Ready For Review a. Currently by Adam Baxter & Ben Massoglia (Ben to take over in the future) 3. If thread is not present, send a DM to Adam Baxter & Steve Allison asking when that will happen 4. Ensure final signoff is given |  |  |  | MD
RM | Make sure Disallow List was reviewed (test videos, out of date replay files, etc) (FN, FNE (Creative+UEFN), JUNO, DelMar, Sparks terms) | TODO | 2025-02-11 |  | Slack: LINK | 1. Navigate to the #fn-encryptedassets-ext slack channel 2. Look for the thread containing Datamine Results a. Currently by Adam Baxter & Ben Massoglia (Ben to take over in the future) 3. If thread is not present, send a DM to Adam Baxter & Steve Allison asking when that will happen 4. Reminder to confirm that All FN, FNE (Creative+UEFN), JUNO, DelMar, Sparks terms are being checked |  |  |  | MD
RM | Ensure code only builds are working properly including verification it can be successfully promoted | TODO | 2025-02-11 |  | Code Only Build: LINK Android Promotion to ReleaseStaging: LINK All Platform Promotion Job: LINK Link(s) to Error/Warning Thread(s): - Link 1 - Link 2 | 1. Navigate to this release's Builds tab in horde 2. Copy the CL of the last passing build 3. New Job > Minimal Code Only Build 4. Set the Base Change to the last passing build you copied 5. Set the Change CL to a green incremental's CL 6. Start Job a. escalate errors/warnings to #fn-build-health-ext or #buildfarm-support-ext (if applicable) for fixes 7. Once complete, copy the ++CL and navigate to the promotions tab of main horde and hit New Job 8. First we will promote Android. Set the following: a. Template Promotion Job (Client) b. Build Version to the ++CL c. To App Name to FortniteReleaseStage (2nd from bottom in list) d. Promote Platforms to Android - EGS App e. Uncheck Keep Build Alive 9. Start Job a. escalate errors/warnings to #fn-build-health-ext or #buildfarm-support-ext (if applicable) for fixes 10. Once complete, reach out to RQA or the Apps Team Reps on RM to see which backend to promote to for this test 11. Once you have an approved backend, rerun steps 7-9 a. Template Promotion Job (Client) b. Build Version to the ++CL c. To App Name to the approved backend d. Promote Platforms to all the platforms built in the Minimal Code Only e. Uncheck Keep Build Alive 12. Start Job a. escalate errors/warnings to #fn-build-health-ext or #buildfarm-support-ext (if applicable) for fixes 13. If all goes well, likely revert the backend back to its previous state (follow up with whoever gave it to you) | Need to see examples to create escalation |  |  | MD
RM | FortniteContentBuilds: Verify platforms below have been updated correctly: - PC/Windows - Android - PS4 - PS5 - Switch - XB1 - XSX Old Wiki | TODO | 2025-02-12 |  | If the admin portal looks weird, confirm the .json file is showing the correct CLs We can safely ignore the following: - iOS | 1. Navigate to the FortniteContentBuilds section of the Admin Portal 2. Under the Promotion Labels section, Look for the Live label (should be first) and open the dropdown 3. Open another window and go to the Release Log to see our live CLs 4. Copy the Live CL for PC/Windows and search for it in the admin portal's Live Label to verify it is correctly reflected a. Repeat this step for Android, PS4, PS5, Switch, XB1, XSX (Ignore iOS, XboxOne & XboxOneGDK) 5. Repeat steps 2-4a. This time for the Rollback label. a. Type Rollback into the filter, then hit the Label Name column header twice to find it. 6. The CL you are looking for is the CL immediately previous to the live CL. Look in Current & Previous Releases section of the Release Log 7. As a secondary check, you can navigate to the below file on the network drive (easiest to use a VM to work computer) P:\Builds\Automation\Fortnite\Config\ConsoleLiveLabels.json 8. Do a find and search of the live and immediately previous to live CLs to ensure they are present a. Can open the file in a text editor > Ctrl+F > Insert CL. It should return 5 hits (PS4, PS5, Switch, XB1, XSX) |  |  |  | MD
RM | Get Folder Comparison sign off from Anticheat for PC (Anticheat PC Diff for UEFN and FN) | TODO | 2025-02-12 |  |  | 1. Check email for Folder Comparison 2. Find the email associated with the latest approved PC candidate (ex. ++Fortnite+Release-26.30-CL-28509302) 3. Ensure there are links to the diff (current live CL vs candidate) for the Game Client & UEFN 4. Ensure we get sign off (Ben Temple, Joe Barrett or Lukasz currently) |  |  |  | MD
SUB | Make sure PS5 titleconfiguration.json/fortbuild.xml files are updated | TODO | 2025-02-12
SUB | Make sure PS4 titleconfiguration.json/fortbuild.xml files are updated | TODO | 2025-02-12
SUB | Make sure SwitchEngine version has been incremented. | TODO | 2025-02-12
SUB | Verify that LatestPatch folder contains last released patches | TODO | 2025-02-12 |  |  | PS4/PS5/XB1/XSX/Switch
SUB | Verify the file system captures for Nintendo have been gathered by QA | TODO | 2025-02-12 |  |  | Details in this document https://docs.google.com/document/d/1krb18jjtEBn10duEBgaiklnLnN55RE5raKLL4acSX3c/edit#heading=h.xd3o88dyuuik
RM | Send Last Call bump for callouts in the Release Strategy Email. WIKI | TODO | 2025-02-12 |  |  | 1. Go to your email and search for the CHECKLIST_VERSION Release Strategy for this version 2. Send a follow up email using the suggested text in Column H a. Deadline for a Tuesday deploy is noon on the Friday b. Deadline for a Friday deploy is noon on the Tuesday | Bumping the thread here for any last minute CHECKLIST_VERSION Call Outs (Copy the below in again from the initial email) From: Deadline for both Deploy Strategy and Hotfix Config..... Till: If you are the owner of a Deploy or Hotfix item you are strongly encouraged to attend |  | Yes
RM | Determine Ship List (using the below Airtable) and pin it in Slack New Hotness: Deliverables Roadmap Build View | TODO | 2025-02-12 |  | Slack: LINK | 1. Go to the Deliverables Roadmap 2. Compile a list of all changes going into the release using the format in Column H 3. Post to #fn-release-CHECKLIST_VERSION-ext channel and Pin the message. Example Here | CHECKLIST_VERSION Ship List :ship: - Items/Gameplay: XXX - REGS/Quests: XXX - Creative: XXX |  | Yes
RM | Identify team for release day and update Release Request | TODO | 2025-02-12 |  | Slack Links: LiveOps ReleaseQA Community | 1. Message the below groups using the suggested text in Column H. a. LiveOps b. ReleaseQA c. Community d. Release Management - Row 24 | Hey INSERT_GROUP Team: Who is your representative for the upcoming CHECKLIST_VERSION release? I'll make sure to get them added to our REAL-XXX ticket for tracking. Thanks! | Release Managers: Hey PERSON_LISTED_IN_SHEET: You all good to own the upcoming CHECKLIST_VERSION release? Looks like you are on the FN Release Schedule for it. If so, I'll make sure to get you added to our REAL-XXX ticket for tracking. Thanks! | Yes
RM | Whiteglove has been completed on INITIAL release candidate (aka crit checks) and issues called out have been threaded/escalated for triage Note: We will never be releasing this build. There will always be another CL for our final candidate (line 137) | TODO | 2025-02-12 |  | Slack: LINK_TO_WG | 1. Go to #fn-release-CHECKLIST_VERSION-ext and search for "beginning whiteglove of:" a. This should bring up all instances of whitegloves bring run 2. Ensure RQA completes the Client WG the day before cert submission (ideally 2 days before) a. You can track progress in TestRail (STC) if you have access 3. Ensure issues called out from the WG are appropriately threaded (outside the WG thread) and triaged in the #fn-release-CHECKLIST_VERSION-ext channel
RM | Redundancy: Row 68 Request Final DAD Links for WG testing: They should provide the following: * Weblinks: * Browse * Library * DAD V2 (used to push live to Discover) * Browse * Library * Discover * Web (fornite . com) | TODO | 2025-02-12 |  | Final Dad CL: 12345 | 1. Continue follow up in the original thread from row 68 using the suggested text in Columns H/I a. Continue once those are provided to us 2. Go to this link, replace the checklist's version and refresh the page. 3. Reconfirm the CL is green and has a red UNLOCK icon. 4. Verify locked CL matches the CL in the 3 links provided in step 1a. | Checking in on final revision delivery. Anything to update since our last request above? We are starting pre-cert checks INSERT_DAY and want to ensure QA is running their WhiteGlove with the accurate info. We are still targeting to go to cert on INSERT_DAY :) |  | Maybe?
RM | Redundancy: Row 47 Ensure Final Shop is in for WG testing | TODO | 2025-02-12 |  | Final Shop CL: 12345 | 1. Send message in the #fn-release-CHECKLIST_VERSION-ext channel using the suggested text in Columns H/I | :shopping_bags: Final Shop Changes::shopping_bags: | Hello there @juan romero nick.owens@epicgames.com Steve Allison @amanda.perry @Matthew.Geisen @alison.McKenzie Just double checking in on final shop delivery. Anything else coming in hot? I see the last commited change on the INSERT_JIRA_FROM_ROW47 is FIX_CL_FROM_JIRA We are starting pre-cert checks and it would be amazing to test against final Shop revisions if they are available. We go to cert on INSERT_DAY :) | Yes
RM | Make sure all Game Config owners are added to the Strategy Meeting for this release | TODO | 2025-02-13 |  |  | 1. Go to Game Config Sheet and add everyone in Column E to the associated Strategy Meeting in the Google Calendar 2. If Column E lists a group, check the cell history. If its an Engineer add them and the component producer. 3. Send calendar invites to newly added people. |  |  | Maybe?
RM | Disable Standard Scheduled Builds for this branch Enable Standard Scheduled Builds for the next branch WIKI | TODO | 2025-02-13 |  | Commit CL: 12345 Slack: LINK | 1. Go to here in P4: //Fortnite/Main/FortniteGame/Build/Streams/ 2. Find the CHECKLIST_VERSION streams.json for the branch(s) you are editing (Next & Next+1) 3. Check out and open file 4. Create a shelf using the suggested P4 Description in Column H --> 5. Find Scheduled Standard Build with Build Health 6 In the ""schedule"" section, change ""enabled"": true to ""enabled"": false 7. Save and commit in P4 8. Send courtesy message in Slack to #buildfarm-support-ext using the suggested P4 Description in Column I --> | Disabling Scheduled Standard Build job for Release-CHECKLIST_VERSION Enabling Scheduled Standard Build job for Release-NEXT_VERSION #jira none #rnx #fyi stan.hormell, swarm-ue-build-reviews | Hi Build Farm, just wanted to inform you that we disabled the Scheduled Standard Build job for CHECKLIST_VERSION and enabled it for NEXT_VERSION at CL XXXXX. That's all!
RM | Post the build list to the release channel when going to cert | TODO | 2025-02-13 |  | Slack: LINK | 1. Once cert candidates are locked in, Copy the info from the REAL-XXXX ticket and post / pin in the #fn-release-xx-xx-ext channel | Hi All, As we approach cert tomorrow, here are the current submission candidates for our upcoming release Post_Info_From_Real_Ticket | Source of Truth Should Be The Submission Owner's Pinned Post in the release channel ex. Release 29.00 Cert Sub Updates | Maybe?
Release Candidate Build (Locked in) |  | IN PROGRESS
RM | Ensure that the Branch Tab within the Game Config Doc has been locked at Noon | TODO | 2025-02-14 |  | Slack: LINK | 1. Spin up a thread in the #fn-release-XX.XX-ext slack channel using the suggested text in Column I | :airhorn-9469: Hello team! Just calling out that the release team has locked the CHECKLIST_VERSION tab of Game Config today. Any further edits to this tab should go through the `Game Config Update` Service Desk Request from this point forward! :lock: Thanks! |  | Maybe?
SUB | Add build info to all cert environments | TODO | 2025-02-19 |  |  | ConsoleCertA/ConsoleCertB/DevPlaytestQ
SUB | Confirm all cert environments have the correct Server, MCP, and Hotfix config | TODO | 2025-02-19 |  |  | ConsoleCertA/ConsoleCertB/DevPlaytestQ
SUB | Spin up / verify that cert backends are online | TODO | 2025-02-19 |  |  | ConsoleCertA/ConsoleCertB/DevPlaytestQ
SUB | Update Release Log and Release Request | TODO | 2025-02-19
SUB | Make local copies to your station for uploads for XB1/XSX/PS4 (SIEA/SIEE)/PS5/Switch/Luna (through EGS)/Android | TODO | 2025-02-19
SUB | CertSub Candidate: Patch Sizes | TODO | 2025-02-19
SUB | Nintendo: Request Waivers | TODO | 2025-02-19
SUB | Submit Switch build in NDP | TODO | 2025-02-19
SUB | Upload SIEA build | TODO | 2025-02-19
SUB | Upload SIEE build | TODO | 2025-02-19
SUB | Upload PS5 shared binary | TODO | 2025-02-19
SUB | Upload the Luna Client and send it to certification | TODO | 2025-02-19
SUB | Upload the Digital Turbine Candidate | N/A | 2025-02-19 |  | DT is currently on hiatus.
SUB | Upload Xbox builds and send them to certification | TODO | 2025-02-19
SUB | Publish Xbox candidate builds to Selective Flight | TODO | 2025-02-19
SUB | Selective Sign-Off: Xbox One/XSX | TODO | 2025-02-19
SUB | Update MDT: SIEA | TODO | 2025-02-19
SUB | Update MDT: SIEE | TODO | 2025-02-19
SUB | Complete and save final MDT (PS5) | TODO | 2025-02-19
SUB | Rapid patch Submission: SIEA | TODO | 2025-02-19
SUB | Rapid patch Submission: SIEE | TODO | 2025-02-19
SUB | Rapid patch Submission: PS5 | TODO | 2025-02-19
RM | Build Protection for current Final Candidate CLs so they don't delete before release WIKI | TODO | 2025-02-19 |  | CL(s) Protected: - 12345 | 1. Go to the Build Protection Sheet, duplicate the Template and rename the copy to the CHECKLIST_VERSION 2. Populate the following fields for each unique CL we intend of releasing a. Version/Team = CHECKLIST_VERSION. Only use a team name if another team asks to protect a certain build (ex. winterbreak) b. Platform = Platform (All or individual platforms) c. Build Version = ++CL (from Horde / Release Ticket) d. Stage Job (Android) = Link to Android Promotion Job from Main Horde e. Keep Release Candidate Script = Link to the job from Main Horde (Clients Only) 3. Check the corresponding box once complete
RM | Disable remaining unneeded builds - Nightly - Nightly Data Rebuild - World Partition Build | TODO | 2025-02-20 |  | DO THIS THE DAY BEFORE RELEASE Commit CL: 12345 | 1. Go to here in P4: //Fortnite/Main/FortniteGame/Build/Streams/ 2. Find the CHECKLIST_VERSION streams.json file for the branch you are editing 3. Check out and open file 4. Create a shelf using the suggested P4 Description in Column H --> 4. Find Nightly Build 5. In the ""schedule"" section > change ""enabled"": true to ""enabled"": false 6. Repeat steps 4-5 for: a. Nightly Data Rebuild b. World Partition Build 7. Save and commit in P4 9. Send courtesy message in Slack to #buildfarm-support-ext using the suggested P4 Description in Column I --> | P4 Description: Disabling the below jobs for Release-CHECKLIST_VERSION: - Nightly Build - Nightly Data Rebuild - World Partition Build #jira none #fyi stan.hormell, swarm-ue-build-reviews #rnx | Hi Build Farm, just wanted to inform you that we disabled the below jobs for CHECKLIST_VERSION at CL XXXXXX. - Nightly Builds - Nightly Data Rebuild - World Partition Build That's all!
Signoff and Submission |  | IN PROGRESS
RM | Verify no new client CLs have been introduced between Final Client WhiteGlove and Final Server/MCP WhiteGlove tests. | TODO | 2025-02-19 |  | Swarm Delta: LINK | 1. Go to the Final Client WG in the #fn-release-CHECKLIST_VERSION-ext channel and note the CL(s) being tested 2. Go to the Final Server/MCP WG in the #fn-release-CHECKLIST_VERSION-ext channel and note the CL(s) being tested a. Ensure these are the intended CLs when comparing with the REAL-XXXX ticket 3. Go to Swarm and edit the link to point to the checklist version and bookend the 2 CLs above. /release-CHECKLIST_VERSION?range=@CLIENT_CL,@SERVER_MCP_CL#commits 4. Ensure all CLs have a Release Manager upvote (which means we have approved and they are not snuck in). a. You can ignore submissions from "Build Machine" 5. If there are any Client CLs, escalate in the #fn-release-mgmt-team-ext immediately
RM | Whiteglove has been completed on FINAL release candidate (aka Cert Checks) and issues called out have been threaded for triage | TODO | 2025-02-19 |  | Slack: LINK_TO_WG | 1. Go to #fn-release-CHECKLIST_VERSION-ext and search for "beginning whiteglove of:" a. This should bring up all instances of whitegloves bring run 2. Ensure RQA completes the Final Client+Server+MCP WG the day of Cert Submission a. You can track progress in TestRail (STC) if you have access 3. Ensure issues called out from the WG are appropriately threaded (outside the WG thread) and triaged in the #fn-release-CHECKLIST_VERSION-ext channel
SUB | Update Akamai with final patch sizes | TODO | 2025-02-19
SUB | Final Scheduling: Xbox One / XSX | TODO | 2025-02-19
SUB | Final Scheduling PS5 | TODO | 2025-02-19
SUB | Final Scheduling PS4 | TODO | 2025-02-19
SUB | Upload PS4 Symbols to devnet | TODO | 2025-02-19
SUB | Upload PS5 Symbols to devnet | TODO | 2025-02-19
SUB | Final Scheduling: Switch | TODO | 2025-02-19
SUB | Submit Android build to Oppo | TODO | 2025-02-19
SUB | Confirm with Luna that we're through certification. | TODO | 2025-02-19 |  |  | Go back to the Luna thread we started for submitting the build, and verify that we're through cert.
SUB | Submit PC build to GFN | N/A | 2025-02-19 |  | GFN will scrape live.
Pre-Release |  | IN PROGRESS
RM | Confirm Release QA is patched up and ready for the morning | TODO | 2025-02-20 |  | NEEDS TO HAPPEN BEFORE 4PM Slack: LINK | 1. Create new thread in #release-team channel using the suggested text in Column H a. Needs to happen before 4pm as people will be gone after then 2. Make sure you have the currently live build installed in your launcher so you can verify the Win patch size come deploy day should you need to | Friendly reminder to the morning deploy owners @RQA1 @RQA2 to ensure your devices are all patched up for the morning deploy. Thanks! |  | Yes
RM | Release Strategy Async Post Example Post: LINK | TODO | 2025-02-20 |  | Slack: LINK | 1. Create a new thread in #fn-release-CHECKLIST_VERSION-ext channel 2. List the Go Live Information recap info (Clients, Backends, Patch Sizes, Deploy Details, People on Duty, Strategy Callouts, Go Live HF, Major Items, and Ship List) from the REAL-XXXX ticket 3. Pin the post | Example Post: LINK
RM | Confirm with Discovery team that the Analytics Stuff revision has been deployed to Live | TODO | 2025-02-20 |  | Slack: LINK | 1. Using the DAD request thread, confirm with Disco team that the Analytics Stuff was updated appropriately for the pending release | Hello again! Just have a checklist item for today to confirm that the Analytics Stuff revision has been deployed to Live. All set there? |  | Yes
RM | Generate Optimized Patches (chunkdbs) for the following platforms - WIKI - Android - PS4 - XB1 - Windows | TODO | 2025-02-20 |  | Horde Job(s): LINK | 1. Go to the Patching tab of Main-Horde 2. Select the 'New Job' button, and choose the Generate Optimized Patches (chunkdbs) template. 3. Set the Build Version to the ++CL that is being released (from the REAL-XXXX ticket) 4. Check Generate ChunksDBs Against Rollback Labels. 5. Set Platforms to any of the 4 platforms from the below list that apply to the ++CL in step 3. a. Android, PS4, XB1, Windows 6. Start Job 7. Re-run steps until all 4 platforms and their corresponding ++CLs are captured a. escalate errors/warnings to #fn-build-health-ext or #buildfarm-support-ext (if applicable) for fixes | Insert message
SUB | Remove ConsoleCert Redirects | TODO | 2025-02-20 |  |  | DO NOT REMOVE PS4 IF WE'RE STILL IN RMT TESTING WITH SONY
SUB | Live: Update PS4/PS5/XboxOneGDK/XSX fake Build Info | TODO | 2025-02-20 |  |  | Needs to be done otherwise you can't check Selective (MSFT)
SUB | Live: Update Switch Build Info | TODO | 2025-02-20 |  |  | NEVER REMOVE BUILDS FROM LIVE
SUB | Live: Update Android Build Info | TODO | 2025-02-20 |  |  | NEVER REMOVE BUILDS FROM LIVE
SUB | Live:Confirm PS4/PS5/XboxOneGDK/XSX fake Build Info has been updated | TODO | 2025-02-20 |  |  | Should already be added but double confirm
RM | Pre-upload symbols for the following (Within 24 hours of deployment) - PC - Switch - Linux - Android Wiki | TODO | 2025-02-20 |  |  | 1. Navigate to the CrashReporter_Symbol-Indexer folder and copy to your computer 2. Open the _Windows file by Right Click > Run With Powershell 3. Input the version number in the format XX.YY (no 2nd decimal) and hit enter 4. Input the CL from the REAL-XXXX Ticket (no ++) and hit enter 5. Repeat for Switch, Android & Linux
RM | Verify Release Request is accurate | TODO | 2025-02-20 |  |  | 1. Look at REAL-XXXX Ticket to ensure everything is up to date and any last minute changes have been captured ex. Clients/Backends/PatchSizes, Release Callouts (migrations, etc) |  |  | Maybe?
RM | Confirm MCP deploy percentage with OGS (now, Pete Axt) and Live Ops. WIKI | TODO | 2025-02-20 |  | Slack: LINK | 1. Make a post in #epic-live-operations-ext or #on-dbs-game-services-ext using the suggested text in Column H | @Pete Axt Just confirming we are targeting 50% DeployHostPercentage during downtime as usual for this CHECKLIST_VERSION MCP deploy? |  | Yes
RM | IF SEASON LAUNCH: Inform the slack channel of the bookmarked RoS, War Room & Calendar Invite Links | TODO | 2025-02-20 |  | Slack: LINK | 1. Go to fn-release-XX.00-ext channel in slack 2. Send message using the suggested text in Column H | @here :announcement-1: Just a heads up for tomorrow: `The Run of Show, War Room Zoom & Calendar Invite` links are bookmarked at the top of this thread. :announcement-1: |  | Yes
RM | Internal Release Email Template | TODO | 2025-02-20 |  | ALL PLATFORMS NEED TO BE THROUGH CERT BEFORE SENDING EMAIL | 1. Look up a previous email to use as a template Search for "online-infra-global@epicgames.com" to find them 2. Copy the formatting and replace content with this release's information a. Look at the REAL-XXXX Ticket for all info 3. Send to the recipients in Column I | TO: online-infra-global@epicgames.com, global-live-deployments@epicgames.com, FN-Live@epicgames.com |  | Maybe?
RM | External Release Email Template | TODO | 2025-02-20 |  | ALL PLATFORMS NEED TO BE THROUGH CERT BEFORE SENDING EMAIL | 1. Look up a previous email to use as a template Search for "partners-liveops-alerts@epicgames.com" to find them 2. Copy the formatting and replace content with this release's information 3. Send to the recipients in Column I | TO: partners-liveops-alerts@epicgames.com BCC: public-alerts@noa.nintendo.com, sie-noc@sony.com, xoc@microsoft.com, epic-issues@vivox.com, noc@subspace.com, release-team@epicgames.com |  | Maybe?
RM | Send "Release is a GO" email | TODO | 2025-02-20 |  | ALL PLATFORMS NEED TO BE THROUGH CERT BEFORE SENDING EMAIL | 1. Look up previous deploy email using the string "is a GO for" 2. Copy the formatting and replace content with this release's information a. Ship List can be found pinned in the release-xxxx-ext slack channel b. Helpful Links can be found in the google calendar c. Down Time, Morning Crew / Patch Sizes can be found in the REAL-XXXX Ticket's Description | TO: fn-release-updates@epicgames.com |  | Maybe?
RM | Release morning owner: Log into all deploy-related tools | TODO | 2025-02-20 |  |  | 1. Log into the following services to ensure their platform is functioning and that you have access and will not be blocked at the last minute. Internal a. Swarm b. LightSwitch2 c. Autoscaler Scaler d. Horde e. Grafana f. Analytics g. Data Asset Directory (DAD) External a. PlayStation i. PlayStation 5 ii. PlayStation 4 b. Microsoft Partner Center c. Nintendo Content Management System d. Nintendo Developer Portal e. NVIDIA GeForce Now f. Amazon Luna g. Android OPPO
RM | Schedule Lightswitch Down in Admin Portal - Scheduling MUST happen at least 1 hour before the downtime start | TODO | 2025-02-20 |  | USE EXTREME CAUTION HERE: There is potential to bring the game down if you are not careful | 1. Go to Lightswitch 2.0 Page in the Admin Portal 2. Go to the "Add Scheduled Event" section at the bottom 3. Set Scheduled Time to the Lightswitch down time in the REAL-XXXX Ticket's Description a. cross-reference LS down time with the CHECKLIST_VERSION Release Strategy Email 4. Set Status to: DOWN 5. Set Message to: Fortnite is down for maintenance. 6. Set Add Actions to: Fortnite_Free_Platforms 7. Select Create Event 8. Double check the info in the new "Scheduled Events" section in the middle of the page - Processed should say No
RM | Record Post PD CLs | TODO | 2025-02-20 | AK | Tracker Tab: LINK | 1. Go to the Post PD Commits Tracker 2. Follow the instructions to complete the task 3. Link the tab in F103 NOTE: This an interim process. Ideally we can pull this data more efficiently through the submit tool flow
RM | Set up Crash Reporter prior to release for Switch | TODO | 2025-02-20 |  | DO NOT DO THIS BEFORE 9PM ET!! DO NOT DO THIS BEFORE SWITCH IS THROUGH CERT | Do this task after 9PM ET 1. Navigate to the below file on the P drive (easily done on a Remote Machine) P:\Symbols\Switch\LiveSymbols\FortniteClient-Switch-Shipping.nsp 2. Open the file and swap in this release's Version Number & ++CL 3. Save and you are done
___ ___ __ __ ___ _ __ _ _ _ ¦ _ \ / _ \ \ \ / / o O O ¦ \ ___ ¦ '_ \ ¦ ¦ ___ ¦ ¦¦ ¦ ¦ / ¦ (_) ¦ \ \/\/ / o ¦ ¦) ¦ / -_) ¦ .__/ ¦ ¦ / _ \ \_, ¦ ¦_¦_\ \___/ \_/\_/ TS__[O] ¦___/ \___¦ ¦_¦__ _¦_¦_ \___/ _¦__/ _¦"""""¦_¦"""""¦_¦"""""¦ {======¦_¦"""""¦_¦"""""¦_¦"""""¦_¦"""""¦_¦"""""¦_¦ """"¦ "`-0-0-'"`-0-0-'"`-0-0-'./o--000'"`-0-0-'"`-0-0-'"`-0-0-'"`-0-0-'"`-0-0-'"`-0-0-'
Lead-up to Downtime - Deployment Owner
| Item | Status | Due buy | Done by | Temp-Notes | Perma-Notes
RM | Final review of Release Request information | TODO | 2025-02-21 |  |  | 1. Make sure all build artifacts match expectations and what was whitegloved by Release QA 2. Make sure all checklist items were completed
RM | Create Post Deploy Tracker sheet and bookmark in in #fn-release-team as well as the associated #fn-release-CHECKLIST_VERSION-ext channel | TODO | 2025-02-21 |  |  | Add as Bookmark to that Release Channel so it is easily visible to everyone. Shared drives > Fortnite > Release Management > Post Deploy > Tracker Sheet > Master Post Deploy Tracker (make a copy, move it to the correct location, and rename) Master Post Deploy: https://docs.google.com/spreadsheets/d/1dycxSjGsHUC29FRelcLz1AVxtBZ8QW2NiG7WsNt-eXo/edit#gid=1420338449 |  |  | Maybe?
RM | Review initial build info setup: Android/Switch and now also including PS4/PS5/XboxOneGDK/XSX fake build info needed starting with 18.40. | TODO | 2025-02-21 |  |  | 1. Make sure Android and Switch candidates are propped up in Live Build Info 2. Make sure Switch build info was removed from NSCert Build Info
RM | Verify Switch symbols crash reporter text file has been updated | TODO | 2025-02-21 |  |  | P:\Symbols\Switch\LiveSymbols\FortniteClient-Switch-Shipping.nsp.version
RM | Verify Generate Optimized Patch was run against the correct build and finished successfully. | TODO | 2025-02-21 |  |  | Android + PS4 + XboxOne + Windows
RM | [Downtime minus 40 mins] Tag Live Ops to Disable Alerts. | TODO | 2025-02-21 |  |  | Only LOps has access to the alerts. Ping whomever is on call to disable. Otherwise there are fireworks. |  |  | Maybe?
RM | [Downtime minus 35 mins] Disable server scaledown ("Pin" server scaling) | TODO | 2025-02-21 |  |  | Navigate to Autoscaler for Live > Click the Edit checkbox (bottom right) > Hit Disable next to "Can Scale Down?" to keep servers from scaling down during downtime. Be sure to post in #fn-release-deploy-ext that this step was done.
RM | [Downtime minus 30 mins] Disable Matchmaking | TODO | 2025-02-21 |  |  | Option 1: MMS Admin Portal toggle button (Navigate to the Live MMS AP page > In the "Playlist Restrictions Configuration" section change "disableAllMatchmaking": to true > Hit the Update button) Option 2: Hotfix directly through Admin Portal System Files DefaultGame.ini [/Script/FortniteGame.FortGameInstance] bBattleRoyaleMatchmakingEnabled=false
RM | Check in "Go Live" Hotfix config and run Preview job | TODO | 2025-02-21 |  |  | Swarm link prepped by Release QA the night prior to release morning Hotfix Deploy Runbook
During Downtime - Deployment Owner
| Item | Status | Due Buy | Done by | Temp-Notes | Perma-Notes
RM | Confirm FN Lightswitch down | TODO | 2025-02-21 |  |  | Validate via Login data that downtime has started properly. (Success by Region/Platform in particular)
RM | PS4/PS5 Client Publish SIEA | TODO | 2025-02-21 |  | New process has PS4/PS5 scheduled like Switch/XB1/XSX | Tip: You might have to be on VPN AND Remote Desktop if performing from a location that does not have a allowlisted IP address. Log in to PlayStation Partners portal then follow these steps in the PS5 section.
RM | PS4/PS5 Client Publish SIEE | TODO | 2025-02-21 |  | New process has PS4/PS5 scheduled like Switch/XB1/XSX | Tip: You might have to be on VPN AND Remote Desktop if performing from a location that does not have a allowlisted IP address. Log in to PlayStation Partners portal then follow these steps in the PS5 section.
RM | Deploy MCP (see Temp-Note in Pre-Release section above for confirmed deploy percentage) (normally 50% for downtime deployments) | TODO | 2025-02-21 |  |  | MCP Deploy Runbook
RM | Deploy MCP to Fortnite Queue Worker Prod11 | TODO | 2025-02-21 |  |  | Fortnite Queue Worker Prod11 in TeamCity
RM | Deploy "Go Live" INI Hotfix config (make sure this is done before server deploy to ensure hotfix config is pulled correctly) | TODO | 2025-02-21 |  |  | Swarm link prepped by Release QA the night prior to release morning Hotfix Deploy Runbook
RM | Deploy "Go Live" Discovery DAD Hotfix | TODO | 2025-02-21 |  |  | Go Live Revision is found in the Game Config sheet.
RM | Deploy Servers | TODO | 2025-02-21 |  | Use the "Fast" option. When this is checked, hosts will immediately start the IPU process | Server Deploy Runbook
RM | Set Server Scale sets to "Sequence" | TODO | 2025-02-21 |  | DS will set it back later in the day | Use the apply all to set each fleet to "sequence" at https://fm-as-scale-fn-prod.ol.epicgames.net/fleet/live/scalesets
RM | PC Client Promotion | TODO | 2025-02-21 |  | PC/Android can be the same job if build labels match | Client Deploy Runbook
RM | Android Client Promotion | TODO | 2025-02-21 |  | PC/Android can be the same job if build labels match | Client Deploy Runbook
RM | Confirm Switch/XSX/XB1/PS4/PS5 (our scheduled platforms) new versions are populating | TODO | 2025-02-21
RM | Start "[Thread] Updates on X.XX Fortnite release:" in #pub-fortnite slack channel | TODO | 2025-02-21 |  | Update with latest big callouts. | Example: https://epicgames.slack.com/archives/C044WR7HZDG/p1691482159647189 [Thread] Updates on 25.30 Fortnite release: (post) Matchmaking Disabled at 3:30 AM ET LightSwitch Down at 4:00 AM ET Deploy started on time (4am ET) and so far things are going smoothly. Estimated uptime is ~5/5:15am ET. Will crosspost any major updates or issues here. |  |  | Yes
RM | Run Live promotion job for Android - Google Play, iOS, PS4, PS5, XB1, XSX, and Switch (no impact to Live players) | TODO | 2025-02-21 |  |  | Example Thread: https://epicgames.slack.com/archives/C044TN4LVFT/p1667291267646149 Example Deploy: https://horde.devtools.epicgames.com/job/6360d85fe271e75dea797f32 22.30 Go Live PS4/PS5/XB1/XSX/Switch - Non-Player facing
RM | Make sure Live Build Info is cleaned up (old fix versions no longer supported) before we go lightswitch up | TODO | 2025-02-21 |  | Expand Live and Live-Compatible sections making sure older releases are not present. Every major release should be a forced patch. (13.40 is fine for Sustained Release on iOS/Map/GooglePlay) | https://adminportal.ol.epicgames.net/launcher/buildinfo/app/Fortnite Ensure that the Promotion Labels section correctly displays the new Live versions for all platforms (This must be done before Light Switch Up) * Build Info for Windows and Shipping-Android should always be real and never fake/dummy/placeholder. * PS4, PS5, XB1, XSX, and Switch will need to be manually updated using the labels from the Live Compat section
RM | [Uptime minus 15 mins] Scaling servers in downtime | TODO | 2025-02-21 |  |  | Note: Servers can take 10-15 min to scale up, please plan appropriately
RM | Make sure all Deploy Strategy callouts are finished before we go lightswitch up | TODO | 2025-02-21 |  |  | Refer to Release Ticket
RM | Additional checks before fully going Lightswitch Up: -Make sure patch has been caught on all platforms by Release QA and that live patch sizes were close to estimates/not egregiously big -If there are brand new non-brcore fleet LTMs going live at Lightswitch Up, confirm we are good with prescaling -Ensure that any QA callouts are okay to come LS Up with, or have a SH that we can associate to each callout as needed -Make sure Live Ops and Community owners approve going Lightswitch Up | TODO | 2025-02-21
RM | Re-enable Matchmaking if the MMS Admin Portal toggle approach was used to Disable Matchmaking above. | TODO | 2025-02-21 |  |  | MMS Admin Portal toggle button (Navigate to the Live MMS AP page > In the "Playlist Restrictions Configuration" section change "disable AllMatchmaking": to false > Hit the Update button)
RM | Fortnite Lightswitch Up. Put "Fortnite is online" in the message box | TODO | 2025-02-21 |  |  | USE EXTREME CAUTION HERE: link to Lightswitch page * Status = Up (for lightswitch UP) * Message = Fortnite is online * Add Actions = Fortnite_Free_Platforms * Create Event
Post-Release - Deployment Owner
| Item | Status | Due Buy | Done by | Temp-Notes | Perma-Notes
RM | [Uptime plus 30 mins] Tag Live Ops to ReEnable Alerts. | TODO | 2025-02-21
RM | Post the following message in the #fn-release-deploy channel once we are lightswitch up: "Friendly reminder that for all general weirdness callouts from this point forward that are unrelated to the live whiteglove to please use #fn-release-XX-XX" | TODO | 2025-02-21 | [5 empty] | Maybe?
RM | Monitor the related release slack channel and thread each one with an acknowledgement (most callouts will come from EU community): -If high urgency: suggest making it a SH -If low urgency: tag appropriate producers/owners to have a look as soon as they get on in normal hours | TODO | 2025-02-21
RM | Update Hotfix Form/Slack Webhook to new release | TODO | 2025-02-21 |  | Scroll to the "Then: Send Web Request" and edit that entry. Make sure to hit Publish once you update and save. | https://api.slack.com/apps/A044VB8SXFV/incoming-webhooks? Add webhook url to FNR automation job: https://jira.it.epicgames.com/secure/AutomationProjectAdminAction!default.jspa?projectKey=FNR#/rule/661
RM | Add "Planned Release Slots" bookmark to the now live release slack channel with a link to the Planned Release Slots Miro board | TODO | 2025-02-21 | [5 empty] | Yes
RM | Create HF Jira for each HF week for this release. | TODO | 2025-02-21 |  |  | Example: FNR-1132 |  |  | Yes
RM | Set Slack channel Topic to Hotfix Request Form | TODO | 2025-02-21 |  |  | Example: Need a Hotfix? https://epic.gm/Hotfix ~ Email `release-team-oncall` to page Release-Team outside of office hours |  |  | Yes
RM | Do a manual post in #fn-live-updates that mentions we are up and copies in the ship list that should be pinned in the related release channel. | TODO | 2025-02-21 |  |  | Example: Good morning! We deployed 26.10 this morning. Game opened up at 5:30 AM ET for players. 26.10 Ship List :ship: * ship list notes here |  |  | Yes
RM | Change JIRA Release from Unreleased to Released | TODO | 2025-02-21 |  |  | Do nothing with any issues still on the release. OOB may linger.
RM | Update Release Log and Release Request | TODO | 2025-02-21 | [5 empty] | Yes
RM | [Uptime plus 2 hours] Enable server scaledown ("Unpin" server scaling) after server usage levels off closer to what it was pre-downtime. Check in with LiveOps first. | TODO | 2025-02-21 |  |  | Navigate to Autoscaler for Live > Click the Edit checkbox > Set "Can Scale Down?" to Yes Be sure to post in #fn-release-deploy-ext that this step was done.
RM | Zero Out AutoScaler Scaler Capacities | TODO | 2025-02-21 |  | Do this when you unpin | https://fm-as-scale-fn-prod.ol.epicgames.net/fleet/live/scalecapacity
RM | Send first Post-Deploy report email | TODO | 2025-02-21 |  | 1. 7am 2. 11am - Contact perf and get release updates to send out. 3. Afternoon 4. Next Day *Add Slack reminders for the email updates | List of Reports |  |  | Yes
RM | Set timed post for 2:30PM ET to: Post in #buildfarm-support-ext to remove the previous release version | TODO | 2025-02-21 |  | Make sure to use the timed post feature in slack to send it at 2:30 PM ET. | Reach out to Build Farm Support via #buildfarm-support-ext channel in slack and ask them to remove the previous branch from horde after the deploy is complete |  |  | Yes
RM | Make sure the Post Deploy Tracker has Stability information in time for the 10:00AM ET Stability Sync | TODO | 2025-02-21 | [5 empty] | Yes
SUB | Update the master cert timing tracker sheet | TODO | 2025-02-21 |  |  | Tracker Google Sheet -- tracking Switch / PS4 (SIEE/SIEA) / PS5 / MSFT
SUB | Update Patch Size Tracking | TODO | 2025-02-21 |  |  | Remember to add Install time thresholds as well
SUB | Increment Switch and PlayStation versions | TODO | 2025-02-21
SUB | Update Sony LatestPatch folder to contain these patches | TODO | 2025-02-21 |  |  | MasterReleases->1.0->Create folder for appropriate app version
SUB | Update Nintendo LatestPatch folder to contain these patches | TODO | 2025-02-21
SUB | Update Xbox LatestPatchfolder to contain these patches | TODO | 2025-02-21
RM | Copy entire build(s) to Milestone Archive | TODO | 2025-02-21 |  |  | This is a copy of the entire build as it appears in the build folder to keep from having to rebuild if it is needed. Archive Fortnite Build CLs (New Job > Archive Fortnite Build > add in the ++CLs > Start Job). For Clients archive the clients and the Content Worker. This can later be found at : P:\Builds\Archive\Fortnite-Releases\Milestone++Fortnite+Release-XX.XX-CL-12345678 |  |  | Maybe?
RM | Send Day-2 Post-Deploy report email | TODO | 2025-02-22 | [5 empty] | Yes
PART | Update Partners Builds | TODO | 2025-02-21 |  |  | Create Release Ticket for Partner Build
Not currently relevant (re-visit as needed)
| Item | Status | Due by | Done by | Temp-Notes | Perma-Notes
x | (Joe) I would just completely kill this line in favor of the Build Protection line just above. Run Keep Release Candidate job for all final client candidate CLs. | TODO | 2025-02-19 |  | PLATFORM_1: HORDE_JOB_LINK PLATFORM_2: HORDE_JOB_LINK PLATFORM_3: HORDE_JOB_LINK | 1. Go to the REAL-XXXX ticket for this release to see the final candidate CLs 2. Go to the Promotions tab of Main Horde 3. Select the blue New Job button in top right 4. Change template dropdown to Keep Release Candidate 5. Put the first CL in the Change field and set the associated Promote Platforms field. Then Start Job. a. Re-Run for all Client CLs with their associated Promote Platforms field.
| Verify the Android APK allowlist is in the game config file | N/A | 2025-02-20 |  | Release Team no longer needs to send hotfixes to update CRC values when we ship new Android client builds. The 13.40 values need to stay, but the Android APK Whitelist hotfixes no longer function in 23.50+ . This is now being done on the AntiCheat side via Dragonfly. | Verify it is in the game config file
SUB | Review Android APK allowlist syntax is included and correct in Release QA swarm link and in PredeployA files | N/A | 2025-02-21 |  | Release Team no longer needs to send hotfixes to update CRC values when we ship new Android client builds. The 13.40 values need to stay, but the Android APK Whitelist hotfixes no longer function in 23.50+ . This is now being done on the AntiCheat side via Dragonfly.
| Create a Jira for StW Calendar/Store to be update/reviewed (CN/RoW) | TODO | 2025-01-06 |  |  | Assign to Dav Harnish and CC Henry Meredith in comments https://jira.it.epicgames.net/browse/FORT-247162
| Check Android APK size and make sure it is under 150 MB | TODO | 2025-02-12 |  |  | Look at APK in the build folder
| Test Upload iOS build and verify Compressed File Size is < 200 MB | TODO | 2025-02-12 |  |  | On the Apple Portal
| Create a tab in FN Playlist Planning sheet and let stakeholders know in #fn-release-playlistplanning-ext that it now exists | TODO | 2025-01-06 |  |  | https://confluence.it.epicgames.com/display/FORT/Playlist+Planning Note: If its a .10 release, spin up a thread. If its not, then mark this task as N/A.
| Schedule Meeting: Release Notes Signoff | N/A | 2025-01-28 |  | No Release Notes! | Thurs. of CertSub week
| Release Notes: Initial Setup and Email Sent | N/A | 2025-01-28 |  | No Release Notes!
| Schedule Calendar Reminders: Release Notes Section Owners | N/A | 2025-01-28 |  | No Release Notes! | 1 each day for 2 document days of release notes
| Create Version on iTunes Connect and let Publishing know | TODO | 2025-01-28
| Order breakfast for morning of publish day | TODO | 2025-02-09 |  | Please bring this back!!!
| Send initial IOS Submission email | TODO | 2025-02-09
| Update Google Play Roadmap email (if applicable) |  | 2025-02-09 |  |  | to: Dan Song <mtd@google.com(opens in new tab)> Lawrence Koh <lawrencekoh@google.com(opens in new tab)> CC release-team Jocelyn Hans
| Send Release Notes 1st Draft to FN-Release-Updates | N/A | 2025-02-09 |  | No Release Notes!
| Forward CN patch notes to EGC | N/A | 2025-02-12 |  | No Release Notes! | Forward version patch notes for China to Martin Yu. Martin will review and deliver to Tencent.
| Add IOS Whitelist Hotfix to MobileCert | TODO | 2025-02-13
| Audit MobileCert environment config for potential cert blockers | TODO | 2025-02-19
| Configure MobileCert Build Info | TODO | 2025-02-19
| MobileCert: MCP Update | TODO | 2025-02-19
| MobileCert: Server Promote | TODO | 2025-02-19
| Cert Submission: iOS | TODO | 2025-02-19
| Send email notifying Apple contacts that build is uploaded | TODO | 2025-02-19
| Send email notifying Google contacts that build is uploaded | TODO | 2025-02-19
| Remove MobileCert Redirect | TODO | 2025-02-20
| Live: Update iOS Build Info | TODO | 2025-02-20
| Remove Android Build Info from MobileCert | TODO | 2025-02-20
| Live: Update LiveCN Build Info | TODO | 2025-02-20 |  |  | Deploy will be coordinated with TC in #ext-fncn-live in Slack. TC will flip WeGame switches. THIS STEP IS ONLY NEEDED IF STAGING THE CN BUILD FAILED.
| Update Apple Cert Timing Tracker | TODO | 2025-02-21
| Update EULA if requested by Legal | TODO | 2025-01-28
VVV To be Re-Added Once iOS comes back VVV
| Make sure PredeployA Hotfix Files are set back to appropriate Android Whitelist and IOS Banning syntax for LOPS to copy at time of release | TODO | 2025-02-20 |  | Only Android? | Android: Whitelist syntax needs to be added IOS: Remove the following: [/Script/FortniteGame.FortGameModeZone] BanCodeAction_20=(AnyReason=2, UnsignedIPA=0) BanCodeAction_28=(AnyReason=2, NoIOSCryptInfo=0)
| Make sure PredeployA Hotfix Files are set back to appropriate Android Whitelist and IOS Banning syntax for QA to not be blocked | TODO | 2025-02-21 |  |  | Android: Whitelist synatx needs to be removed IOS: Add the following: [/Script/FortniteGame.FortGameModeZone] BanCodeAction_20=(AnyReason=2, UnsignedIPA=0) BanCodeAction_28=(AnyReason=2, NoIOSCryptInfo=0
| Determine if release breaks Replays and/or if we should whitelist any old CLs | TODO | 2025-01-28 |  | https://wiki.it.epicgames.net/pages/viewpage.action?spaceKey=FORT&title=Replay+Whitelisting | Should be considered if we are breaking replays of a major Live event from the previous release Ask Shak or Matt Grandstaff
| Test verify PS4 remaster jobs have no errors or warnings | TODO | 2025-02-11 |  |  | Nightly Job "Publish PS4 Remaster Submission Packages (SIEA Only)"
| Confirm all Non-Unity warnings and errors are fixed or benign | TODO | 2025-02-11
| PS4: Update R:\Analytics\sony_version.csv | TODO | 2025-02-21 |  | I refuse | Instruction Doc
Lead-up to Downtime - China Deploy Owner
| Make sure PredeployA Hotfix Files are set back to appropriate Android Whitelist and IOS Banning syntax for QA to not be blocked | TODO | 2025-02-21 |  |  | Android: Whitelist synatx needs to be removed IOS: Add the following: [/Script/FortniteGame.FortGameModeZone] BanCodeAction_20=(AnyReason=2, UnsignedIPA=0) BanCodeAction_28=(AnyReason=2, NoIOSCryptInfo=0
| [24 hrs before] Inform Tencent and Community | TODO | #REF! |  |  | 24 hrs before - Inform in #ext-fncn-live @Sula Yu and CN QA deply captain Check EGC QA Checklist > Captain tab for additional @ https://docs.google.com/spreadsheets/d/1nUx7qP1aLLU6D1VVv0Q4mx18aMMG_tz5vmQC0Z9wxgc/edit?usp=sharing
| [24 hrs before] Release JIRA | TODO | #REF! |  |  | Link Release management Jira ticket here
| [2 hours befire] Hotfixes Checked In and Previewed | TODO | #REF! |  | Check fn-release-team around 4PM ET | RQA will provide a Swarm shelf to approve and merge around 4PM ET https://docs.google.com/spreadsheets/d/1w5PQcnciR-lbbU6H6m0aaqgiFWNRbttSr7uEoCmKUzk/edit#gid=2063781583
| [2 hours before] Schedule Downtime (Fortnite) | TODO | #REF! |  | Schedule sometime before 4:40pm | https://adminportal-website-management.ol.epicgames.net/lightswitch2/schedule/fortnitelivecn?server=Lightswitch&moduleName=lightswitch
| [1 hrs before] Verify Client, Server, and MCP for release | TODO | #REF! |  |  | Pinged in Release Private if unsure of any changes
| [1 hrs before] Internal Release Email | TODO | #REF! |  |  | fncn-live@epicgames.com, fn-live, online-infra, global-live-deployments
| [35 min before] Turn off FN CN Alerts | TODO | #REF! |  | Poke liveOPS at MMS disable | Request liveOPS pause FN Grafana integration in OpsGenie https://epicgames.app.opsgenie.com/teams/dashboard/76f730d9-7346-4f83-b599-ab3589ba2fce/integrations
| [35 min before] Alternatively, Set False to True for Playlist Restrictions Configuration section at https://adminportal.ol.epicgames.net/fortnite/profileProxy?server=Fortnite%20China&moduleName=fortnite Click MMS at top and scroll down to Playlist Restrictions Configuration Set disableAllMatchmaking to true | TODO | #REF! |  |  | 35mins before LS down Edit directly under Admin Portal https://adminportal-website-management.ol.epicgames.net/fortnite/systemFiles Make sure you are in "Fortnite China" Notify fn-release-deploy (FN-Deploy Public) and Mission Control slack channels |  | For Old Hotfix Method: DefaultGame.ini [/Script/FortniteGame.FortGameInstance] bBattleRoyaleMatchmakingEnabled=false
During Downtime - China Deploy Owner
| Item | Status | Due by | Done by | Temp-Notes | Perma-Notes
| Confirm Lightswitch down status | TODO | #REF! |  |  | Check status has switched to DOWN - https://adminportal-website-management.ol.epicgames.net/lightswitch2/schedule/fortnitelivecn?server=Lightswitch&moduleName=lightswitch
| Lightswitch down notifications | TODO | #REF! |  |  | Post message in fn-release-deploy and Mission Control slack channels
| We Games access disabled | TODO | #REF! |  |  | Notify ext-fncn-live to disable access for we games. More often than not this is Sula, but confirm it isn't a different Tencent employee
| Deploy "Go Live" INI Hotfix config (make sure this is done before server deploy to ensure hotfix config is pulled correctly) | TODO | #REF! |  |  | Can move on to MCP and Client deploys until Hotfix is done. Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy internal
| Deploy MCP | TODO | #REF! |  |  | Deploy %: 50% Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy internal
| Deploy MMS | TODO | #REF! |  |  | Done by MMS team after matcmaking is disabled - confirm with them during release sync if a deployment is being done. Loop them in when light switch down
| PC Client Deploy - Use Promotion Job (Client) | TODO | #REF! |  |  | Whole build string, LiveCN, only Windows. Allow Live Promotions and BPT checked Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy Public
| Server Deploy | TODO | #REF! |  | Make sure Hotfix is underway before Deploying Server. Otherwise servers won't get new hotfixes for possibly 4 hours. | Start immediately after hotfix deploy, due to server prep time, hotfixes should be live just prior to sessions starting Fleet: LiveCN Cohort: Main Use fast deploy option for downtime releases. Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy internal
Post-Release - China Deploy Owner
| Item | Status | Due by | Done by | Temp-Notes | Perma-Notes
RM | Nvidia: reply to already existing corresponding release thread in #ue-partner-nvidia-ext with courtesy status updates | TODO | 2025-02-21 |  |  | Usually Douglas Valkenaar, Alexander Gustev or Andrew Saritsky - #external-nvidia channel |  |  | Maybe?
| StW Whiteglove | TODO | #REF! |  |  | Poke ext-fccn-live with @s to start whiteglove
| BR Whiteglove | TODO | #REF! |  |  | Whiteglove is completed by both Epic CN and Tencent teams separately - need confirmation from both teams of a successful check.
| If help is needed flushing buckets | TODO | #REF! |  | Click "Direct control panel link" in next link | https://adminportal-website-management.ol.epicgames.net/fortnite/profileProxy?server=Fortnite%20China&moduleName=fortnite
| Re-enable Light Switch Up | TODO | #REF! |  |  | Ready once the whiteglove has been confirmed and without any issues Update status message to Fortnite is up! Notify Sula - Access has been re-enabled. @Sula Yu please re-enable from wegames side as well Notify in Mission Control and FN-Release-Deploy - No whiteglove callout and lightswitch up
| Re-enable CN alerts | TODO | #REF! |  |  | Unpause FN Grafana integration in OpsGenie https://epicgames.app.opsgenie.com/teams/dashboard/76f730d9-7346-4f83-b599-ab3589ba2fce/integrations
| Post in #buildfarm-support to remove the previous release version | TODO | #REF! |  |  | Reach out to Build Farm Support via #buildfarm-support channel in slack and ask them to remove the previous branch from horde after CN deploy is complete
| Archive previous release Slack channel | TODO | #REF!

## V5 Combined Release Checklist D (hidden)
| V5 | Branch Open Date: | 2025-01-06 | Change to =Workday? | 2025-01-18 | <-- Schedule Bug Bids Email To Go Out On This Date | Formula. Do Not Edit | Checklist_Version | Find and Replace
76 |  | Hard Lock: | 2025-01-28 |  |  | INSERT_REAL_TICKET | Information to gather
41 |  | Pencils Down: | 2025-02-07 | Weekend |  | ROS Sheet | POST Deploy
83 |  | Cert Submission: | 2025-02-13 |  |  | ROS Zoom
|  | ROW Deploy: | 2025-02-21 |  |  | JIRA DASHBOARD
|  | Item | Status | Due by | Completed by | Temp-Notes | Steps To Complete | Suggested Slack Post Text (unless otherwise stated) | Suggested Slack Thread Text (unless otherwise stated) | Automation? | Additional Notes
| Pre-Candidate Build - MUST DO | [5 empty] | 77
Reorg | By Hard Lock: |  | IN PROGRESS
PROD | RM | Release Content Legal Approval has Started | N/A | 2025-01-27 |  | Slack: LINK | 1. Navigate to the #fn-legal-publishing-approvals-ext slack channel 2. Look for thread containing Ready For Review a. Currently by Ben Massoglia (Adam Baxter if Ben is OOO) 3. If thread is not present, send a DM to Ben Massoglia asking when that will happen
PROD | RM | Make sure Disallow List has Started (Data Encryption) | TODO | 2025-01-27 |  | Slack: LINK | 1. Navigate to the #fn-encryptedassets-ext slack channel 2. Look for the thread containing Datamine Results a. Currently by Ben Massoglia (Adam Baxter if Ben is OOO) 3. If thread is not present, send a DM to Ben Massoglia asking when that will happen 4. Reminder to confirm that All FN, FNE (Creative+UEFN), JUNO, DelMar, Sparks terms are being checked
SUB | SUB | Ensure Sony publishing tools are up to date | TODO | 2025-01-27 |  | Slack: LINK | PS4: https://ps4.siedev.net/docs/master_submission PS5: https://p.siedev.net/docs/master_submission To find Sony Publishing Version: Look at the build logs from the "PS4 Client Full Package" step lists the version of the tools in the output Ping Luke Thatcher and/or Ben Woodhouse if you have issues
SUB | SUB | Confirm SwitchEngine.ini updated with new Version and Release | TODO | 2025-01-27 |  | Commit CL: 12345
SUB | SUB | Make sure PS4 SIEE (07669) packages are being built | TODO | 2025-01-27
| By Pencils Down: |  | IN PROGRESS
OPS | RM | All Remaining Build Errors/Warnings Have Been Approved To Ship With - Start on the 1st Nightly build after HardLock | TODO | 2025-02-04 |  | Tracking Sheet Here Last Update: - MONTH_DAY | 1.Go to the Tracking Sheet and dupe the template and rename to this checklists version 2. Go to the Builds tab of the Horde Branch for the checklist's version 2. Go to latest completed Nightly and SSB builds. 3. Go through any Red/Yellow badges in the Clients, Servers, UEFN columns and enter information into the tracker sheet. a. You can ignore the Test Content Worker Docker Image Win64/Linux badges in the UEFN section 4. Go through any Red/Yellow badges in the Nightly Data Rebuild & World Partition Build builds and enter information into the tracker sheet. 5. Once you have entered all Errors/Warnings into the tracker sheet, spin up build health threads (as normal for BH) in the #fn-build-health-ext channel and escalate to the appropriate people for sign off - template in 1st tab of sheet a. Ensure all issues have a JIRA for tracking so these can be addressed at some point 6. Spin up a general World Partition Build thread and tag Sébastien Lussier for review (example here)
OPS | RM | Verify Android version number has been updated in perforce | TODO | 2025-02-06 |  | Commit CL: 12345 | 1. Open P4 and navigate to the below file //Fortnite/Release-CHECKLIST_VERSION/FortniteGame/Config/DefaultEngine.ini 2. Search file for the string: VersionDisplayName a. Should live under the [/Script/AndroidRuntimeSettings.AndroidRuntimeSettings] header 3. Verify this is set to CHECKLIST_VERSION.0
OPS | RM | Verify iOS version number has been updated in perforce | TODO | 2025-02-06 |  | Commit CL: 12345 | 1. Open P4 and navigate to the below file //Fortnite/Release-CHECKLIST_VERSION/FortniteGame/Config/IOS/IOSEngine.ini 2. Search file for the string: VersionInfo a. Should live under the [/Script/IOSRuntimeSettings.IOSRuntimeSettings] header 3. Verify this is set to CHECKLIST_VERSION (should not have a .0)
OPS | RM | Verify Version Locking AND that the Net Version locked to is different than the currently live branch | TODO | 2025-02-06 |  | PREVIOUS_VERSION: 12345 CHECKLIST_VERSION: 12345 Reviewed by: PERSON | 1. Open P4 and navigate to the below file path //Fortnite/release-PREVIOUS_VERSION/Engine/Source/Runtime/Core/Public/Misc/NetworkVersion.h 2. Search file for the string: ENGINE_NET_VERSION 3. Note the listed CL in Column F 4. Repeat steps 1-3 using the below file path //Fortnite/release-CHECKLIST_VERSION/Engine/Source/Runtime/Core/Public/Misc/NetworkVersion.h a. If the ENGINE_NET_VERSION is not set to 0, verify the set CL is higher than the previous release's CL b. If the ENGINE_NET_VERSION is set to 0, set it to a CL that is higher than the previous release's CL i. Can use the last successful Nightly Build CL & make sure to deadend your commit using the suggested text in Column H 5. Once submitted, have someone else on the team review your commit. | Setting NetCL after CHECKLIST_VERSION Hardlock #jira none #okforgithub public #rnx #robomerge -NEXT_VERSION #submittool bypass
PROD | RM | Send Slack Review For Untriaged Pre-SH & QA High Risk JIRAs: Keep this checklist item open until closer to CERT to continue to refresh and escalate issues added | TODO | 2025-02-06 |  | Slack: LINK Last Update: - MONTH_DAY | 1. Go to the following FILTER and set the affectedVersion=CHECKLIST_VERSION 3. Spin up a thread in the #fn-release-CHECKLIST-VERSION-ext slack channel using the suggested text in column H/I --> a. Tag in the Tech component owner (currently Chris Tran / Jay Chaney) and the seasonal prod owner (row 1) b. Tag in Component owners for each JIRA in the filter c. Copy the links to the 2 filters and link them over their associated blue text Example: LINK Steps for how to easily add jiras into message in this cells note (This task would certainly benefit from an already existing workato recipe... someone just needs to set it up) | CHECKLIST_VERSION Untriaged Pre-SH & QA High Risk Review :thread: | Hi @PROD_OWNER & @Chris Tran If y'all have time in the next couple days, RM would appreciate your review of various Untriaged QA High Risk & Pre-SH JIRAs affecting CHECKLIST_VERSION. Please ensure these JIRAs have an appropriate Priority, Fix Version & Assignee set so they do not fall through the cracks. The goal of this ask is to make sure these crashes get visibility and review now, instead of potentially in a post-release shit happens. We will be doing a sweep of this dashboard periodically leading up to CERT. :ty: in Advance! PreShitHappens and QAHighRisk XXX | Yes | Workato - Component Lookup
PROD | RM | Send Slack Review For Untriaged Escaped Crashes / Asserts / Ensures JIRAs: Keep this checklist item open until closer to CERT to continue to refresh and escalate issues added | TODO | 2025-02-06 |  | Slack: LINK Keep this checklist item open until closer to CERT to continue to refresh and escalate issues added | 1. Go to the following FILTER and set the affectedVersion=CHECKLIST_VERSION 3. Spin up a thread in the #fn-release-CHECKLIST-VERSION-ext slack channel using the suggested text in column H/I --> a. Tag in the Tech component owner (currently Chris Tran / Jay Chaney) and the seasonal prod owner (row 1) b. Tag in Component owners for each JIRA in the filter c. Copy the links to the 2 filters and link them over their associated blue text Example: LINK Steps for how to easily add jiras into message in this cells note (This task would certainly benefit from an already existing workato recipe... someone just needs to set it up) | CHECKLIST_VERSION Untriaged Escaped Crashes / Asserts / Ensures Review :thread: | Hi @PROD_OWNER & @Chris Tran If y'all have time in the next couple days, RM would appreciate your review of various Untriaged Escaped Crash / Assert / Ensure JIRAs affecting CHECKLIST_VERSION. Please ensure these JIRAs have an appropriate Priority, Fix Version & Assignee set so they do not fall through the cracks. The goal of this ask is to make sure these crashes get visibility and review now, instead of potentially in a post-release shit happens. We will be doing a sweep of this dashboard periodically leading up to CERT. :ty: in Advance! Escaped Crashes / Asserts / Ensures XXX | Yes | Workato - Component Lookup
SUB | SUB | Get engineer sign off of patch Sizes | TODO | 2025-02-06 |  | Slack: LINK | Tag fn-tech-patchreview in #fn-release-patchsizes. Try to send first prelim sizes soon after hard-lock |  | Hello @fn-tech-patchreview Can you please review and sign off on the above Patch Sizes?
PROD | RM | Release Content Legal Approval (FN and UEFN content) Cosmetic Content Assets Sheet | TODO | 2025-02-06 |  | Slack: LINK | 1. Navigate to the #fn-legal-publishing-approvals-ext slack channel 2. Look for thread containing Ready For Review a. Currently by Adam Baxter & Ben Massoglia (Ben to take over in the future) 3. If thread is not present, send a DM to Adam Baxter & Steve Allison asking when that will happen 4. Ensure final sign off is given | Hi @Ben Massoglia, just checking in for CHECKLIST_VERSION readiness. Have we confirmed we are all wrapped up and ready to go on the Legal/Publishing front? If not, what is still left to do? :ty: in advance!
PROD | RM | Make sure Disallow List was reviewed (FN, FNE (Creative+UEFN), JUNO, DelMar, Sparks terms) | TODO | 2025-02-08 |  | Slack: LINK | Reference: Term Tracker Sheet 1. Navigate to the #fn-encryptedassets-ext slack channel 2. Look for the thread containing Datamine Results a. Currently by Adam Baxter & Ben Massoglia (Ben to take over in the future) 3. If thread is not present, send a DM to Adam Baxter & Steve Allison asking when that will happen 4. Reminder to confirm that All FN, FNE (Creative+UEFN), JUNO, DelMar, Sparks terms are being checked | Hi @Ben Massoglia, just checking in for CHECKLIST_VERSION readiness. Have we confirmed we are all wrapped up and ready to go on the Encrypted Assets front? If not, what is still left to do? And also - as always - just confirming All FN, FNE (Creative+UEFN), JUNO, DelMar, Sparks terms are being checked. :ty: in advance!
| By Cert Submission: |  | IN PROGRESS
PROD | RM | Confirm the final loc commit job successfully makes it into P4 Need to ask for: - Fortnite - UEFN - Lego - Festival - Rocket Racing | TODO | 2025-02-12 |  | Slack: LINK | 1. Navigate to the #fn-release-loc slack channel 2. Look for the thread around Final Loc Import and tag in the LOC POCs for all of the live products (currently FN, UEFN, Festival, Rocket Racing & Lego) a. FN is Kevin Shen UEFN is Abdul Alenezi, Festival, RR, Lego are Liza Grebenshchikova 3. If not already stated when its coming in (or past that date), poke the thread using the suggested text in Column H | Hi @loc-fn-producers @Abdul Alenezi just want to confirm the final loc commit job for CHECKLIST_VERSION is on track for all products. Will that be delivered tonight by tonight?
OPS | RM | FortniteContentBuilds: - This is Content On Demand (downloading additional stuff in the background which is only present on some platforms) Verify platforms below have been updated correctly: - PC/Windows - Android - PS4 - PS5 - Switch - XB1 - XSX - iOS Old Wiki | TODO | 2025-02-12 |  | Check the prior 3 content versions, and confirm they are present in the Rollback labels (code only versions will not appear) If the admin portal looks weird, confirm the .json file is showing the correct CLs for CONSOLES Escalate any issues to the #fn-tech-ext channel If Switch doesn't look correct, escalate to Justin Marcus to see if that is intended or not (something about Fort inquiry??) | 1. Navigate to the FortniteContentBuilds section of the Admin Portal 2. Under the Promotion Labels section, Look for the Live label (should be first) and open the dropdown 3. Open another window and go to the Release Log to see our live CLs 4. Copy the Live CL for PC/Windows and search for it in the admin portal's Live Label to verify it is correctly reflected a. Repeat this step for Android, PS4, PS5, Switch, XB1, XSX, iOS (Ignore XboxOne & XboxOneGDK) 5. Repeat steps 2-4a. This time for the Rollback label. a. Type Rollback into the filter, then hit the Label Name column header twice to find it. 6. The CL you are looking for is the CL immediately previous to the live CL. Look in Current & Previous Releases section of the Release Log 7. As a secondary check (FOR CONSOLES ONLY - NOT PC), you can navigate to the below file on the network drive (easiest to use a VM to work computer) P:\Builds\Automation\Fortnite\Config\ConsoleLiveLabels.json 8. Do a find and search of the live and immediately previous to live CLs to ensure they are present a. Can open the file in a text editor > Ctrl+F > Insert CL. It should return 5 hits (PS4, PS5, Switch, XB1, XSX)
OPS | RM | Get Folder Comparison sign off from Anticheat for PC (Anticheat PC Diff for UEFN and FN) | TODO | 2025-02-12 |  |  | 1. Check email for Folder Comparison 2. Find the email associated with the latest approved PC candidate (ex. ++Fortnite+Release-26.30-CL-28509302) 3. Ensure there are links to the diff (current live CL vs candidate) for the Game Client & UEFN 4. Ensure we get sign off (Ben Temple, Joe Barrett or Lukasz currently) | CHECKLIST_VERSION Folder Comparison Sign Off :thread: | Hello @ben.temple @joe.barrett @lukasz
Preparation
|  | Item | Status | Due by | Completed by | Temp-Notes | Steps To Complete | Suggested Slack Post Text (unless otherwise stated) | Suggested Slack Thread Text (unless otherwise stated)
| By Branch: |  | IN PROGRESS
PROD | RM | Replacing template text in this checklist OPTIONAL: Alex Will Do This If You Don't Want To | TODO | 2024-12-30 |  | This step should eliminate needing to change MOST template text in any pathing or messaging templates OPTIONAL: Alex Will Do This If You Don't Want To | 1. Click Cell A1 2. Press Ctrl+F > push the 3 dots 3. Find the string "CHECKLIST_VERSION" and replace it with the real value a. ex. Find: CHECKLIST_VERSION Replace with 32.00 ^Checklist dot Version^ 4. Select the "Replace All" button to swap all instances 4. Repeat steps 3-4 by replacing PREVIOUS_VERSION with 31.40 ^Previous Version^ 5. Repeat steps 3-4 by replacing CHECKLIST-VERSION with 32-00 ^Checklist dash Version^ 6. Repeat steps 3-4 by replacing NEXT_VERSION with 32.10 ^Next Version^ 7. Repeat steps 3-4 by replacing NEXT_MAJOR_VERSION with 33.00 ^Next Major Version (.00)^ You will know it worked if all red text in this cell/sheet has been updated to the set values
OPS | RM | Branching Dates Slack Email Kickoff | TODO | 2024-12-30 |  | Slack: LINK | 1. Spin up a thread titled ":thread: CHECKLIST_VERSION Branching" in #buildfarm-support-ext and use the suggested text in column H for the thread messaging 2. Search for previous email (from a similar version number) titled: "[Branch News]" 2. Copy the formatting into a new email and swap in the appropriate information gleaned from the buildfarm thread | Thread Title: :thread: CHECKLIST_VERSION Branching! :yesyes: ------------------------------------------------------ Thread Body: Based on the roadmap: - Branch Operation/Creation: DAY_DATE from BRANCH - Branch Opening/Work Cutover (9am ET): DAY_DATE Sending out initial email NEXT day afternoon for wider knowledge. @release-team @buildfarmsupport @p4admins @fn-buildhealthqa | Thread Title: :thread: CHECKLIST_VERSION Branching! :yesyes: ---------------------------------------------------------------------- Hello! It's about that time again. CHECKLIST_VERSION/Dev-FN-XX Branch Operation is DAY_DATE and officially opens for business DAY_DATE morning per the roadmap. Based on the roadmap: Dev-FN-XX - Branch Operation/Creation: DAY_DATE from BRANCH - Branch Opening/Work Cutover (9am ET): DAY_DATE XX.00: - Branch Operation/Creation: DAY_DATE from BRANCH - Branch Opening/Work Cutover (9am ET): DAY_DATE Sending out initial email Tuesday afternoon for wider knowledge. Will be pushing extra hard on proxy servers. Has there been changes to the proxy server process and is the wiki up to date? @release-team @buildfarmsupport @p4admins @fn-buildhealthqa | Yes | Replace with Pre-Pop
OPS | RM | Branching Email - Go Ahead and Sync Reply | TODO | 2025-01-02 |  | Should be done on the friday the week prior to branch open | 1. Reply to Branch News email with a "branch is now fully open" message 2. Search for previous email (from a similar version number) titled: "[Branch News]" 3. Copy the formatting into a reply to the original email from from row 34 and swap in the appropriate information | see Stan's 30.30 for text |  | Yes | Replace with Pre-Pop
OPS | RM | Branching Email - Branch is now fully open! | TODO | 2025-01-06 |  |  | 1. Reply to Branch News email with a "branch is now fully open" message 2. Search for previous email (from a similar version number) titled: "[Branch News]" 3. Copy the formatting into a reply to the original email from from row 34 and swap in the appropriate information |  |  | Yes | Replace with Pre-Pop
OPS | RM | Ensure "Time Offset" is set to the main branches' season start date ONLY RUN IF THIS IS A XX.00 CHECKLIST (otherwise N/A) | TODO | 2025-01-06 |  | Adjusted offset by XX days ONLY RUN IF THIS IS A XX.00 CHECKLIST (otherwise N/A) | 1. Go to the below file in p4 > get latest > checkout and open https://epicenter.on.epicgames.com/fortnite/backends/latest-gamedev 2. Determine the deploy date for NEXT_MAJOR_VERSION (which main is currently representing) in the release calendar or FN Release Schedule 3. Using the built in calculator, calculate the number of days from today till that date 4. Search for the following and swap that value in for the value that is currently set in the file > save config.com.epicgames.modules.profile.time_offset_days: 5. Click on the days cell on the right to copy to clipboard 6. Update the value on the left window 7. Save Don't need to kick it in manually as its scheduled to kick every time a main build finishes as well as every hour 8. Check back in TeamCity to ensure the pending change is now a real boy
PROD | RM | Create fn-release-CHECKLIST-VERSION-ext Slack channel and invite groups/users listed in Columns H/I | TODO | 2025-01-06 |  | Slack Channel: LINK IT Request: LINK | 1. Create a new slack channel using the naming format "fn-release-CHECKLIST-VERSION-ext" a. Type /channel and press enter to bring up the window b. Select fn for the prefix c. Channel name = release-CHECKLIST-VERSION d. Check Allow Non-Employees In the Channel e. Skip Invite Users & Topic for now f. Description = Coordination Channel for the CHECKLIST_VERSION Release g. Result should look like: fn-release-CHECKLIST-VERSION-ext 2. Add the people in columns H and I a. Cross reference with This List from Frima to ensure the list in column I is up to date. If not, please update it accordingly 3. Create an IT request to add the 'Fortnite External QA' workspace a. Send a message to it-helpdesk with the following message: Hello there, can I please have the `Fortnite External QA` Workspace added to the newly created #fn-release-CHECKLIST-VERSION-ext channel? @Andrew Lucas for vis on this request Thanks in advance! | Internal Friends To Add (can add all at once, may have to manually adjust the red ones by clicking on them and selecting the intended alias)) ---------------------------------------------------------------------- @release team @release qa @fn-perfprod @community_swat @greg.garnhart @tristan.hardy @fn-buildhealthqa @liveqa @eric.day @lusine.davtyan @competitive ops @laura.stone @paris.nourmohammadi @Michael Micholic @chris.etuk @fn-calendar-owners @epic-liveops | External friends need to be added with the '/user add @username' command (These are all Frima folks) NOTE: copy/pasting this list may not work. If not, add one by one (up to 15 at a time) ---------------------------------------------------------------------- Batch 1 - Frima Batch 1 - Frima @Mathieu.Roy @Charles.Rheaume @MarcAndre.Cossette @Laurie.Bernard @Maryeve.Boivin @Fourat.Jellouli @Maxime.Vaillancourt @Danick.Carpenter @Steven.Comeau @Michael.Desharnais @Camille.Gendreau @Samuel.Carrier @Annick.Dunn @David.Savard Batch 2 - Frima+Ben @JeanGabryel.Caron @Katheryne.Bergeron @Olivier.Levesque @Jean-Simon.Racine @Alex.St-Louis @Alexandre.Turgeon @Remi.Senechal @Anthony.Lamoureux @Edson.Goncalves @Velystia.Cloutier @Francois.Guimond @Ben.Massoglia @Scott.Sevon @Haley.Nelson @Michael.Krkuc @matthew.geisen @amanda.perry @alison.mckenzie | Maybe?
PROD | RM | Create Release Request | TODO | 2025-01-06 |  | JIRA Ticket: LINK | 1. Go to the Release Ticket Template 2. More > Clone 3. Change name to: [FN] CHECKLIST_VERSION Release 4. Put the name+link to the ticket in cell F3 5. Set Fix Version to CHECKLIST_VERSION |  |  | Yes
PROD | RM | Create Release JIRA Dashboard | TODO | 2025-01-06 |  | Dashboard: LINK | 1. Go to the Release Dashboard Template 2. Go to the "..." on the top right and Copy Dashboard 3. Change name to: CHECKLIST_VERSION Release Dashboard 4. Set "Add Viewers: Group to Any Logged In User and press +Add 5. Set "Add Editors" to the AD-Jira-FNRM Group +Add 6. When complete, Press Add at the bottom 7. Go to the bottom of the dashboard to the 2 Controller Widgets a. Set the RED Affect Version & BLUE Fix Version to the CHECKLIST_VERSION (there are duplicate entries but they are all the same so just select 1) 8. Add the Burndown chart using the steps in column H | Steps for adding Release Burndown Chart: ---------------------------------------------------------------------- 1. Go to the Release Burndown Template Tab > Duplicate and rename 2. Add Branch Open Date (C2) using the FN Release Schedule Sheet (row 16) 3. Adjust the other milestone gates (column A) to thier corresponding rows for their dates using the FN Release Schedule Sheet 4. In the ReleaseList Tab, copy cells B3/B4 and paste into B2 a. If B2 is currently set to a version that has NOT been deployed, DO NOT OVERWRITE IT. 5. Input as a string "CHECKLIST_VERSION" into Cell B4 6. Edit the title of the graph to this checklist's version tab (double click text) a. 3 vertical dots on graph > Publish > Link tab > copy link 7. Go back to this checklist's version Dashboard > JIRA Burndown > 3 horizontal dots > Paste in External Page Link |  | Maybe?
PROD | RM | Set Slack channel Topic to Release Manager and Dashboard Link | TODO | 2025-01-06 |  |  | 1. Go to fn-release-CHECKLIST-VERSION-ext channel 2. Select the channel name at the top 3. Enter the suggested text in Column H in the Topic Section a. Person 1/2 are row 22 of the FN Schedule Sheet b. Set the Fix and Affects Version prior to creating the Dashboard Link from Controller (bottom right widget) with "..." > "Generate Permalink" > Right Click & Copy Link i. Go to Rebrandly > New Link > Paste Permalink > Leave Branded Domain > Set Signature slug to Release Version ii. Final should look like epic.gm/28-10 | @PERSON1 @PERSON2 ¦ Dashboard: epic.gm/CHECKLIST-VERSION ¦ Deploy JIRA: REAL-XXXX ¦ Hotfix Req epic.gm/Hotfix ~ Email `release-team-oncall` to page after office hours; epic.gm/3fl
PROD | RM | Create tab in Game Config Sheet | TODO | 2025-01-06 |  | Game Config Sheet: LINK | 1. Go to the Automated Template (Release) tab of the Game Config Sheet 2. Duplicate and rename to CHECKLIST_VERSION (LIVE_MM/DD) |  |  | Maybe?
PROD | RM | Setup Release Dashboard's Top Widget | TODO | 2025-01-06 |  | Dashboard: LINK | 1. In the Dashboard, mouse over the Schedule section > "..." > Edit 2. Using the template in column H, replace the red text with the appropriate info a. RM owners from the Release Schedule b. Game Config from tab's link c. Copy slack channel's link | <div class="left"> <h3>Release Schedules</h3> <ul> <li> <strong>Google Sheets:</strong> <a href="https://docs.google.com/spreadsheets/d/11P9U3a6TDH-u8mR6ynIKFpqGKaMxSe-NbvfAmt42iIY/edit?gid=2068775089/" target="_blank">FN Release Schedule </a></li> <li> <strong>Air Table:</strong> <a href="https://airtable.com/appTMZnv3FFYvaEf5/pagXaUnRze2SaaSDS/" target="_blank">Milestone Calendar </a></li> <li> <strong>Google Calendar:</strong> <a href="https://calendar.google.com/calendar?cid=ZXBpY2dhbWVzLmNvbV84ZXIzOG1oZXV1djFzZXEyNzltNmg0dmQ3OEBncm91cC5jYWxlbmRhci5nb29nbGUuY29t" target="_blank"> Add To My Google Calendar</a></li> </ul></div> <div class="right"> <h3>RMs: PERSON_1 & PERSON2 </h3> <ul> <li> <strong>Roadmap:</strong> <a href="https://airtable.com/appachk0WfaFrftUG/pagfMvTQneR53xcwj" target="_blank">Deliverables Roadmap</a></li> <li> <strong>Bug Bids:</strong> <a href="https://wiki.it.epicgames.net/display/FORT/Bug+bids+for+CHECKLIST_VERSION" target="_blank">CHECKLIST_VERSION Bug Bids</a></li> <li> <strong>Game Config:</strong> <a href="https://docs.google.com/spreadsheets/d/1w5PQcnciR-lbbU6H6m0aaqgiFWNRbttSr7uEoCmKUzk/edit#gid=XXXXXXX" target="_blank">Hotfix Game Config Tracking</a> </li> <li> <strong>Slack:</strong> <a href="https://epicgames.slack.com/archives/XXXXXXXX" target="_blank"> #fn-release-CHECKLIST-VERSION-ext</a> </li> <div><font color="red"><b>First time viewing dashboard and numbers are large: </b></font>Scroll down to bottom and update FixVersion and AffectsVersion to desired release. It will save the cookies for next view. </div> </ul></div> <style type="text/css"> table {margin-left:20px;} div.left{float:left} div.right{margin-left:350px} li {padding-bottom: 5px;} .tg {border-collapse:collapse;border-spacing:0;border-color:#ccc;} .tg td{font-family:Arial, sans-serif;font-size:14px;padding:10px 5px;border-style:solid;border-width:1px;overflow:hidden;word-break:normal;border-color:#ccc;color:#333;background-color:#fff;} .tg th{font-family:Arial, sans-serif;font-size:14px;font-weight:normal;padding:10px 5px;border-style:solid;border-width:1px;overflow:hidden;word-break:normal;border-color:#ccc;color:#333;background-color:#f0f0f0;} .tg .header{font-weight:bold;background-color:#f0f0f0;border-color:inherit;text-align:center;vertical-align:top} .tg .data{border-color:inherit;vertical-align:top} </style> |  | Maybe?
OPS | RM | Update MOTD in UGS to have Lockdown dates & JIRA filter link Wiki Old Wiki | TODO | 2025-01-06 |  | Commit CL: 12345 Robo Resolve CL: 12345 | 1. Go to the following file in P4 while in the same workspace //Fortnite/release-CHECKLIST_VERSION/FortniteGame/Build/UnrealGameSync.ini 2. Get latest > Checkout and Open 3. Create a pending CL using the suggested P4 Description in Column H --> 4. Scroll to the bottom of file 5. Copy the Message text from PREVIOUS_VERSION's block of code and overwrite CHECKLIST_VERSIONS's lime 6. Add the dates from FN Release Calendar 7. Edit and check the link to the dashboard to ensure its working 8. Save and commit CL using the submit tool You will run into a robomerge conflict. Here is how to resolve that: 1. Use robomerge to make a shelf in the downstream branch of the conflict 2. Unshelve the file in this new pending CL 3. Get latest on the file 4. RC > Resolve 5. Run Merge Tool 6. Scroll down to the conflict (or use the red arrows at the top) and remove the Yellow & Green blocks of text (leaving the blue one). 7. Save and open the file to ensure the intended changes are there 8. Once satisfied, commit the file, and hit retry on the robomerge blocker to ensure that is resolved correctly. | Updated Lockdown Dates & JIRA Filter Link on MOTD in UGS for CHECKLIST_VERSION #jira none #rnx #fyi stan.hormell | Message=:alert: Hard Lock = MM/DD 8PM ET ¦ Pencils Down = MM/DD 8PM ET ¦ CertSub = MM/DD 9am ET ¦ Release = MM/DD 4am ET [Jira Dashboard](https://epic.gm/CHECKLIST-VERSION)
OPS | RM | Only done if this checklist is for a version immediately prior to a XX.00 Version Otherwise N/A Update DEV-FN-XX MOTD to notify it is being sunset and to stop working in it (as we will be archiving the Dev-FN-XX branch) | TODO | 2025-01-06 |  | Commit CL: 12345 Robo Resolve CL: 12345 Do this checklist item if this checklist is for a version immediately before a XX.00 version (as the Dev-FN-XX branch is no longer valid for work - Since it should be done in the explicit Release-CHECKLIST_VERSION branch) | 1. Go to the following file in P4 while in the same workspace //Fortnite/Dev-FN-XX/FortniteGame/Build/UnrealGameSync.ini 2. Get latest > Checkout and Open 3. Create a pending CL using the suggested P4 Description in Column H --> 4. Scroll to the bottom of file 5. Copy text from column i and overwrite the "Message=.... text currently in the file" 6. Save and commit CL using the submit tool You will run into a robomerge conflict. Here is how to resolve that: 1. Use robomerge to make a shelf in the downstream branch of the conflict 2. Unshelve the file in this new pending CL 3. Get latest on the file 4. RC > Resolve 5. Run Merge Tool 6. Scroll down to the conflict (or use the red arrows at the top) and remove the Yellow & Green blocks of text (leaving the blue one). 7. Save and open the file to ensure the intended changes are there 8. Once satisfied, commit the file, and hit retry on the robomerge blocker to ensure that is resolved correctly. | Updated Dev-FN-XX MOTD to note this branch is no longer valid for work. All work moving forward should be done in CHECKLIST_VERSION #jira none #rnx #fyi stan.hormell | Message=:alert: THIS BRANCH IS NOW DEPRECATED AND SHOULD NOT BE COMMITTED TO MOVING FORWARD! Please commit previously associated work into the new explicit CHECKLIST_VERSION branch. StatusPanelColor=#ff0000
OPS | RM | Verify UGS MOTD in Main shows the below information (completed by #buildfarm-support-ext) - Main is now NEXT_MAJOR_VERSION - Target Release-NEXT_MAJOR_VERSION+ - Branch Creation Date - Branch Open Date | TODO | 2025-01-06 |  |  | 1. Open UGS 2. Go to the Main Tab (need to import the project's .uproject file) 3. Verify you see the correct information
PROD | RM | Cross check Fortnite Release Calendar below dates are accurate for all versions from this checklist's season and the following season found in the FN Release Schedule and populated from the Air Table - Row 16: Branch Opening - Row 17: Development Complete - Row 18: Hard Lock - Row 19: Pencils Down - Row 20: Cert Sub - Row 5: Live - Row 5 of next column(s): HF(s) Live | TODO | 2025-01-06 |  | Alternate AirTable Link | 1. Go to the FN Release Schedule to get the dates 2. Go to Google Calendar and search for CHECKLIST_VERSION 3. Ensure the dates from the Release Schedule are present in Google Calendar (This is driven by AirTable Automation) a. If there are any discrepancies, flag it to the release management team |  |  | Yes
PROD | RM | Create a Jira for BR Calendar/Store/Shop to be update/reviewed | TODO | 2025-01-06 |  | JIRA Ticket: LINK | 1. Go to the JIRA Template 2. Move > Clone 3. Rename ticket in the format: ¦Shop¦ Verify ROW Store/Calendar (BR) for [CHECKLIST_VERSION] Deploy Scheduled for [MM/DD] 4. Add as "Watchers" and CC the following in the comments (copy below and paste in TEXT vs VISUAL) *CC:* [~juan.romero] [~nick.owens] [~steve.allison] [~amanda.perry] [~matthew.geisen] [~alison.mckenzie] 5. Set Fix Version to CHECKLIST_VERSION |  |  | Yes
PROD | RM | Verify BranchFoundIn in JIRA is already populated for CHECKLIST_VERSION if not, request it be done in #fn-jira-admins-ext | TODO | 2025-01-06 |  | Slack: LINK | 1. Go to JIRA > Create (blue button at top) 2. Look for BranchFoundIn 3. Type in Release-CHECKLIST_VERSION a. If it is present, you are done. If not, go to step 4. 4. Spin up a post in #fn-jira-admins-ext using the suggested text in Column H | Hello JIRA Admins, Could you please add `Release-CHECKLIST_VERSION` as an option in the BranchFoundIn dropdown? Thanks in advance! |  | Maybe?
PROD | RM | Schedule Google Calendar Meeting: Stability Sync | TODO | 2025-01-06 |  | Calendar Event: LINK | 1. Go to the Google Calendar 2. Search for Stability Sync and go to the previous release's event 3. Duplicate the card and update the following: a. Event Title (Set to correct version) b. Date (set to 10am the morning of release date) c. Zoom Meeting (remove and add a new one to account for duping even wonkiness) 4. If not already on the previous event when duping. ensure the following people/groups are added: a. Chris Tran, Alex Ruse, Tyler Buczek, Jay Chaney b. fn-tech-production c. Release-Team d. ReleaseQA |  |  | Yes
PROD | RM | Schedule Google Calendar Meeting: Post Mortem | TODO | 2025-01-06 |  | Calendar Event: LINK Post Mortem Sheet: LINK | 1. Go to the Google Calendar 2. Search for Post Mortem and go to the previous release's event 3. Duplicate the card and update the following: a. Event Title (Set to correct version) b. Date (set to the Thursday following the release date) c. Zoom Meeting Use this - the link to our shared zoom where we will use the RQA break out room d. Post Mortem Sheet Link (set to applicable tab - If not created, make the tab) 4. If not already on the previous event when duping, ensure the following groups are added: a. fn-release b. Release-Team (embedded in the 4a. group) c. liveqa@epicgames.com |  |  | Yes
PROD | RM | Schedule Calendar Events: - Hard Lock - Pencils Down | TODO | 2025-01-06 |  |  | 1. Go to the Google Calendar 2. Search for Hard Lock and go to the previous release's event (should be at 8PM ET) 3. Duplicate the card and update the following: a. Event Title (Set to correct version) 4. Repeat steps 2-3 for the Pencils Down calendar event. |  |  | Yes
PROD | RM | Determine Deploy Time with the below teams: - Live Ops - Competitive - Publishing/Marketing | TODO | 2025-01-06 |  | Deploy Types and Times: Season Release time of `2:00am ET` Dot Release time of `4:00am ET` Unforced Emergency Patches: 8:00am ET Slack: LINK | 1. Spin up a post in the fn-release-CHECKLIST-VERSION-ext channel using the suggested text in Column H/I 2. Once agreed upon, Bold+Underline the selected time in column F to easily identify what we settled on without having to go back to the thread | Deploy Time Alignment for Checklist_Version on Fri Feb 21 :thread: | Hello @release-team @releaseqa @competitive-ops @epic-liveops @Laura.Stone @Paris.Nourmohammadi Just wanted to get everyone together to align on the deploy time for CHECKLIST_VERSION. Any objections to going with our usual INSERT_TEXT_FROM_COL_F? | Yes
OPS | RM | Enable the following Scheduled Horde Jobs 1. Nightly Build with Build Health 2. Nightly Data Rebuild 3. World Partition Build 4. Juno Limited Build WIKI If this checklist is for a XX.00 version, also enable these for the Dev-FN-NN branch | TODO | 2025-01-06 |  | Commit CL: 12345 | 1. Go to here in P4: //Fortnite/Main/FortniteGame/Build/Streams/fortnite-release-CHECKLIST_VERSION.stream.json 2. Get Latest & Check out and open file 3. Create a shelf using the suggested P4 Description in Column H --> 4. Find "Nightly Build with Build Health" 5. In the "schedule" section > change "enabled": true to "enabled": false 6. Repeat steps 4-5 for: a. "Nightly Data Rebuild" b. "World Partition Build" c. "Juno Limited Build" 7. Save and commit in P4 8. Send courtesy message in Slack to #buildfarm-support-ext using the suggested P4 Description in Column I --> If this checklist is for a XX.00 version, also enable these for the Dev-FN-NN branch | Enabling the below jobs for Release-CHECKLIST_VERSION: - Nightly Build - Nightly Data Rebuild - World Partition Build - Juno Limited Build #jira none #rnx #fyi stan.hormell, swarm-ue-build-reviews | Hi Build Farm, just wanted to inform you that we enabled the below jobs for CHECKLIST_VERSION at CL XXXXX. - Nightly Builds - Nightly Data Rebuild - World Partition Build - Juno Limited Build That's all!
PROD | RM | Now that every deploy is a "Season Launch": Create Season Run of Show sheet for orchestrating the teams Normal Release: 2x First Check-In: 8 days before live date Last Check-In: 1 day before live date Season Launch: 3x First Check-In: 15 days before live date Second Check-In: 8 days before live date Last Check-In: 1 day before live date | TODO | 2025-01-06 |  | Do we want to standardize 1st check in to land the day before PD so any last minute changes can come in before then?? ROS Sheet - See F4 ROS Zoom - See F5 | Before running through the following, check the season folder to see if the RoS has already been created. If so, skip to Step 3 1. Duplicate the Master TEMPLATE 2. Rename to CHECKLIST_VERSION Run of Show & set the deploy date in cell I1 3. Duplicate previous instance(s) of the Run Of Show Calendar Events in the Fortnite Release Team Calendar and set to dates outlined in column B 4. Remove existing zoom link and re-add to ensure they work properly. Add the same zoom link to all instances of the 2 or 3 calendar events as well as adding the link to Cell E1 in the RoS 5. Search the list for anyone that may not be with the company and remove them to avoid bounce back emails a. Look for blank profile pics and first.last@epicgames.com OR by searching for the * character and remove those if they don't exist in slack 6. Search google calendar for a previous instance of the Launch Room (previously War Room) calendar event and duplicate it (ensure its set to the Fortnite Release Calendar) and set to the day of deploy. Remove its zoom link and add the same one used for the RoS meetings a. Ensure Jamie Domach, Zach Moore & Jonathan Titus Are included b. Go to https://epicgames.zoom.us/ and sign into account i. Scroll down to the bottom section's Alternative Hosts and add Stan Hormell and Nick Bentham ii. Select the Breakout Room pre-assign and click the "+" icon 10x and save 7. Go to the Release-CHECKLIST_VERSION slack channel and create a Bookmark Folder titled Run of Show. a. Add a link to the RoS Sheet b. Add a link to the Deploy Day Launch Zoom c. Add a link to the Deploy Day Launch Zoom Calendar Event 8. Reach out to publishing to let them know the RoS has been created a. Currently Paris Nourmohammadi Laura Stone Michael Micholic | :fyi: @Paris Nourmohammadi @Laura Stone @Michael Micholic The CHECKLIST_VERSION Run of Show has been created for both Fortnite & Publishing coordination and links have been added to the Run of Show folder in this channel. Please let us know if you were planning on tracking work elsewhere as we would like to avoid potential "thread splitting" :ty: in advance! |  | Yes
Likely remove, should fall under the teams owning testing of these | RM | Ensure TestFlight Beta App Review has been submitted | TODO | 2025-01-06 |  | Slack: LINK | 1. Track review in Apple Cert Timing Tracker a. If info has not been filled out, reach out to Chris Etuk for a status update in the fn-release-CHECKLIST-VERSION-ext channel using the suggested text in column H/I Alternatively you can see if TestFlight Beta Review has been submitted by enabling notifications in sweden on your AppStore Connect profile and filtering your email for the following "has words" "Your app Fortnite (6483539426) has been approved for beta testing" | :apple-neon: CHECKLIST_VERSION TestFlight Beta App Review Status :apple-deal: | Hey @chris Etuk I noticed that we haven't submitted a CHECKLIST_VERSION build to TestFlight Beta yet. Any plan for when that will happen?
|  | By Hard Lock: | IN PROGRESS
PROD | RM | For XX.00 Deploys Only: Reminder messaging for seasonal Hotfix clean up | TODO | 2025-01-27 |  | Slack: LINK | 1. Spin up a post in the fn-release-CHECKLIST-VERSION-ext channel using the suggested text in Column H/I | Seasonal Hotfix Cleanup reminder for Release-CHECKLIST_VERSION Please respond by the end of day, {Day}, {Date} 5:00PM EST, if you have hotfix syntax that needs to persist and cannot be baked in. If not, your syntax may get wiped after the clean up. (Timing in the above messaging should align with first whiteglove?) | It's time to cleanup the hotfix files with a new season release. This is to maintain a clean and minimal list of changes in the files. Teams should be proactively baking in their changes release over release and requesting clean ups in the game config sheet. Unfortunately, this does not always happen, and leaves a lot of stale changes and bloat that is no longer needed. If there are any specific changes that must be kept, please let us know so that we can flag as DO NOT PURGE in the hotfix files ;(DNP). Thanks in advance to all that do regularly bake in and request removals. This is very much appreciated. | Yes
PROD | RM | Send Release Strategy email Confluence Wiki (need to merge all the things) Wiki on creating the meeting calendar event Template (if not copied from a previous email) | TODO | 2025-01-28 |  |  | 1. Search your email for "Release Strategy" and go to a previous release's email 2. Copy a previous email's TO:. Subject and Body (either a .00 if this checklist is a .00 or a .10/.20.30 if not) and update the following a. Version & Expected Release Timing (also confirm if downtime from 4am-5am is applicable) b. Cutoff for Deploy Strategy and Hotfix Confirm Items Date (Should be friday noon if tuesday deploy) 3. Send Email | TO: FN-Release-Updates <fn-release-updates@epicgames.com> Release Dates: FN Release Calendar | Replace with Pre-Pop | Yes
PROD | RM | Redundancy: Make sure zoom links are still valid for all meetings related to CHECKLIST_VERSION | TODO | 2025-01-28 |  |  | 1. Search Google Calendar for the release version and check the below meetings: - Stability Sync - Post Mortem 2. Click the current zoom link to try to enter as normal. If it works, you are good. 3. If you get an error, kill the current zoom link and make a new one
OPS | RM | Set NetCL Version Number | TODO | 2025-01-28 |  | Commit CL: 12345 | 1. Go to the following file in P4 while in the same workspace //Fortnite/Release-CHECKLIST_VERSION/Engine/Source/Runtime/Core/Public/Misc/NetworkVersion.h 2. Get latest > Checkout and Open 3. Create a shelf using the suggested P4 Description in Column H --> 4. In the file, search for ENGINE_NET_VERSION (should be line 12 ish) 5. If it is currently 0, set it to the CL of the Last Successful SSB/Nightly Build in Horde a. If it is not 0, verify the set CL is the CL of the Last Successful SSB/Nightly Build in Horde 6. Save and commit CL using the submit tool (must be deadended) 7. Verify via Track Change that it did not merge - https://robomerge.epicgames.net/trackchange/####### | Setting NetCL version to CL XXXXXX #jira none #okforgithub public #rnx #robomerge -Release-NEXT_VERSION #robomerge FNONLY #submittool bypass
SUB | SUB | Review the Cert issues filter to make sure nothing egregious still needs to be fixed | TODO | 2025-01-28 |  | Double check to ensure cert impacting issues have been confirmed fixed on the current candidate | Dashboard - https://jira.it.epicgames.com/secure/Dashboard.jspa?selectPageId=25898
|  | AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK |  |  | AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK | AFTER 8PM ET HARDLOCK
OPS | RM | HARDLOCK! Add Temporary Allowlisters to lockdown file | TODO | 2025-01-28 |  | Check Release's Hard Lock Calendar invite for additional instructions Commit CL: 12345 Slack: LINK | 1. Go to Allowlister Sheet and go to the appropriate release tab. 2. Copy names from Cell F2 at step 7. 3. Go to this P4 file path //Fortnite/Main/FortniteGame/Build/p4lockdown/lockdown_config.ini 4. Check out the file and Open. For the description, use the suggested text in Column H --> 5. In the file, search for [ReleaseA-Lockdown-Hardcore] and [ReleaseB-Lockdown-Hardcore] 6. Determine which list is setup for the upcoming release. If neither are, replace the older release with CHECKLIST_VERSION (See Step 2) 7. Paste the allowlisted names from step 2 after Stan.Hormell (ensure comma placement is retained). 8. Save and commit. 9. Post a message in the #fn-Release-CHECKLIST-VERSION-ext channel using the suggested text in column I | Adding Temporary Allow Listers & HardLocking CHECKLIST_VERSION #jira none #rnx | :announcement-1: CHECKLIST_VERSION is now Hardlocked and temporary allowlisted permissions have been set :lock: -- Please submit all changes through the Submit Tool using the standard integration process.
OPS | RM | Update MOTD in UGS | TODO | 2025-01-28 |  | Commit CL: 12345 Conflict Resolve CL: 678910 | 1. Go to the following file in P4 while in the same workspace //Fortnite/Release-CHECKLIST_VERSION/FortniteGame/Build/UnrealGameSync.ini 2. Get latest > Checkout and Open 3. Create a shelf using the suggested P4 Description in Column H --> 4. Scroll to the bottom of file 5. Copy text from column i and overwrite the "Message=.... text currently in the file" & StatusPanelColor 6. Add the dates from FN Release Calendar (or copy from current banner message) 7. Edit and check the link to the dashboard to ensure its working 8. Save and commit CL using the submit tool Resolving the robo conflict: 1. Remove the conflicting yellow and green lines for the text your just changed. 2. Keep the blue text which should be exactly what you just updated in the checklist branch 3. Save and commit | Updated MOTD in UGS for CHECKLIST_VERSION Hard Lock #jira none #rnx | Overwrite current message with below (update the red text) Message=:alert: THIS BRANCH IS NOW HARD LOCKED. Refer to [Branching, Lockdown, Integrations](https://confluence.it.epicgames.com/pages/viewpage.action?pageId=42600502) to submit changes ¦ Pencils Down = MM/DD 8PM EST ¦ CertSub = MM/DD 9am ET ¦ Release = MM/DD 3am ET [Jira Dashboard](https://epic.gm/CHECKLIST-VERSION) StatusPanelColor=#e20000
| By Pencils Down: |  | IN PROGRESS
OPS | RM | Update the metastream UE robomerge connection to point to NEXT_VERSION | TODO | 2025-01-29 |  | Slack: LINK | 1. Go to the Robomerge Bot Setup 2. Look to see if //UE5/Dev-Release is pointing to NEXT_VERSION a. if yes, DONE the check b. if no, go to #epic-release-managers-ext and post using the suggested text in Column H | @Marc Audy @release-team CHECKLIST_VERSION has been hardlocked :lock: Please update the metastream UE robomerge connection to the next FN release if that applies in this case.
OPS | RM | Redundancy Verify NetCL was set correctly and did not merge | TODO | 2025-01-31 |  | Robomerge Track Change Link: | 1. Open Robomerge Track Change and input the CL from HERE a. if the change did not merge, we are good b. if the change DID merge, WHAT ARE THE NEXT STEPS HERE?? c. if someone forgot to add the commit CL to the original task (shame on them and), run through the steps HERE
OPS | RM | Ensure code only builds are working properly including verification it can be successfully promoted Be sure to include iOS for build and promotion steps | TODO | 2025-02-05 |  | Code Only Build: LINK ++CL: 123456 Android Promotion to ReleaseStaging: LINK All Platform Promotion Job: LINK Link(s) to Error/Warning Thread(s): - Link 1 - Link 2 | PART 1: 1. Navigate to //Fortnite/Release-CHECKLIST_VERSION's Builds tab in HORDE 2. Copy the CL of the last passing build 3. New Job > Minimal Code Only Build 4. Set the Base Change to the last passing build you copied 5. Set the Change CL to a green incremental's CL 6. Go to the Advanced Tab and in the JOB NAME input: CHECKLIST_VERSION MCO Creation TEST 7. Start Job a. escalate errors/warnings to #fn-build-health-ext or #buildfarm-support-ext (if applicable) for fixes 8. Once complete, move onto the next part where we will promote Android to FortniteReleaseStage PART 2: 1. Copy the ++CL from the above job and go to THIS link (which will retain all the necessary setup parameters) > Select JOB > RUN AGAIN a. Remove the CL from the CHANGE field b. Remove the ++CL from the BUILD VERSION and paste in the correct one from part 1 c. Go to the Advanced Tab and in the JOB NAME input: CHECKLIST_VERSION MCO Android Promotion TEST 2. Start Job a. escalate errors/warnings to #fn-build-health-ext or #buildfarm-support-ext (if applicable) for fixes 3. Once complete, move onto the final part where we will promote All Clients to a test backend PART 3: 1. Reach out to RQA or the Apps Team Reps on RM (currently Keaton Stewart Edwin Maynard) to see which backend to promote to for this test. a. If RQA is not in the loop, make a post in the fn-release-team channel informing them you are doing this test using the suggested text in Column I 2. Once you have an approved backend, Copy the ++CL from part 1 and go to THIS link (which will retain all the necessary setup parameters) > Select JOB > RUN AGAIN a. The link above contains all platforms. If a platform failed to build in part 1, unselect it from the PROMOTE PLATFORMS field 3. Repeat Step 1 from Part 2 with the addition of a. Select the approved backend to deploy to from the TO APP NAME dropdown b. Go to the Advanced Tab and in the JOB NAME input: CHECKLIST_VERSION MCO All Client Promotion TEST 4. Start Job a. escalate errors/warnings to #fn-build-health-ext or #buildfarm-support-ext (if applicable) for fixes 5. Once testing is complete, follow up with the person who gave you the backend to see if you need to rollback/revert your changes to restore it to its previous configuration | Need to see examples to create escalation | Hello friends! Just wanted to give you a heads up that I will be promoting a minimum code only build to `INSERT_APPROVED_BACKEND` as part of our release checklist. Please let me know if you have any questions or concerns.
OPS | RM | Lock the DAD CL | TODO | 2025-02-07 |  | Slack: LINK | 1. Go to the Data Asset Directory and select CHECKLIST_VERSION 2. Click on the newest (top of the list) CL's Blue Lock button which will turn it red and unlocked (yes it seems backwards) as well as the CL turning green 3. Once complete, spin up a post in #fn-release-CHECKLIST-VERSION-ext using the suggested text in Column H | :announcement-1: RM has locked the DAD for CHECKLIST_VERSION to CL XXXXX :lock:
PROD | RM | Request Final DAD revision for pre whiteglove They should provide the following: * Weblinks: * Browse * Library * DAD V2 (used to push live to Discover) * Browse * Library * Discover * Web (fortnite . com) | TODO | 2025-02-07 |  | Slack: LINK | 1. Go to the #fn-release-CHECKLIST-VERSION-ext and spin up a post using the suggest text in Columns H/I a. Check the FN Release Schedule or Fortnite Release Calendar for the cert date 2. After links have been provided, add them to the Game Config Sheet, for all links provided 3. Ensure that RQA is able to receive the DAD revisions prior to the weekend so weekend testing can be done by external QA teams | :dad:CHECKLIST_VERSION Final DAD Revisions:dad: | Hello there @Greg Garnhart @Kareem Al-Attar @Hana Zubovic @manu pareek Checking in on final revision delivery prior to going live on INSERT_DEPLOY_DAYnDATE As a heads up, we will be starting pre-cert checks this weekend and would like the revisions to be in place ahead of that testing if possible. Additionally any required Analytics Stuff links would be great as well. We go to cert on INSERT_CERT_DAY :) @releaseqa for viz | Yes
PROD | RM | 1st touchpoint with Calendar owners Typically you get sign off from all but BR (Shop & Non-Shop) | TODO | 2025-02-07 |  | Slack: LINK | 0. Ensure the people in column I are invited to the slack channel 1. Go to the #fn-release-CHECKLIST-VERSION-ext and spin up a post using the suggested text in Columns H/I 2. Get confirmation from each calendar owner area | :calendar: Calendar Updates for CHECKLIST_VERSION | Hi there @fn-calendar-owners Checking in on calendar promotions being setup prior to going live on INSERT_DEPLOY_DAYnDATE As a heads up, we will be starting pre-cert checks this weekend and would like the final calendar promotions to be in place ahead of that testing if possible. We go to cert on INSERT_CERT_DAY :) Please be sure to remove any leak sensitive information from any calendars that are checked into the client-events channel. Changes made to that channel will be visible to leakers as early as two hours before the scheduled event is set to go live. We'll have a follow up check-in with calendar owners closer to deploy, but flagging now to ensure this process is on your radar. Thanks in advance! STW - @Patrick.Malott BR (Non-Shop) - @DJ.Schilens BR (Shop) - @Juan.Romero @matthew.geisen @alison.mckenzie @amanda.perry LTM - @scott.sevon @haley.nelson @michael.krkuc Juno/Sprout (need confirmation on both) - @Tyler.Yungmann @Keith.Leiker @Jason.Kanagaratnam @Steven.Tarry @Alec.Fisher-Lasky Sparks - @Kyle Wynn DelMar - @Daniel.Nguyen @Andrew.Rimpici OG - @DJ.Schilens
OPS | RM | Set up Modes & Tags in FleetMan for Release QA Whiteglove WIKI | TODO | 2025-02-07 |  | Slack: LINK | 1. Go to the Fleetman Release page and select CHECKLIST_VERSION 2. If you see a blue banner stating No Tags Defined, continue. 3. Select the Import Button (right of Mode Configurations) > Select the previous version from the dropdown 4. Select All (above ID column) to check all boxes 5. Select the Import Button to confirm 6. Scroll down to the bottom of the page and select the Import Button (right of Tags) > Select the previous version from the dropdown 7. Select the Confirm checkbox > Import 8. Once complete, send a message to fn-release-team using the suggested text in Column H | :announcement-1: Just a heads up, we have set up CHECKLIST_VERSION Modes & Tags in FleetMan in preparation of WhiteGloves!ves on the weekend
|  | AFTER 8PM ET PENCILS DOWN | AFTER 8PM ET PENCILS DOWN |  |  | AFTER 8PM ET PENCILS DOWN | AFTER 8PM ET PENCILS DOWN | AFTER 8PM ET PENCILS DOWN | AFTER 8PM ET PENCILS DOWN
OPS | RM | Remove Temporary Allow Listed - 8PM ET WIKI | TODO | 2025-02-07 |  | Commit CL: 12345 Slack: LINK | 1. Go to this P4 file path //Fortnite/Main/FortniteGame/Build/p4lockdown/lockdown_config.ini 2. Check out the file and Open. For the description, use the suggested text in Column H --> 3. In the file, search for [ReleaseA-Lockdown-Hardcore] and [ReleaseB-Lockdown-Hardcore] 4. Find the list that corresponds to CHECKLIST_VERSION 5. Delete the names that come after Stan.Hormell (ensure there is no comma after Stans name). 6. Navigate to the [Release-Archive-Hardcore] section and remove the version corresponding to this checklist 7. Save and commit. 8. Post in the #fn-Release-CHECKLIST-VERSION-ext Slack Channel using the suggested text in column I | 1. Removing Temporary Allow Listers for CHECKLIST_VERSION Pencils Down 2. Removing CHECKLIST_VERSION from [Release-Archive-Hardcore] #jira none #rnx | :announcement-1: CHECKLIST_VERSION is now Pencils Down and temporary allowlisted permissions have been revoked:pencilsdown: -- Everyone must now submit any changes through the Submit Tool using the standard integration process.
OPS | RM | Enable Robomerge Gate - 8PM ET This will create a post in the integrations channel if someone attempts to robomerge a change up to the Pencils Down branch | TODO | 2025-02-07 |  | Commit CL: 12345 | 1. Go to this P4 file path //GamePlugins/Main/Programs/RoboMerge/data/fortnite.branchmap.json 2. Check out the file and Open. For the description, use the suggested text in Column H --> 3. In the file, search for EDGES 4. Set "from" to NEXT_VERSION 5. Set "to" to the CHECKLIST_VERSION 6. Use the Robomerge preview feature to ensure that there are no parsing issues (right click the pending CL in p4v and choose Robomerge Preview Graph from UE Toolbox) eg. https://robomerge.epicgames.net/preview/33192043 7. Save and commit. [example] | Adding CHECKLIST_VERSION <~~ NEXT_VERSION Robomerge Gate Alert #jira none #rnx #fyi stan.hormell, swarm-ue-build-reviews
SUB | SUB | Verify that the PS5/PS4 versioning is correct for the release. | TODO | 2025-02-07 |  |  | 1. Open the P drive and locate a recent build in this release branch. 2. Verify that the PS4 and PS5 build versions are correctly incremented from the previous release. *Previous release app versions can be found on the Release Log.
SUB | SUB | Make sure SwitchEngine version has been incremented. | TODO | 2025-02-07 |  |  | 1. Open the P4 navigate to the following file: Release-XX.XX > FortniteGame > Platforms > Switch > Config > SwitchEngine.ini 2. Verify that the Application Version, and ApplicationVersionString have been appropriately updated. *Previous Release version can be found on the Release Log.
SUB | SUB | Verify that LatestPatch folder contains last released patches | TODO | 2025-02-07 |  |  | 1. Navigate to the Latest Patch folder on the P drive: P:\Builds\Fortnite\MasterReleases\1.0 2. Open the appropriate folders for PS4/PS5/XB1/XSX and verify that the previous release versions have been updated to the last patch that successfully compeleted certification.
Pre-Candidate Build
| By Cert Submission: |  | IN PROGRESS
SUB | SUB | Request Patches: Email Xbox Account Manager | TODO | 2025-02-09 |  |  | "TO: Derek Russel <deruss@microsoft.com>, Epic Games WAM <epicwam@microsoft.com> CC: Release-team"
SUB | SUB | Verify Xbox Submission Validator logs do not have any warnings or errors | TODO | 2025-02-09 |  |  | 1. Go to any CHECKLIST_VERSION completed build on the P drive in the following example path P:\Builds\Fortnite\++Fortnite+Release-CHECKLIST_VERSION-CL-12345678 2. Go to the XB1Client folder > FullPackages folder and open the Validator_xxxxx link (bottom of list) 3. Search for the string "<ValidationSummary>" (or look for the 3rd dropdown) to view the results 4. Repeat steps 2-3 this for all Xbox Folders (ex. XSX) 5. If it says anything other than 0 Total Warnings / 0 Total Failures, start a thread in the release-CHECKLIST_VERSION slack channel and loop in the Tech-Console Component Owners (primarily Mickael Gilabert)
SUB | SUB | Send Akamai early estimate of patch sizes - Email | TODO | 2025-02-09
SUB | SUB | Notify Nvidia of the upcoming patch date and time - Email | TODO | 2025-02-09 |  |  | Email: GFN-DevOps-External@nvidia.com, ssolovyev@nvidia.com fliljegren@nvidia.com Format: MM/DD/YYYY, TIME_UTC_24H Example - 08/27/2018, 08:00 UTC
SUB | SUB | Notify AWS of the upcoming patch date, time, and sizes - Email | TODO | 2025-02-09 |  |  | epicgames-events@amazon.com
SUB | SUB | Notify Fastly of the upcoming patch date, time, and patch sizes - Slack Post | TODO | 2025-02-09 |  |  | #fastly-epicgames
SUB | SUB | Notify Akamai of the upcoming patch date, time, and patch sizes - Slack Post | TODO | 2025-02-09 |  |  | #vndr-akamai-ext
SUB | SUB | Notify Cloudflare channel of the upcoming patch date, time, and patch sizes - Slack Post | TODO | 2025-02-09 |  |  | #vndr-aws-egs-cloudfront-ext #vndr-cloudflare-ext
SUB | SUB | Notify ISP email group alias of the upcoming patch date, time and patch sizes - Email | TODO | 2025-02-09 |  |  | ext-fn-release-notify@epicgames.com
SUB | SUB | Update DevNet Thread with Incoming Patch Information | TODO | 2025-02-09 |  |  | PS4 and PS5
SUB | SUB | Request Patches: Create New Release for Nintendo | TODO | 2025-02-09
SUB | SUB | Request Patches: Fill out and submit new OMAS for Nintendo | TODO | 2025-02-09
SUB | SUB | Request Patches: SIEA (07022) - WIKI | TODO | 2025-02-09
SUB | SUB | Request Patches: SIEE (07669) - WIKI | TODO | 2025-02-09
SUB | SUB | Request Patches: PS5 Shared | TODO | 2025-02-09
SUB | SUB | Create Version on App Store Connect and check if any Publishing metadata updates are needed | TODO | 2025-02-09 |  |  | 1. Go to https://appstoreconnect.apple.com/apps 2. Select Fortnite 3. From the Distribution tab, in the left-hand column click the (+) button to add a new version if it does not already exist (Only two versions can be in at one time: the Live build and the Next build) 4. Sanity check that the metadata has carried over correctly 5. Confirm with publishing (Alex Conner/Emu Servais) if any screenshots or text need to be updated (The data present in App Store connect only appears in the App Installation Sheet, when confirming to install Fortnite. EGS metadata is found in Product Framework) * What's New in This Version -- metadata is not required as per 2.3.12 (listed as n/a for Notarization Review Guidelines Only) | :apple-bounce: CHECKLIST_VERSION App Store Connect Metadata | @Alex Conner @Ross Marabella @Zach Moore Are we planning on changing any of the screenshots or text on the iOS App Store Connect portal for CHECKLIST_VERSION? I am assuming no but would rather ask for sanity sake. :ty: in advance!
PROD | RM | Redundancy Request Final DAD Links for WG testing: They should provide the following: * Weblinks: * Browse * Library * DAD V2 (used to push live to Discover) * Browse * Library * Discover * Web (fortnite . com) | TODO | 2025-02-11 |  | Final Dad CL: 12345 | 1. Continue follow up in the original thread from row 68 using the suggested text in Columns I a. Once the final info is provided, continue to step 2 2. Go to this link, replace the XX,XX with CHECKLIST_VERSION and refresh the page. 3. Reconfirm the CL is green and has a red UNLOCK icon. 4. Verify locked CL matches the CL in the 3 links provided in step 1a. |  | Checking in on final revision delivery. Anything to update since our last request above? We are starting pre-cert checks INSERT_DAY and want to ensure QA is running their :whiteglove-wave: with the most accurate info. We are still targeting to go to cert on INSERT_CERT_DAY :smiley: | Maybe?
PROD | RM | Ensure Final Shop is in for WG testing | TODO | 2025-02-11 |  | Final Shop CL: 12345 | 1. Send message in the #fn-release-CHECKLIST-VERSION-ext channel using the suggested text in Columns H/I | :shopping_bags: CHECKLIST_VERSION Final Shop Changes :shopping_bags: | Hello there @juan romero @nick.owens @Steve.Allison @amanda.perry @Matthew.Geisen @alison.McKenzie Just double checking in on final shop delivery. Anything else coming in hot? I see the last committed change on INSERT_JIRA_FROM_ROW46 is FIX_CL_FROM_JIRA We are starting pre-cert checks INSERT_DAY and want to ensure QA is running their :whiteglove-wave: against the final shop revisions if they are locked in. We are targeting to go to cert on INSERT_CERT_DAY :smiley: | Yes
SUB | SUB | Verify the file system captures for Nintendo have been gathered by QA | TODO | 2025-02-12 |  | Slack: LINK | Details in this document https://docs.google.com/document/d/1krb18jjtEBn10duEBgaiklnLnN55RE5raKLL4acSX3c/edit#heading=h.xd3o88dyuuik Example Post
PROD | RM | Send Last Call bump for callouts in the Release Strategy Email. WIKI | TODO | 2025-02-12 |  |  | 1. Go to your email and search for the "CHECKLIST_VERSION Release Strategy" 2. Send a follow up email using the suggested text in Column H a. Deadline for a Tuesday deploy is noon on the Friday b. Deadline for a Friday deploy is noon on the Tuesday | Bumping the thread here for any last minute CHECKLIST_VERSION Call Outs Recopy the deadline line from the original email in again | Replace with Pre-Pop | Yes
PROD | RM | Determine Ship List (using the below Airtable) and pin it in Slack New Hotness: Deliverables Roadmap Build View | TODO | 2025-02-12 |  | Slack: LINK | 1. Go to the Deliverables Roadmap and set the filter date to the deploy date 2. Compile a list of all changes going into the release using the format in Column H 3. Post to #fn-release-CHECKLIST-VERSION-ext channel and Pin the message. Example Here | CHECKLIST_VERSION Ship List :ship: - Items/Gameplay: XXX - REGS/Quests: XXX - Creative: XXX :exclamation: Disclaimer: :exclamation: If there is anything missing or incorrect with this list, please have the corresponding owners update the Airtable from which this information is taken from (Deliverables Roadmap) |  | Yes
OPS Need to make an additional Embedded item | RM | Identify team for release day and update Release Request | TODO | 2025-02-12 |  | Slack Links: LiveOps ReleaseQA Community Tech Console | 1. Message the below groups using the suggested text in Column H. a. LiveOps b. ReleaseQA c. Community d. Release Management - Row 24 e. Tech Console | Hey INSERT_GROUP Team! Who is your representative for the upcoming CHECKLIST_VERSION release? Once you know, please add the name(s) to the corresponding place in the `People On Duty` section of REAL-1234 's description. :ty: in advance! | Release Managers: Hey PERSON_LISTED_IN_SHEET: You all good to own the upcoming CHECKLIST_VERSION release? Looks like you are on the FN Release Schedule for it. If so, I'll make sure to get you added to our REAL-XXX ticket for tracking. Thanks! | Yes
PROD | RM | Whiteglove has been completed on INITIAL release candidate (aka crit checks) and issues called out have been threaded/escalated for triage Note: We will never be releasing this build. There will always be another CL for our final candidate (THIS LINE) | TODO | 2025-02-12 |  | Slack WG: LINK | 1. Go to #fn-release-CHECKLIST-VERSION-ext and search for "Fortnite CHECKLIST_VERSION Whiteglove:" a. This should bring up all instances of whitegloves bring run 2. Ensure RQA completes the Client WG the day before cert submission (ideally 2 days before) a. You can track progress in TestRail (STC) if you have access 3. Ensure issues called out from the WG are appropriately threaded (outside the WG thread) and triaged in the #fn-release-CHECKLIST-VERSION-ext channel
OPS | RM | Kick Cert Build | TODO | 2025-02-12 |  | Last Committed CL: 12345 WPB CL: 12345 NDR CL: 12345 Nightly CL: 12345 | 1. Commit remaining changes 2. Ensure World Partition Build & Nightly Data Rebuild jobs have been kicked at a CL AFTER the last committed change a. If they kicked too early, cancel and rekick using their templates b. Make sure the canceled jobs have completed before kicking the new jobs or issues can arise 3. Ensure both jobs complete with no issues a. if errors/warnings, escalate (WPB - Sebastian Lussier, NDR - INSERT) 4. Kick Nightly build at a CL AFTER the 2 above jobs
PROD | RM | Check-in: Create Slack thread in release channel for Game Config Owners to confirm | TODO | 2025-02-13 |  | Slack: LINK | 1. Go to the CHECKLIST_VERSION tab in the Game Config Sheet 2. Create Slack Thread using template in columns H/I and tag in Component Owner and Dev Owner to confirm Ask Alex for access to worksheet to make a little bit better EXAMPLE HERE | CHECKLIST_VERSION Game Config Check-in :thread: | Hello! We are double-checking on CHECKLIST_VERSION Game Config requests. Please review the above sheet to ensure we are not missing any changes. [Component] [@ Component Owner] - [@ Dev Owner (column E)] [Hotfix Description (column A)] | Maybe?
OPS | RM | Disable Standard Scheduled Builds for CHECKLIST_VERSION branch Enable Standard Scheduled Builds for the next TWO branches (NEXT_VERSION and NEXT+1_VERSION) WIKI | TODO | 2025-02-13 |  | Commit CL: 12345 Slack: LINK | 1. Go to here in P4: //Fortnite/Main/FortniteGame/Build/Streams/fortnite-release-CHECKLIST_VERSION.stream.json 2. Select this file as well as the 2 .json files for the following 2 branch versions 3. Check out and open file 4. Create a shelf using the suggested P4 Description in Column H --> 5. Find: Scheduled Standard Build with Build Health 6 In the ""schedule"" section, change ""enabled"": true to ""enabled"": false 7. Save and commit in P4 8. Send courtesy message in Slack to #buildfarm-support-ext using the suggested P4 Description in Column I --> | Disabling Scheduled Standard Build job for Release-CHECKLIST_VERSION Enabling Scheduled Standard Build job for Release-NEXT_VERSION & Release-NEXT+1_VERSION #jira none #rnx #fyi stan.hormell, swarm-ue-build-reviews | Hi Build Farm! Just wanted to inform you that we disabled the Scheduled Standard Build job for CHECKLIST_VERSION and enabled it for NEXT_VERSION & NEXT+1_VERSION at CL XXXXX. That's all!
Release Candidate Build (Locked in)
IN PROGRESS
SUB | SUB | Make local copies to your station for all platforms going to certification | TODO | 2025-02-13
SUB | SUB | Create a cert thread in the Release channel. | TODO | 2025-02-13 |  |  | Pin it to the channel (example)
SUB | SUB | Add build info to the relevant cert backends. (CCA/ CCB / MobileCert) | TODO | 2025-02-13 |  |  | Steps to Complete can be found in this WIKI
SUB | SUB | Set up the above cert environments to have the correct: - Server (CCA / CCB / DPQ / MobileCert) - MCP (CCA / CCB / DPQ / MobileCert) | TODO | 2025-02-13
SUB | SUB | Ensure cert backends are online (CCA / CCB / DPQ / MobileCert) | TODO | 2025-02-13 |  |  | 1. Go to the links in Col A "Deployments" Tab 2. Change the status drop down in the middle to "Host Limits" 3. Input desired hosts into the max header (in this case 1) 4. Hit Apply > Review > Save > Refresh Page 5. Ensure the circles are going green
SUB | SUB | CertSub Candidate: Patch Sizes | TODO | 2025-02-13 |  |  | Steps to Complete can be found in this WIKI
SUB | SUB | Update Release Log and Release Request | TODO | 2025-02-13 |  |  | 1. Update REAL-XXXX ticket's description with build CLs, backend CLs & patch sizes 2. Check Release Log to ensure that info is reflected in the upcoming releases section
SUB | SUB | Upload Nintendo ROM and complete pre-submit waiver requests | TODO | 2025-02-13
SUB | SUB | Submit Switch the Switch build to lotcheck | TODO | 2025-02-13
SUB | SUB | Submit IOS for Notarization | TODO | 2025-02-13 |  |  | - Make sure to include the "test_accounts.xlsx" file - Make sure that the "FN External Testers" group is added to the build so it can be played on Live outside of the EU
SUB | SUB | Upload SIEA (07022) build | TODO | 2025-02-13
SUB | SUB | Upload SIEE (07669) build | TODO | 2025-02-13
SUB | SUB | Upload PS5 shared binary | TODO | 2025-02-13
SUB | SUB | Upload the Luna Client and send it to certification | TODO | 2025-02-13
SUB | SUB | Upload Xbox builds and send them to certification | TODO | 2025-02-13
SUB | SUB | Complete and save final MDT (PS5) | TODO | 2025-02-13
SUB | SUB | Update MDT: SIEA | TODO | 2025-02-13
SUB | SUB | Update MDT: SIEE | TODO | 2025-02-13
SUB | SUB | Rapid patch Submission: SIEA (07022) | TODO | 2025-02-13
SUB | SUB | Rapid patch Submission: SIEE (07669) | TODO | 2025-02-13
SUB | SUB | Rapid patch Submission: PS5 | TODO | 2025-02-13
PROD | RM | Aegis Prewarm (Final Client CL) | TODO | 2025-02-13 |  | Slack: LINK | Let #fne-aegis-prewarm-reports-ext know the build version and type and tag Garry Casey, Derek Burandt, and @fne-release.
OPS | RM | Generate Optimized Patches (chunkdbs) for the following platforms - Process update – run this for all platforms that are patching, not just (Android, PC, PS4, XB1, IOS) | TODO | 2025-02-13 |  | Horde Job(s): LINK | 1. Go to the Patching tab of Main-Horde 2. Select the 'New Job' button, and choose the Generate Optimized Patches (chunkdbs) template. 3. Set the Build Version to the ++CL that is being released (from the REAL-XXXX ticket) 4. Check Generate ChunksDBs Against Rollback Labels. 5. Set Platforms to any of the platforms that apply to the ++CL in step 3. a. Process update – run this for all platforms that are patching, not just (Android, PC, PS4, XB1, IOS) 6. Start Job 7. Re-run steps until all 4 platforms and their corresponding ++CLs are captured a. escalate errors/warnings to #fn-tech-ext (if applicable) for fixes | Hi INSERT_PERSON I'm getting some errors while running the Optimized Patch Job for our CHECKLIST_VERSION INSERT_ERRORING_PLATFORMS clients. Wondering if someone can take a look and advise on next steps.
OPS | RM | Final Client Build Protection - WIKI (so they don't delete the build before release date) | TODO | 2025-02-13 |  | CL(s) Protected: - 12345 | 1. Go to the Build Protection Sheet, duplicate the Template and rename the copy to CHECKLIST_VERSION 2. Populate the following fields for each unique CL we intend of releasing a. Version/Team = CHECKLIST_VERSION. Only use a team name if another team asks to protect a certain build (ex. winterbreak) b. Platform = Platform (All or individual platforms) c. Build Version = ++CL (from Horde / Release Ticket) d. Stage Job (Android) = Link to Android Promotion Job from Main Horde e. Keep Release Candidate Script = Link to the job from Main Horde (Clients Only) 3. Check the corresponding box once complete For UEFN Client Protection: - Rerun the UEFN Client CL with Windows checked off
PROD | RM | Ensure that the Branch Tab within the Game Config Doc has been locked at Noon | TODO | 2025-02-14 |  | Slack: LINK | 1. Spin up a thread in the #fn-release-CHECKLIST-VERSION-ext slack channel using the suggested text in Column H | :airhorn-9469: Hello team! Just calling out that the release team has locked the CHECKLIST_VERSION tab of Game Config today. Any further edits to this tab should go through the `Game Config Update` Service Desk Request from this point forward! :lock: Thanks! |  | Maybe?
OPS | RM | Final Server Build Protection - WIKI (so they don't delete the build before release date) | TODO | 2025-02-15 |  | CL(s) Protected: - 12345 | 1. Go to the Build Protection Sheet, duplicate the Template and rename the copy to CHECKLIST_VERSION 2. Populate the following fields for each unique CL we intend of releasing a. Version/Team = CHECKLIST_VERSION. Only use a team name if another team asks to protect a certain build (ex. winterbreak) b. Platform = Linux c. Build Version = ++CL (from Horde / Release Ticket) d. Stage Job (Android) = Link to Android Promotion Job from Main Horde e. Keep Release Candidate Script = Link to the job from Main Horde (Clients Only) 3. Check the corresponding box once complete For UEFN Server Protection: - Rerun the UEFN Client CL with Windows checked off | <--- This is a straight dupe of client... need to update for server
PROD | RM | Aegis Prewarm (Server) | TODO | 2025-02-20 |  | Slack: LINK | Let #fne-aegis-prewarm-reports-ext know the build version and type and tag Garry Casey, Derek Burandt, and @fne-release.
PROD | RM | 2nd touchpoint with Calendar owners | TODO | 2025-02-20 |  | Slack: LINK | 1. Revisit thread in THIS and poke calendar owners with the text provided in Row H 2. Confirm with all calendar owners that relevant calendars have been published to live ahead of CHECKLIST_VERSION release |  | Happy Day Before Deploy Day! Checking in to make sure all changes have been promoted to live leading up to our deploy on INSERT_DEPLOY_DAYnDATE.
OPS | RM | Disable remaining unneeded builds - Nightly Build with Build Health - Nightly Data Rebuild - World Partition Build - Juno Limited Build | TODO | 2025-02-20 |  | DO THIS THE DAY BEFORE RELEASE Commit CL: 12345 | 1. Go to here in P4: //Fortnite/Main/FortniteGame/Build/Streams/fortnite-release-CHECKLIST_VERSION.stream.json 2. Check out and open file 3. Create a shelf using the suggested P4 Description in Column H --> 4. Find "Nightly Build with Build Health" 5. In the "schedule" section > change "enabled": true to "enabled": false 6. Repeat steps 4-5 for: a. "Nightly Data Rebuild" b. "World Partition Build" c. "Juno Limited Build" 7. Save and commit in P4 9. Send courtesy message in Slack to #buildfarm-support-ext using the suggested P4 Description in Column I --> | Disabling the below jobs for Release-CHECKLIST_VERSION: - Nightly Build - Nightly Data Rebuild - World Partition Build - Juno Limited Build #jira none #fyi stan.hormell, swarm-ue-build-reviews #rnx | Hi Build Farm, just wanted to inform you that we disabled the below jobs for CHECKLIST_VERSION at CL XXXXXX. - Nightly Builds - Nightly Data Rebuild - World Partition Build - Juno Limited Build That's all!
Signoff and Submission
IN PROGRESS
OPS | RM | Verify no new client CLs have been introduced between Final Client WhiteGlove and Final Server/MCP WhiteGlove tests. | TODO | 2025-02-19 |  | Swarm Delta: https://p4-swarm.epicgames.net/files/Fortnite/release-CHECKLIST_VERSION?range=@FINAL_CLIENT_CL,@FINAL_SERVER_CL#commits | 1. Go to the Final Client WG in the #fn-release-CHECKLIST-VERSION-ext channel and note the CL(s) being tested 2. Go to the Final Server/MCP WG in the #fn-release-CHECKLIST-VERSION-ext channel and note the CL(s) being tested a. Ensure these are the intended CLs when comparing with the REAL-XXXX ticket 3. Go to Swarm and edit the link to point to the checklist version and bookend the 2 CLs above. /release-CHECKLIST_VERSION?range=@CLIENT_CL,@SERVER_MCP_CL#commits 4. Ensure all CLs have a Release Manager upvote (which means we have approved and they are not snuck in). a. You can ignore submissions from "Build Machine" 5. If there are any Client CLs, escalate in the #fn-release-mgmt-team-ext immediately
PROD | RM | Whiteglove has been completed on FINAL release candidate (aka Cert Checks) and issues called out have been threaded for triage | TODO | 2025-02-19 |  | Slack: LINK_TO_WG | 1. Go to #fn-release-CHECKLIST-VERSION-ext and search for "beginning whiteglove of:" a. This should bring up all instances of whitegloves bring run 2. Ensure RQA completes the Final Client+Server+MCP WG the day of Cert Submission a. You can track progress in TestRail (STC) if you have access 3. Ensure issues called out from the WG are appropriately threaded (outside the WG thread) and triaged in the #fn-release-CHECKLIST-VERSION-ext channel
SUB | SUB | Update Akamai with final patch sizes | TODO | 2025-02-19
SUB | SUB | Final Scheduling: Xbox One / XSX | TODO | 2025-02-19
SUB | SUB | Final Scheduling PS5 | TODO | 2025-02-19
SUB | SUB | Final Scheduling PS4 | TODO | 2025-02-19
SUB | SUB | Upload PS4 Symbols to devnet | TODO | 2025-02-19
SUB | SUB | Upload PS5 Symbols to devnet | TODO | 2025-02-19
SUB | SUB | Upload XB1/XSX crash symbols through Xbox Send | TODO | 2025-02-19 |  |  | 1. Log into your Xbox Send account 2. Upload the XB1/XSX crash symbols from our RC build. 3. Send it to Sean White <seanwh@microsoft.com> and Andy Hess <andrewhess@microsoft.com> 4. Find the email titled "RE: [EXTERNAL] Re: Symbol missing on MS Partner for Xbox and XSX for Fortnite" and ping the thread letting them know that they have been sent over.
SUB | SUB | Final Scheduling: Switch | TODO | 2025-02-19
SUB | SUB | Upload the Digital Turbine Candidate | TODO | 2025-02-20
SUB | SUB | Submit Android build to Oppo | TODO | 2025-02-19
SUB | SUB | Confirm with Luna that we're through certification. | TODO | 2025-02-19 |  |  | 1. Return to the Fortnite Overview in the Luna portal, check if the "alpha state" is set to "certified". *If the title is still certifying, ping Amazon in the submission thread to ask for an update.
SUB | SUB | Submit PC build to GFN | N/A | 2025-02-19 |  | GFN will scrape live.
Pre-Release
IN PROGRESS
PROD | RM | Confirm Release QA is patched up and ready for the morning | TODO | 2025-02-20 |  | NEEDS TO HAPPEN BEFORE 12PM ET (For Ivan) Slack: LINK | 1. Create new thread in #release-team channel using the suggested text in Column H a. Needs to happen before 12pm ET as Ivan will be gone after then 2. Make sure you have the currently live build installed in your launcher so you can verify the Win patch size come deploy day should you need to | Friendly reminder to the morning deploy owners @RQA1 @RQA2 to ensure your devices are all patched up for the morning deploy. :thankskeanu: |  | Yes
OPS | RM | Confirm with Discovery team that the Analytics Stuff revision has been deployed to Live | TODO | 2025-02-20 |  | Slack: LINK | 1. Using the DAD request thread, confirm with Disco team that the Analytics Stuff was updated appropriately for the pending release | Hello again! Just have a checklist item for today to confirm that the Analytics Stuff revision has been deployed to Live and there is no further work expected to finalize for our CHECKLIST_VERSION deploy tomorrow? We all set and ready to :rock: & :rollcat: ? |  | Yes
SUB | SUB | Remove Cert Redirects | TODO | 2025-02-20 |  |  | DO NOT REMOVE PS4 IF WE'RE STILL IN RMT TESTING WITH SONY - CCA, CCB, DPQ, FortniteMobileCert
SUB | SUB | Spindown Cert Servers | TODO | 2025-02-20
SUB | SUB | Live: Update PS4/PS5/XB1/XSX/IOS fake Build Info | TODO | 2025-02-20 |  |  | Needs to be done otherwise you can't check Selective (MSFT)
SUB | SUB | Live: Update Switch Build Info | TODO | 2025-02-20 |  |  | NEVER REMOVE BUILDS FROM LIVE
SUB | SUB | Live: Update Android Build Info | TODO | 2025-02-20 |  |  | NEVER REMOVE BUILDS FROM LIVE
SUB | SUB | Prep AltStore Stage Source | TODO | 2025-02-20 |  |  | Can be done once cert complete - need ADP ID
OPS | RM | Pre-upload symbols for the following (Within 24 hours of deployment) - PC - Switch - Linux - IOS - Android Wiki | TODO | 2025-02-20 |  |  | 1. Navigate to the CrashReporter_Symbol-Indexer folder and copy to your computer 2. Open the _Windows file by Right Click > Run With Powershell 3. Input the version number in the format XX.YY (Not XX.YY.Z) and hit enter CHECKLIST_VERSION 4. Input the CL from the REAL-XXXX Ticket (no ++) and hit enter 5. Repeat for Switch, Android, IOS & Linux
OPS | RM | Verify Release Request is accurate | TODO | 2025-02-20 |  |  | 1. Look at REAL-XXXX Ticket to ensure everything is up to date and any last minute changes have been captured ex. Clients/Backends/PatchSizes, Release Callouts (migrations, etc) |  |  | Maybe?
PROD | RM | Release Strategy Async Post Example Post: LINK | TODO | 2025-02-20 |  | Slack: LINK | 1. Create a new thread in #fn-release-CHECKLIST-VERSION-ext channel 2. Perform the steps outlined in Column I to layout the info consistently 3. Pin the post |  | 0. Begin post with the following line :announcement-1: CHECKLIST_VERSION Go Live Information Real Ticket Info 1. Add a line break using SHIFT+ENTER and then Copy all info in the BUILD INFO / PATCH SIZES section of the REAL-XXXX ticket and CTRL+SHIFT+V to paste values only into the slack post a Highlight the ++CLs and CTRL+SHIFT+C to turn them orange b. Highlight the Client / Server / Patch Size info and CTRL+SHIFT+9 to Block Quote them 2. Add a line break using SHIFT+ENTER and then Copy all info in the DESCRIPTION section of the REAL-XXX ticket and paste below the above info in the slack post a. Properly tag any people using @person if they are listed in plain text - Should we do this or leave it as plain text? Go Live Hotfix 3. Ask RQA if the final Game Config and add a line under the above section with it Major Items 4. Hit SHIFT+ENTER x3 to properly line break, then Add the following section below (BLUE TEXT indicates linking to the corresponding item). a. Copy the blue items and CTRL+SHIFT+8 to list as bullet items Major Items: INSERT_MAJOR_ITEMS_EX_PRODUCT_NEW_SEASON Run of Show related links can be found in the Run of Show bookmark Folder at the top of this channel Ship List 5. Hit SHIFT+ENTER x3 to properly line break, then lastly go to the Ship List (should be pinned in the #fn-release-CHECKLIST-VERSION-ext channel) and copy and paste that info below the major items Should result in a post like THIS
PROD | RM | Now that every deploy is a "Season Launch": Inform the slack channel of the bookmarked: - Run of Show Sheet - War/Launch Room Zoom Link - War/Launch Room Calendar Link | TODO | 2025-02-20 |  | Slack: LINK | 1. Go to fn-release-CHECKLIST-VERSION-ext channel in slack 2. Send message using the suggested text in Column H If the War/Launch Zoom/Calendar Event doesn't exist, create one and put it in the Run of Show | :announcement-1: Just a heads up for tomorrow: `The Run of Show, Launch Room Zoom & Calendar Invite` links are bookmarked at the top of this channel. :announcement-1: |  | Yes
SUB | RM | Internal Release Email Template | TODO | 2025-02-20 |  | ALL PLATFORMS NEED TO BE THROUGH CERT BEFORE SENDING EMAIL | 1. Look up a previous email to use as a template Search for "online-infra-global@epicgames.com" to find them 2. Copy the formatting and replace content with CHECKLIST_VERSION's information a. Look at the REAL-XXXX Ticket for all info 3. Send to the recipients in Column H | TO: online-infra-global@epicgames.com, global-live-deployments@epicgames.com, FN-Live@epicgames.com | Fortnite - XX.YY Release - MM/DD @ 4:00am ET Release Ticket: REAL-XXXX Player Impact: VERIFY_AGAINST_SLACK_THREAD Fortnite matchmaking will be disabled at 03:30am ET, downtime will then begin at 04:00am and is estimated to conclude at 05:30am. When downtime begins players will be kicked from active sessions. Players may experience throttled logins as we come back online. Build Info: App: Fortnite INSERT_FROM_REAL_TICKET Clients Windows: ++Fortnite+Release-XX.YY-CL-XXXXX PS4: ^^ PS5: ^^ Xbox: ^^ XSX: ^^ Switch: ^^ Android (EG): ^^ UEFN: ^^ Backend Server: ++Fortnite+Release-XX.YY-CL-XXXXX MCP: XX.YY.nnn-rXXXXX UEFN: ++Fortnite+Release-XX.YY-CL-XXXXX Patch Sizes Windows: X.XX GB PS4: X.XX GB PS5: X.XX GB XSX: X.XX GB Xbox: X.XX GB Switch: X.XX GB Android: Low End: X.XX GB / High End: X.XX GB Testing Requirements: Whiteglove Communication: #fn-release-deploy-ext | Maybe?
SUB | RM | External Release Email Template | TODO | 2025-02-20 |  | ALL PLATFORMS NEED TO BE THROUGH CERT BEFORE SENDING EMAIL | 1. Look up a previous email to use as a template Search for "partners-liveops-alerts@epicgames.com" to find them 2. Copy the formatting and replace content with CHECKLIST_VERSION's information 3. Send to the recipients in Column H | TO: partners-liveops-alerts@epicgames.com BCC: public-alerts@noa.nintendo.com, sie-noc@sony.com, xoc@microsoft.com, epic-issues@vivox.com, noc@subspace.com, release-team@epicgames.com | Fortnite - XX.YY Release - MM/DD @ 4:00am ET Player Impact: TAKE_FROM_MESSAGE_ABOVE Fortnite matchmaking will be disabled at 03:30am ET, downtime will then begin at 04:00am and is estimated to conclude at 05:30am. When downtime begins players will be kicked from active sessions. Players may experience throttled logins as we come back online. | Maybe?
SUB | RM | Send "Release is a GO" email | TODO | 2025-02-20 |  | ALL PLATFORMS NEED TO BE THROUGH CERT BEFORE SENDING EMAIL | 1. Look up previous deploy email using the string "is a GO for" 2. Copy the formatting and replace content with CHECKLIST_VERSION's information a. Ship List can be found pinned in the release-CHECKLIST-VERSION-ext slack channel b. Helpful Links can be found in the google calendar c. Down Time, Morning Crew / Patch Sizes can be found in the REAL-XXXX Ticket's Description | TO: fn-release-updates@epicgames.com | Replace with Pre-Pop | Maybe?
OPS | RM | Release morning owner: Log into all deploy-related tools | TODO | 2025-02-20 |  |  | 1. Log into the following services to ensure their platform is functioning and that you have access and will not be blocked at the last minute. Internal a. Swarm b. LightSwitch2 c. Autoscaler Scaler d. Horde e. Grafana f. Analytics g. Data Asset Directory (DAD) External a. PlayStation i. PlayStation 5 ii. PlayStation 4 b. Microsoft Partner Center c. Nintendo Content Management System d. Nintendo Developer Portal e. NVIDIA GeForce Now f. Amazon Luna g. Android OPPO
OPS | RM | Schedule Lightswitch Down in Admin Portal - Scheduling MUST happen at least 1 hour before the downtime start | TODO | 2025-02-20 |  | USE EXTREME CAUTION HERE: There is potential to bring the game down if you are not careful | 1. Go to Lightswitch 2.0 Page in the Admin Portal 2. Go to the "Add Scheduled Event" section at the bottom 3. Set Scheduled Time to the "Downtime" in the REAL-XXXX Ticket's Description a. cross-reference LS down time with the CHECKLIST_VERSION Release Strategy Email b. NOTE THIS TIME SHOULD BE SET TO EST 4. Set Status to: DOWN 5. Set Message to: Fortnite is down for maintenance 6. Set Add Actions to: Fortnite_Free_Platforms 7. Select Create Event 8. Double check the info in the new "Scheduled Events" section in the middle of the page - Processed should say No
Remove on cadence, Prod to handle this by request | RM | Record Post PD CLs (I don't see a point in doing this if nobody is looking, so setting to N/A for now. Don't waste your time with this clunky process. Justin will save us all with his airtable anyhow!) | N/A | 2025-02-20 |  | Tracker Tab: LINK | 1. Go to the Post PD Commits Tracker 2. Follow the instructions to complete the task 3. Link the tab in F103 NOTE: This an interim process. Ideally we can pull this data more efficiently through the submit tool flow
OPS | RM | Copy entire build(s) to Milestone Archive | TODO | 2025-02-20 |  |  | This is a copy of the entire build as it appears in the build folder to keep from having to rebuild if it is needed. Archive Fortnite Build CLs (New Job > Archive Fortnite Build > add in the ++CLs > Start Job). For Clients archive the clients and the Content Worker. This can later be found at : P:\Builds\Archive\Fortnite-Releases\Milestone++Fortnite+Release-CHECKLIST_VERSION-CL-12345678 |  |  | Maybe?
___ ___ __ __ ___ _ __ _ _ _ ¦ _ \ / _ \ \ \ / / o O O ¦ \ ___ ¦ '_ \ ¦ ¦ ___ ¦ ¦¦ ¦ ¦ / ¦ (_) ¦ \ \/\/ / o ¦ ¦) ¦ / -_) ¦ .__/ ¦ ¦ / _ \ \_, ¦ ¦_¦_\ \___/ \_/\_/ TS__[O] ¦___/ \___¦ ¦_¦__ _¦_¦_ \___/ _¦__/ _¦"""""¦_¦"""""¦_¦"""""¦ {======¦_¦"""""¦_¦"""""¦_¦"""""¦_¦"""""¦_¦"""""¦_¦ """"¦ "`-0-0-'"`-0-0-'"`-0-0-'./o--000'"`-0-0-'"`-0-0-'"`-0-0-'"`-0-0-'"`-0-0-'"`-0-0-'
Lead-up to Downtime - Deployment Owner
|  | Item | Status | Due buy | Done by | Temp-Notes | Perma-Notes
OPS | RM | Set up Crash Reporter prior to release for Switch | TODO | 2025-02-21 |  |  | 1. Navigate to the below file on the P drive (easily done on a Remote Machine) P:\Symbols\Switch\LiveSymbols\FortniteClient-Switch-Shipping.nsp 2. Open the file and swap in CHECKLIST_VERSION & the ++CL for the Switch Client 3. Save and you are done
OPS | RM | Final review of Release Request information | TODO | 2025-02-21 |  |  | 1. Make sure all build artifacts match expectations and what was whitegloved by Release QA 2. Make sure all checklist items were completed
OPS | RM | Create Post Deploy Tracker sheet and bookmark in in #fn-release-team as well as the associated #fn-release-CHECKLIST-VERSION-ext channel | TODO | 2025-02-21 |  |  | Add as Bookmark to that Release Channel so it is easily visible to everyone. Shared drives > Fortnite > Release Management > Post Deploy > Tracker Sheet > Master Post Deploy Tracker (make a copy, move it to the correct location, and rename) Master Post Deploy: https://docs.google.com/spreadsheets/d/1dycxSjGsHUC29FRelcLz1AVxtBZ8QW2NiG7WsNt-eXo/edit#gid=1420338449 |  |  | Maybe?
OPS | RM | Review initial build info setup: iOS/Android/Switch and now also including PS4/PS5/XB1/XSX fake build info needed starting with 18.40. | TODO | 2025-02-21 |  |  | 1. Make sure Android and Switch candidates are propped up in Live Build Info 2. Make sure Switch build info was removed from NSCert Build Info
OPS | RM | Verify Generate Optimized Patch was run against the correct build and finished successfully. | TODO | 2025-02-21 |  |  | Process update – check this for all platforms that are patching, not just (Android, PC, PS4, XB1, IOS) Escalate any issues to the #fn-tech-ext channel
OPS | RM | [Downtime minus 40 mins] Tag Live Ops to Disable Alerts. | TODO | 2025-02-21 |  |  | Only LOps has access to the alerts. Ping whomever is on call to disable. Otherwise there are fireworks. |  |  | Maybe?
OPS | RM | [Downtime minus 35 mins] Disable server scaledown ("Pin" server scaling) | TODO | 2025-02-21 |  |  | Navigate to Autoscaler for Live > Click the Edit checkbox (bottom right) > Hit Disable next to "Can Scale Down?" to keep servers from scaling down during downtime. Be sure to post in #fn-release-deploy-ext that this step was done.
OPS | RM | [Downtime minus 30 mins] Disable Matchmaking | TODO | 2025-02-21 |  |  | Option 1: MMS Admin Portal toggle button (Navigate to the Live MMS AP page > In the "Playlist Restrictions Configuration" section change "disableAllMatchmaking": to true > Hit the Update button) Option 2: Hotfix directly through Admin Portal System Files DefaultGame.ini [/Script/FortniteGame.FortGameInstance] bBattleRoyaleMatchmakingEnabled=false
OPS | RM | Check in "Go Live" Hotfix config and run Preview job | TODO | 2025-02-21 |  |  | Swarm link prepped by Release QA the night prior to release morning Hotfix Deploy Runbook
During Downtime - Deployment Owner
|  | Item | Status | Due Buy | Done by | Temp-Notes | Perma-Notes
OPS | RM | Confirm FN Lightswitch down | TODO | 2025-02-21 |  |  | Validate via Login data that downtime has started properly. (Success by Region/Platform in particular)
OPS | RM | PS4/PS5 Client Publish SIEA (07022) | TODO | 2025-02-21 |  | New process has PS4/PS5 scheduled like Switch/XB1/XSX | Tip: You might have to be on VPN AND Remote Desktop if performing from a location that does not have a allowlisted IP address. Log in to PlayStation Partners portal then follow these steps in the PS5 section.
OPS | RM | PS4/PS5 Client Publish SIEE (07669) | TODO | 2025-02-21 |  | New process has PS4/PS5 scheduled like Switch/XB1/XSX | Tip: You might have to be on VPN AND Remote Desktop if performing from a location that does not have a allowlisted IP address. Log in to PlayStation Partners portal then follow these steps in the PS5 section.
OPS | RM | Deploy MCP | TODO | 2025-02-21 |  |  | MCP Deploy Runbook
OPS | RM | Confirm MCP version is reflected in Fortnite Queue Worker Prod11 | TODO | 2025-02-21 |  | Queue Worker now auto deploys when we trigger an MCP deployment. We no longer need a manual job for QW. However we need to still confirm that QW updated correctly. | Fortnite Queue Worker Prod11 in TeamCity
OPS | RM | Deploy "Go Live" INI Hotfix config (make sure this is done before server deploy to ensure hotfix config is pulled correctly) | TODO | 2025-02-21 |  |  | Swarm link prepped by Release QA the night prior to release morning Hotfix Deploy Runbook
OPS | RM | Deploy "Go Live" Discovery DAD Hotfix | TODO | 2025-02-21 |  |  | Go Live Revision is found in the Game Config sheet.
OPS | RM | Deploy Servers | TODO | 2025-02-21 |  | Use the "Fast" option. When this is checked, hosts will immediately start the IPU process | Server Deploy Runbook
OPS | RM | Set Server Scale sets to "Sequence" | TODO | 2025-02-21 |  | DS will set it back later in the day | Use the apply all to set each fleet to "sequence" at https://fm-as-scale-fn-prod.ol.epicgames.net/fleet/live/scalesets
OPS | RM | PC Client Promotion (also select WindowsGFN/WindowsLuna if unchecked) | TODO | 2025-02-21 |  | PC/Android can be the same job if build labels match (Client deploy should align with Downtime) | Client Deploy Runbook
OPS | RM | Android Client Promotion | TODO | 2025-02-21 |  | PC/Android can be the same job if build labels match (Client deploy should align with Downtime) | Client Deploy Runbook
OPS | RM | iOS Client Promotion (wiki linked) | TODO | 2025-02-21 |  |  | 1. Update the Live-IOS build label to the new ADPID version in Admin Portal. 2. Ensure that the ++ version is listed in LiveCompat. 3. Run GitHub Action Workflow to promote to AltStore
OPS | RM | Confirm Switch/XSX/XB1/PS4/PS5 (our scheduled platforms) new versions are populating | TODO | 2025-02-21 |  | (Client deploy should align with Downtime)
OPS | RM | Start "[Thread] Updates on CHECKLIST_VERSION Fortnite release:" in #pub-fortnite slack channel | TODO | 2025-02-21 |  | Update with latest big callouts. | Example: https://epicgames.slack.com/archives/C044WR7HZDG/p1691482159647189 [Thread] Updates on CHECKLIST_VERSION Fortnite release: (post) Matchmaking Disabled at 3:30 AM ET LightSwitch Down at 4:00 AM ET Deploy started on time (4am ET) and so far things are going smoothly. Estimated uptime is ~5/5:15am ET. Will crosspost any major updates or issues here. |  |  | Yes
OPS | RM | Run Live promotion job for iOS, PS4, PS5, XB1, XSX, and Switch (no impact to Live players) | TODO | 2025-02-21 |  | Escalate any issues to the #fn-tech-ext channel | Example Thread: https://epicgames.slack.com/archives/C044TN4LVFT/p1667291267646149 Example Deploy: https://horde.devtools.epicgames.com/job/6360d85fe271e75dea797f32 22.30 Go Live PS4/PS5/XB1/XSX/Switch - Non-Player facing
OPS | RM | Make sure Live Build Info is cleaned up (old fix versions no longer supported) before we go lightswitch up | TODO | 2025-02-21 |  | Expand Live and Live-Compatible sections making sure older releases are not present. Every major release should be a forced patch. | https://adminportal.ol.epicgames.net/launcher/buildinfo/app/Fortnite Ensure that the Promotion Labels section correctly displays the new Live versions for all platforms (This must be done before Light Switch Up) * Build Info for Windows and Shipping-Android should always be real and never fake/dummy/placeholder. * IOS, PS4, PS5, XB1, XSX, and Switch will need to be manually updated using the labels from the Live Compat section ** Be sure to delete previously live Build Info from Live Compatible labels (Excluding 13.40 for now)
OPS | RM | [Uptime minus 15 mins] Scaling servers in downtime | TODO | 2025-02-21 |  |  | Note: Servers can take 10-15 min to scale up, please plan appropriately
OPS | RM | Make sure all Deploy Strategy callouts are finished before we go lightswitch up | TODO | 2025-02-21 |  |  | Refer to Release Ticket
OPS | RM | Additional checks before fully going Lightswitch Up: -Make sure patch has been caught on all platforms by Release QA and that live patch sizes were close to estimates/not egregiously big -If there are brand new non-brcore fleet LTMs going live at Lightswitch Up, confirm we are good with prescaling -Ensure that any QA callouts are okay to come LS Up with, or have a SH that we can associate to each callout as needed -Make sure Live Ops and Community owners approve going Lightswitch Up | TODO | 2025-02-21
OPS | RM | Re-enable Matchmaking if the MMS Admin Portal toggle approach was used to Disable Matchmaking above. | TODO | 2025-02-21 |  |  | MMS Admin Portal toggle button (Navigate to the Live MMS AP page > In the "Playlist Restrictions Configuration" section change "disable AllMatchmaking": to false > Hit the Update button)
OPS | RM | Fortnite Lightswitch Up. Put "Fortnite is online" in the message box | TODO | 2025-02-21 |  |  | USE EXTREME CAUTION HERE: link to Lightswitch page * Status = Up (for lightswitch UP) * Message = Fortnite is online * Add Actions = Fortnite_Free_Platforms * Create Event
Post-Release - Deployment Owner
|  | Item | Status | Due Buy | Done by | Temp-Notes | Perma-Notes
OPS | RM | [Uptime plus 30 mins] Tag Live Ops to ReEnable Alerts. | TODO | 2025-02-21
OPS | RM | Post the following message in the #fn-release-deploy channel once we are lightswitch up: "Friendly reminder that for all general weirdness callouts from this point forward that are unrelated to the live whiteglove to please use #fn-release-CHECKLIST-VERSION" | TODO | 2025-02-21 | [5 empty] | Maybe?
OPS | RM | Monitor the related release slack channel and thread each one with an acknowledgement (most callouts will come from EU community): -If high urgency: suggest making it a SH -If low urgency: tag appropriate producers/owners to have a look as soon as they get on in normal hours | TODO | 2025-02-21
OPS | RM | Update Hotfix Form/Slack Webhook to new release | TODO | 2025-02-21 |  | Scroll to the "Then: Send Web Request" and edit that entry. Make sure to hit Publish once you update and save. | https://api.slack.com/apps/A044VB8SXFV/incoming-webhooks? Add webhook url to FNR automation job: https://jira.it.epicgames.com/secure/AutomationProjectAdminAction!default.jspa?projectKey=FNR#/rule/661
OPS | RM | Add "Planned Release Slots" bookmark to the now live release slack channel with a link to the Planned Release Slots Miro board | TODO | 2025-02-21 | [5 empty] | Yes
OPS | RM | Create HF Jira for each HF week for CHECKLIST_VERSION. | TODO | 2025-02-21 |  |  | Example: FNR-1132 |  |  | Yes
OPS | RM | Set Slack channel Topic to Hotfix Request Form | TODO | 2025-02-21 |  |  | Example: Need a Hotfix? https://epic.gm/Hotfix ~ Email `release-team-oncall` to page Release-Team outside of office hours |  |  | Yes
OPS | RM | Do a manual post in #fn-live-updates that mentions we are up and copies in the ship list that should be pinned in the related release channel. | TODO | 2025-02-21 |  |  | Example: Good morning! We deployed CHECKLIST_VERSION this morning. Game opened up at 5:30 AM ET for players. CHECKLIST_VERSION Ship List :ship: * ship list notes here |  |  | Yes
OPS | RM | Change JIRA Release from Unreleased to Released | TODO | 2025-02-21 |  |  | Do nothing with any issues still on the release. OOB may linger.
OPS | RM | Update Release Log and Release Request | TODO | 2025-02-21 | [5 empty] | Yes
OPS | RM | [Uptime plus 2 hours] Enable server scaledown ("Unpin" server scaling) after server usage levels off closer to what it was pre-downtime. Check in with LiveOps first. | TODO | 2025-02-21 |  |  | Navigate to Autoscaler for Live > Click the Edit checkbox > Set "Can Scale Down?" to Yes Be sure to post in #fn-release-deploy-ext that this step was done.
OPS | RM | Zero Out AutoScaler Scaler Capacities | TODO | 2025-02-21 |  | Do this when you unpin | https://fm-as-scale-fn-prod.ol.epicgames.net/fleet/live/scalecapacity
OPS | RM | Send first Post-Deploy report email | TODO | 2025-02-21 |  | 1. 7am 2. 11am - Contact perf and get release updates to send out. 3. Afternoon 4. Next Day *Add Slack reminders for the email updates | List of Reports |  |  | Yes
OPS | RM | Set timed post for 2:30PM ET to: Post in #buildfarm-support-ext to remove the previous release version | TODO | 2025-02-21 |  | Make sure to use the timed post feature in slack to send it at 2:30 PM ET. | Reach out to Build Farm Support via #buildfarm-support-ext channel in slack and ask them to remove the previous branch from horde after the deploy is complete |  |  | Yes
OPS | RM | Make sure the Post Deploy Tracker has Stability information in time for the 10:00AM ET Stability Sync | TODO | 2025-02-21 | [5 empty] | Yes
SUB | SUB | Update the master cert timing tracker sheet | TODO | 2025-02-21 |  |  | Tracker Google Sheet -- tracking Switch / PS4 (SIEE (07669) /SIEA (07022) ) / PS5 / MSFT / Apple
SUB | SUB | Update Patch Size Tracking | TODO | 2025-02-21 |  |  | Remember to add Install time thresholds as well
SUB | SUB | Increment Switch version | TODO | 2025-02-21
SUB | SUB | Increment PlayStation versions | TODO | 2025-02-21
SUB | SUB | Increment iOS version | TODO | 2025-02-21
SUB | SUB | Update Sony LatestPatch folder to contain these patches | TODO | 2025-02-21 |  |  | MasterReleases->1.0->Create folder for appropriate app version
SUB | SUB | Update Nintendo LatestPatch folder to contain these patches | TODO | 2025-02-21
SUB | SUB | Update Xbox LatestPatchfolder to contain these patches | TODO | 2025-02-21
OPS | RM | Send Day-2 Post-Deploy report email | TODO | 2025-02-22 | [5 empty] | Yes
SUB | PART | Update Partners Builds | TODO | 2025-02-21 |  |  | Create Release Ticket for Partner Build
DONE
N/A
Not currently relevant (re-visit as needed)
|  | Item | Status | Due by | Done by | Temp-Notes | Perma-Notes
| RM | Confirm MCP deploy percentage with OGS (tag Pete Axt & Joe Pintozzi) and Live Ops. WIKI | TODO | 2025-02-20 |  | Slack: LINK | 1. Make a post in #epic-live-operations-ext or #on-dbs-game-services-ext using the suggested text in Column H | @Joe Pintozzi @Pete Axt Just confirming we are targeting 50% DeployHostPercentage during downtime as usual for the CHECKLIST_VERSION MCP deploy tomorrow? |  | Yes
| RM | Create Bug Bids Page | BLOCKED | 2025-01-06 |  | Bug Bids Page: LINK | 1. Go to the previous version's Bug Bids Page (here) 2. Click "..." > Copy > Copy 3. Change title to Bug Bids for CHECKLIST_VERSION > Publish 4. Note the current values in the Issues Left column 5. Edit the page > Update the hard coded HL-1w and HL dates as per the FN Schedule 6. Clear the hardcoded values in HL-1W and HL columns (highlight and delete) This section is borked until the <> is re-added back. Need to do manually until then :((((( 7. Select the <> icon to open in source editor 8. Find the version you copied from, replace all with the version you want > Apply > Update 9. Ensure the values have changed |  |  | Yes
| RM | Schedule Send Bug Bids Email 10 days prior to Hard Lock date at 10:30am | BLOCKED | 2025-01-06 |  | Send scheduled for DATE | 1. Go to GMail and compose a new email 2. Send email using the suggested text in Column H 3. Link the bug bids page to the blue text 4. Change Day MM/DD to the date of review (monday the week of HL) 5. Once done, hit the drop down arrow on the blue Send button > Schedule Send 6. Pick a Date & Time > 10 days prior to Hard Lock date at 10:30am (See Cell F2) 7. Schedule Send 8. Go to your gmail > Scheduled (below sent) and review the preview to ensure it is all correct 9. Paste the scheduled send info in column F for reference | The CHECKLIST_VERSION Bug Bids wiki has been created and is ready for you to enter your bids! We will start reviewing at morning sync next week on DAY MM/DD. Reminder, there's a link on the top of this page you can use to look at historic fix rate data for your components, which you can use to reason about what your teams can realistically tackle leading up to CHECKLIST_VERSION. Past Bug Bid pages are also still available for review under the Release Accountability parent page. CHECKLIST_VERSION Dashboard: [Link] Doing this thinking now, ahead of the hectic bugfix stage, will help identify rational targets you can use to guide triage activities & tradeoff decisions. Thanks, Release Team | TO: Release-Team@epicgames.com CC: FN-Prod-All <FN-Prod-All@epicgames.com>, FNE Release <fne-release@epicgames.com> Subject: Bug Bids for CHECKLIST_VERSION | Yes
| x | (Joe) I would just completely kill this line in favor of the Build Protection line just above. Run Keep Release Candidate job for all final client candidate CLs. | TODO | 2025-02-19 |  | PLATFORM_1: HORDE_JOB_LINK PLATFORM_2: HORDE_JOB_LINK PLATFORM_3: HORDE_JOB_LINK | 1. Go to the REAL-XXXX ticket for this release to see the final candidate CLs 2. Go to the Promotions tab of Main Horde 3. Select the blue New Job button in top right 4. Change template dropdown to Keep Release Candidate 5. Put the first CL in the Change field and set the associated Promote Platforms field. Then Start Job. a. Re-Run for all Client CLs with their associated Promote Platforms field.
|  | Verify the Android APK allowlist is in the game config file | N/A | 2025-02-20 |  | Release Team no longer needs to send hotfixes to update CRC values when we ship new Android client builds. The 13.40 values need to stay, but the Android APK Whitelist hotfixes no longer function in 23.50+ . This is now being done on the AntiCheat side via Dragonfly. | Verify it is in the game config file
| SUB | Review Android APK allowlist syntax is included and correct in Release QA swarm link and in PredeployA files | N/A | 2025-02-21 |  | Release Team no longer needs to send hotfixes to update CRC values when we ship new Android client builds. The 13.40 values need to stay, but the Android APK Whitelist hotfixes no longer function in 23.50+ . This is now being done on the AntiCheat side via Dragonfly.
|  | Create a Jira for StW Calendar/Store to be update/reviewed (CN/RoW) | TODO | 2025-01-06 |  |  | Assign to Dav Harnish and CC Henry Meredith in comments https://jira.it.epicgames.net/browse/FORT-247162
|  | Check Android APK size and make sure it is under 150 MB | TODO | 2025-02-12 |  |  | Look at APK in the build folder
|  | Create a tab in FN Playlist Planning sheet and let stakeholders know in #fn-release-playlistplanning-ext that it now exists | TODO | 2025-01-06 |  |  | https://confluence.it.epicgames.com/display/FORT/Playlist+Planning Note: If its a .10 release, spin up a thread. If its not, then mark this task as N/A.
|  | Schedule Meeting: Release Notes Signoff | N/A | 2025-01-28 |  | No Release Notes! | Thurs. of CertSub week
|  | Release Notes: Initial Setup and Email Sent | N/A | 2025-01-28 |  | No Release Notes!
|  | Schedule Calendar Reminders: Release Notes Section Owners | N/A | 2025-01-28 |  | No Release Notes! | 1 each day for 2 document days of release notes
|  | Order breakfast for morning of publish day | TODO | 2025-02-09 |  | Please bring this back!!!
|  | Send initial IOS Submission email | TODO | 2025-02-09
|  | Update Google Play Roadmap email (if applicable) |  | 2025-02-09 |  |  | to: Dan Song <mtd@google.com(opens in new tab)> Lawrence Koh <lawrencekoh@google.com(opens in new tab)> CC release-team Jocelyn Hans
|  | Send Release Notes 1st Draft to FN-Release-Updates | N/A | 2025-02-09 |  | No Release Notes!
|  | Forward CN patch notes to EGC | N/A | 2025-02-12 |  | No Release Notes! | Forward version patch notes for China to Martin Yu. Martin will review and deliver to Tencent.
|  | Add IOS Whitelist Hotfix to MobileCert | TODO | 2025-02-13
| RM | Check iOS Compressed File Size | TODO | 2025-01-28 |  | Compressed File Size: MB Previously in 13.40 Release flagged if greater than 200 MB. Compressed sizes have increased in allowance from Apple. We should still note what the size is and report to tech-mobile Jira for investigations is FORT-772296 This process may be something we can remove, but need to keep an eye out for a few releases. [thread] | 1. Go to https://appstoreconnect.apple.com/apps 2. Select Fortnite 3. Select TestFlight 4. Select the RC candidate Version and Build 5. View the Build Metadata for Compressed File Size 6. Record the size and pass along to Tech-Mobile
|  | Audit MobileCert environment config for potential cert blockers | TODO | 2025-02-19
|  | Configure MobileCert Build Info | TODO | 2025-02-19
|  | MobileCert: MCP Update | TODO | 2025-02-19
|  | MobileCert: Server Promote | TODO | 2025-02-19
|  | Cert Submission: iOS | TODO | 2025-02-19
|  | Send email notifying Apple contacts that build is uploaded | TODO | 2025-02-19
|  | Send email notifying Google contacts that build is uploaded | TODO | 2025-02-19
|  | Remove MobileCert Redirect | TODO | 2025-02-20
|  | Live: Update iOS Build Info | TODO | 2025-02-20
|  | Remove Android Build Info from MobileCert | TODO | 2025-02-20
|  | Live: Update LiveCN Build Info | TODO | 2025-02-20 |  |  | Deploy will be coordinated with TC in #ext-fncn-live in Slack. TC will flip WeGame switches. THIS STEP IS ONLY NEEDED IF STAGING THE CN BUILD FAILED.
|  | Update Apple Cert Timing Tracker | TODO | 2025-02-21
|  | Update EULA if requested by Legal | TODO | 2025-01-28
VVV To be Re-Added Once iOS comes back VVV
|  | Make sure PredeployA Hotfix Files are set back to appropriate Android Whitelist and IOS Banning syntax for LOPS to copy at time of release | TODO | 2025-02-20 |  | Only Android? | Android: Whitelist syntax needs to be added IOS: Remove the following: [/Script/FortniteGame.FortGameModeZone] BanCodeAction_20=(AnyReason=2, UnsignedIPA=0) BanCodeAction_28=(AnyReason=2, NoIOSCryptInfo=0)
|  | Make sure PredeployA Hotfix Files are set back to appropriate Android Whitelist and IOS Banning syntax for QA to not be blocked | TODO | 2025-02-21 |  |  | Android: Whitelist synatx needs to be removed IOS: Add the following: [/Script/FortniteGame.FortGameModeZone] BanCodeAction_20=(AnyReason=2, UnsignedIPA=0) BanCodeAction_28=(AnyReason=2, NoIOSCryptInfo=0
|  | Determine if release breaks Replays and/or if we should whitelist any old CLs | TODO | 2025-01-28 |  | https://wiki.it.epicgames.net/pages/viewpage.action?spaceKey=FORT&title=Replay+Whitelisting | Should be considered if we are breaking replays of a major Live event from the previous release Ask Shak or Matt Grandstaff
|  | Test verify PS4 remaster jobs have no errors or warnings | TODO | 2025-02-11 |  |  | Nightly Job "Publish PS4 Remaster Submission Packages (SIEA (07022) Only)"
|  | Confirm all Non-Unity warnings and errors are fixed or benign | TODO | 2025-02-11
|  | PS4: Update R:\Analytics\sony_version.csv | TODO | 2025-02-21 |  | I refuse | Instruction Doc
Lead-up to Downtime - China Deploy Owner
|  | Make sure PredeployA Hotfix Files are set back to appropriate Android Whitelist and IOS Banning syntax for QA to not be blocked | TODO | 2025-02-21 |  |  | Android: Whitelist synatx needs to be removed IOS: Add the following: [/Script/FortniteGame.FortGameModeZone] BanCodeAction_20=(AnyReason=2, UnsignedIPA=0) BanCodeAction_28=(AnyReason=2, NoIOSCryptInfo=0
|  | [24 hrs before] Inform Tencent and Community | TODO | #REF! |  |  | 24 hrs before - Inform in #ext-fncn-live @Sula Yu and CN QA deply captain Check EGC QA Checklist > Captain tab for additional @ https://docs.google.com/spreadsheets/d/1nUx7qP1aLLU6D1VVv0Q4mx18aMMG_tz5vmQC0Z9wxgc/edit?usp=sharing
|  | [24 hrs before] Release JIRA | TODO | #REF! |  |  | Link Release management Jira ticket here
|  | [2 hours befire] Hotfixes Checked In and Previewed | TODO | #REF! |  | Check fn-release-team around 4PM ET | RQA will provide a Swarm shelf to approve and merge around 4PM ET https://docs.google.com/spreadsheets/d/1w5PQcnciR-lbbU6H6m0aaqgiFWNRbttSr7uEoCmKUzk/edit#gid=2063781583
|  | [2 hours before] Schedule Downtime (Fortnite) | TODO | #REF! |  | Schedule sometime before 4:40pm | https://adminportal-website-management.ol.epicgames.net/lightswitch2/schedule/fortnitelivecn?server=Lightswitch&moduleName=lightswitch
|  | [1 hrs before] Verify Client, Server, and MCP for release | TODO | #REF! |  |  | Pinged in Release Private if unsure of any changes
|  | [1 hrs before] Internal Release Email | TODO | #REF! |  |  | fncn-live@epicgames.com, fn-live, online-infra, global-live-deployments
|  | [35 min before] Turn off FN CN Alerts | TODO | #REF! |  | Poke liveOPS at MMS disable | Request liveOPS pause FN Grafana integration in OpsGenie https://epicgames.app.opsgenie.com/teams/dashboard/76f730d9-7346-4f83-b599-ab3589ba2fce/integrations
|  | [35 min before] Alternatively, Set False to True for Playlist Restrictions Configuration section at https://adminportal.ol.epicgames.net/fortnite/profileProxy?server=Fortnite%20China&moduleName=fortnite Click MMS at top and scroll down to Playlist Restrictions Configuration Set disableAllMatchmaking to true | TODO | #REF! |  |  | 35mins before LS down Edit directly under Admin Portal https://adminportal-website-management.ol.epicgames.net/fortnite/systemFiles Make sure you are in "Fortnite China" Notify fn-release-deploy (FN-Deploy Public) and Mission Control slack channels |  | For Old Hotfix Method: DefaultGame.ini [/Script/FortniteGame.FortGameInstance] bBattleRoyaleMatchmakingEnabled=false
During Downtime - China Deploy Owner
|  | Item | Status | Due by | Done by | Temp-Notes | Perma-Notes
|  | Confirm Lightswitch down status | TODO | #REF! |  |  | Check status has switched to DOWN - https://adminportal-website-management.ol.epicgames.net/lightswitch2/schedule/fortnitelivecn?server=Lightswitch&moduleName=lightswitch
|  | Lightswitch down notifications | TODO | #REF! |  |  | Post message in fn-release-deploy and Mission Control slack channels
|  | We Games access disabled | TODO | #REF! |  |  | Notify ext-fncn-live to disable access for we games. More often than not this is Sula, but confirm it isn't a different Tencent employee
|  | Deploy "Go Live" INI Hotfix config (make sure this is done before server deploy to ensure hotfix config is pulled correctly) | TODO | #REF! |  |  | Can move on to MCP and Client deploys until Hotfix is done. Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy internal
|  | Deploy MCP | TODO | #REF! |  |  | Deploy %: 50% Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy internal
|  | Deploy MMS | TODO | #REF! |  |  | Done by MMS team after matcmaking is disabled - confirm with them during release sync if a deployment is being done. Loop them in when light switch down
|  | PC Client Deploy - Use Promotion Job (Client) | TODO | #REF! |  |  | Whole build string, LiveCN, only Windows. Allow Live Promotions and BPT checked Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy Public
|  | Server Deploy | TODO | #REF! |  | Make sure Hotfix is underway before Deploying Server. Otherwise servers won't get new hotfixes for possibly 4 hours. | Start immediately after hotfix deploy, due to server prep time, hotfixes should be live just prior to sessions starting Fleet: LiveCN Cohort: Main Use fast deploy option for downtime releases. Notify fn-release-deploy and Mission Control slack channels Use FN-Deploy internal
Post-Release - China Deploy Owner
|  | Item | Status | Due by | Done by | Temp-Notes | Perma-Notes
| RM | Nvidia: reply to already existing corresponding release thread in #ue-partner-nvidia-ext with courtesy status updates | TODO | 2025-02-21 |  |  | Usually Douglas Valkenaar, Alexander Gustev or Andrew Saritsky - #external-nvidia channel |  |  | Maybe?
|  | StW Whiteglove | TODO | #REF! |  |  | Poke ext-fccn-live with @s to start whiteglove
|  | BR Whiteglove | TODO | #REF! |  |  | Whiteglove is completed by both Epic CN and Tencent teams separately - need confirmation from both teams of a successful check.
|  | If help is needed flushing buckets | TODO | #REF! |  | Click "Direct control panel link" in next link | https://adminportal-website-management.ol.epicgames.net/fortnite/profileProxy?server=Fortnite%20China&moduleName=fortnite
|  | Re-enable Light Switch Up | TODO | #REF! |  |  | Ready once the whiteglove has been confirmed and without any issues Update status message to Fortnite is up! Notify Sula - Access has been re-enabled. @Sula Yu please re-enable from wegames side as well Notify in Mission Control and FN-Release-Deploy - No whiteglove callout and lightswitch up
|  | Re-enable CN alerts | TODO | #REF! |  |  | Unpause FN Grafana integration in OpsGenie https://epicgames.app.opsgenie.com/teams/dashboard/76f730d9-7346-4f83-b599-ab3589ba2fce/integrations
|  | Post in #buildfarm-support to remove the previous release version | TODO | #REF! |  |  | Reach out to Build Farm Support via #buildfarm-support channel in slack and ask them to remove the previous branch from horde after CN deploy is complete
|  | Archive previous release Slack channel | TODO | #REF!