## Release Run of Show
| Launch Day: | 2025-07-17 | Run Of Show Meeting & Launch Day Zoom Link |  |  |  | EST To UTC: | 4 |  | Set Filter
Product | Date | Time (ET) | Action Summary | Action Type | Primary Owner(s) | Backup Owner(s) | Flag for mention in next RoS Sync? | Status | Notes
Early Planning
Release | 2025-07-03 | 10:00 | Calculate CCU Projections |  | Analytics | Analytics | Yes - Needs Discussion | Not Started
Release | 2025-07-03 | 4:00 | PREVIOUS_VERSION Releases |  | @release-team | @release-team | No - Already Discussed | Not Started
Release | 2025-07-10 | 23:00 | CHECKLIST_VERSION Pencils Down |  | @release-team | @release-team | No - Already Discussed | Not Started
Release | 2025-07-10 | 10:00 | Cancel/Reschedule Weekend Horde & P4 Maintenance |  | @release-ops | @release-ops | Yes - Needs Discussion | Not Started
BR | 2025-07-10 | 13:00 | Verify accurate in-game season end date on the battlepass page and level up pack |  | Shania Williams | Matt Argueta | Yes - Needs Discussion | Not Started
Online | 2025-07-10 | 10:00 | Server fleet reservations |  | Mathew Bender | Ben Constable | Yes - Needs Discussion | Not Started | point releases we just autoscale, no need for reservations | .00 ONLY
Release | 2025-07-10 | 10:00 | Communicate timing with 1st Parties, CDNs and ISPs. Include CCU projections where appropriate and a warning for their player support teams to safeguard information. |  | Release Team (Hilda Cruz) | @release-submissions | Yes - Needs Discussion | Not Started | Dependent on CCU projections being done.
Online | 2025-07-11 | 13:00 | Review if this release requires any new metrics or dashboards |  | Gaëtan Gireme / LiveOps | David Lubell | Yes - Needs Discussion | Not Started | Prior Example: https://grafana.ol.epicgames.net/d/zoPakyK7k/event-back-end-services-dashboard?orgId=1&refresh=1m
BR | 2025-07-11 | 14:00 | Ensure that we are not planning an item grant to players as soon as we come up from downtime, or after exiting an event THIS WILL CAUSE THE ECOSYSTEM TO CRASH FROM MCP CALL OVERLOAD IF IT HAPPENS |  | Release Team | Product Stakeholders | Yes - Needs Discussion | Not Started | Context from PIR doc the last time this happened.PIR 2023/12/02 - Login outage after durian concert end
Online | 2025-07-14 | 12:00 | Update prod Fortnite catalog item |  | Patrick Sun |  | Yes - Needs Discussion | Not Started | DISTRO-3342 This is the EGS Mitigation for Event Landrush! If expecting a landrush of logins to Fortnite. Example; big event (w/Night-Night) -> shut down, then yes. normal shutdown, then no
Launch Run up
Anticheat | 2025-07-15 | 17:00 | Anticheat Scaling (Dragonfly) |  | Joe Barrett | Charlie Nomides | Yes - Needs Discussion | Not Started | If Analytics calculates CCU projects under 8M, can N/A this check.
BR | 2025-07-15 | 17:00 | Check-In with Ranked team if there is a planned Season reset for any Ranked modes. Create a Ranked milestone to differentiate the old from the new season. These should be coordinated with the Marketing Web team. |  | Osmar Junior | Sean Gibson | Yes - Needs Discussion | Not Started
Online | 2025-07-15 | 17:00 | EOS Voice Prescaling |  | Luke Cody |  | Yes - Needs Discussion | Not Started | Autoscaling will cover -- As long as the CCU growth is linear, we do not have any concerns. If there is a sudden huge jump in players, then we would want to pre scale
Online | 2025-07-15 | 17:00 | Postparty Scaling |  | Luke Cody |  | Yes - Needs Discussion | Not Started | Autoscaling will cover -- As long as the CCU growth is linear, we do not have any concerns. If there is a sudden huge jump in players, then we would want to pre scale
Release | 2025-07-15 | 23:00 | Adjusted Perforce/Horde weekly maintenance |  | Build Farm / Perforce | @release-team | Yes - Needs Discussion | Not Started | If there are any issues POR is to page IT oncall and ask them to page perforce team oncall. Scheduling confirmed by BuildFarm and Perforce Admins
Online | 2025-07-16 | 10:00 | Schedule Locker Service DDB Scaling Event |  | James Miao | Joe Pintozzi | Yes - Needs Discussion | Not Started | Locker Service DDB read capacity needs to be pre-warmed before LS up in order to handle the initial landrush of traffic. This can be done via a terraform change any time before the release. See runbook: https://github.ol.epicgames.net/dbs/service-locker?tab=readme-ov-file#schedule-ddb-scale-out-prior-to-release
Social | 2025-07-16 | 14:00 | Post heads-up messaging on social about when things will be disabled. | tweet | Community (Sean McIntosh) | Community (Catherine Pope) | Yes - Needs Discussion | Not Started | Happens every release. Timing dependent on Release Go Live
Social | 2025-07-16 | 14:00 | Larger Patch Size Messaging |  | Community (Sean McIntosh) |  | Yes - Needs Discussion | Not Started
Insights/ Data | 2025-07-16 | Anytime | Press 'Start' on Statsig experiments | Statsig UI | Josh Clark Justin Chiang Yulia Savitskaya | Johnie Allen | No - Already Discussed | Not Started | There Statsig experiments managed by Shop team for the this release. - locker_search_v2 - show_shop_action_icon_on_lobby We need to manual press 'Start' for them before the release on the Statsig web UI.
Launch Day
Online | 2025-07-17 | 3:00 | Adjusted Perforce/Horde weekly maintenance ends |  | Build Farm / Perforce | Release Team (Stan Hormell) | Yes - Needs Discussion | Not Started | If there are any issues POR is to page IT oncall and ask them to page perforce team oncall. Scheduling confirmed by BuildFarm and Perforce Admins
Release | 2025-07-17 | 3:30 | Disable MatchMaking | Admin Portal | Release Team (Stan Hormell) | Release Team (@release-ops) | Yes - Needs Discussion | Not Started
Release | 2025-07-17 | 4:00 | Downtime Begins | Admin Portal | Release Team (Stan Hormell) | Release Team (@release-ops) | Yes - Needs Discussion | Not Started | INSERT LINK TO Deploy Time Alignment THREAD
Release | 2025-07-17 | 4:00 | Clients are released on all platforms. datamining/leaks will begin. | Horde + Schedule First Party | Release Team (Stan Hormell) | Release Team (@release-ops) | Yes - Needs Discussion | Not Started
Release | 2025-07-17 | 4:00 | Deploy MCP | Team City | Release Team (Stan Hormell) | Release Team (@release-ops) | Yes - Needs Discussion | Not Started
Online | 2025-07-17 | 4:30 | Start MCP Profile loading |  | Joe Pintozzi, Dan Scauzillo | page-mcp-backend-team@epicgames.opsgenie.net | Yes - Needs Discussion | Not Started |  | .00 ONLY
Release | 2025-07-17 | 4:00 | Hotfixes + Resiliency + DAD | Hotfix | Release Team (Stan Hormell) | Release Team (@release-ops) | Yes - Needs Discussion | Not Started | Game Config Tracker
Online | 2025-07-17 | 5:00 | Profile migration completed or disabled/stopped early |  | Joe Pintozzi, Dan Scauzillo | page-mcp-backend-team@epicgames.opsgenie.net | Yes - Needs Discussion | Not Started |  | .00 ONLY
Release | 2025-07-17 | 5:30 | Server deployed | Horde | Release Team (Stan Hormell) | Release Team (@release-ops) | Yes - Needs Discussion | Not Started
Release | 2025-07-17 | 5:30 | LS Down Checks Begin | Whiteglove | Release QA (Tatiana Gonzalez / Ivan Blaus) | Release QA (@releaseqa) | Yes - Needs Discussion | Not Started
Online | 2025-07-17 | 6:00 | Verify waiting room configuration in admin portal is set to 50 (Fortnite) |  | Joe Pintozzi | Live Ops/Pulse | Yes - Needs Discussion | Not Started |  | .00 ONLY
Release | 2025-07-17 | 6:00 | Server Scaling | DS Portal | Release Team (Stan Hormell) | Live Ops/Pulse | Yes - Needs Discussion | Not Started
Release | 2025-07-17 | 5:30 | Enable Matchmaking | Admin Portal | Release Team (Stan Hormell) | Release Team (@release-ops) | Yes - Needs Discussion | Not Started
Release | 2025-07-17 | 5:30 | Downtime Ends | Admin Portal | Release Team (Stan Hormell) | Release Team (@release-ops) | Yes - Needs Discussion | Not Started
Release | 2025-07-17 | 14:00 | Revert Resiliency Hotfixes (Schedule a HF Request in Advance for Follow Up) | Hotfix | Release Team (Stan Hormell), Joe Pintozzi | Release Team (@release-ops) | Yes - Needs Discussion | Not Started | Exact time TBD based on service health Schedule a HF Request in Advance [example hotfix] | .00 ONLY

## Addendum
If there is a new Island Code update (Reload, Ballistic)
Make 1PP REAL TICKET https://jira.it.epicgames.com/browse/REAL-4958
Publishing / Activation
Prewarm Island Code
Discovery Surface Update
Enable Island Code in Links Service
Link Migrator
If there is a new LTM
Server fleet perfmem testing
Server config with DS team
Discovery Surface Update

## Information (hidden)
Points of Contact |  | Communications / Info Resources
Run of Show Production | Joseph Sozio | Dev working slack channel (private) | #fn-armadillo-event
Event Production (Epic) | Josh Mast | Showtime / War Room slack channel (private) | #fn-armadillo-event
Jason Glatz
| Stefanie Cage | Showtime / War Room zoom | Zoom Link
Event Production (High Voltage) | James McClellan | One Stop Shop Grafana (CCU, Mesh Health, Etc.) | General Event Health
Keith Hladik
| Jessa Carlson | Hotfix Config Sheet | Armadillo Tab
Nina Cortez
| Kevin Vekony | Playlist name | Playlist_Armadillo
Event Directors | Billy Rivers | Season 21 Launch Day General Callouts | #fn-release-21-00
Tim Elek
Gil Rimmer
Event QA (Epic) | Dara Potocska
Riley Halligan
Event QA (High Voltage) | Chris Franz
Event QA (EPAM) | Uladzimir Lushchyts

## Leak Prevention (hidden)
Date | Time (ET) | Action Summary | Primary Owner(s) | Backup Owner(s) | Leak Mitigation / Notes | Action Items if leak occurs | Level of Concern | Strings identified for Datamining passes | Related Terms | Specific Assets or Strings of Concern | Encryption/Removal from 20.40/Placeholder Text/OK Doing Nothing Confirmed? | Notes
Previous Event Post Incident Review / Generic Callouts | [7 empty] | Armadillo | End Event, Build-Up to End Event | Crew (20.40):
N/A | N/A | Loading screen cosmetic grant containing spoilers given too early/before event started |  |  | -Event Directors have signed off on all 3 cosmetic rewards (2 loading screens and 1 lobby track) are safe to be granted ahead of the event. -Make sure loading screens encryption happens |  | Low | ArmadilloRoll | End Event, Build-Up to End Event | CID_A_418_Athena_Commando_M_ArmadilloRobot | Encryption Confirmed | Final encryption config incoming
N/A | N/A | Tik Tok and other external marketing partners posting assets too early | Scott N, Kyle G |  | -Hyper caution is game plan here |  | Medium | Realm | Vader, Vader Lightsaber | BID_A_018_ArmadilloMale | Encryption Confirmed | Final encryption config incoming
N/A | N/A | 1st party player support responses spoiling downtime duration/target uptime | Hilda Cruz, Nat Parkinson |  |  |  | High | Noble | Obi-Wan Kenobi | Wrap_479_Armadillo | Encryption Confirmed | Final encryption config incoming
N/A | N/A | Website in a different country that dropped too early (backend at the wrong time) | Justin Shelton |  | No one seems to recall this post incident review callout from Guava |  | Low | Collision | Player facing event name
N/A | N/A | Application launch splash images and game tile art contained spoilers causing late scramble to change | Jodi L |  | -Followed up with Laura, Emu, Jodi, Lauren and current thinking is no special plans or concerns here -Have followup conversation, may not be as sensitive as chapter 3 launch -Might be ok |  | Low | Doggus? | Pickaxe, and Outfit itself (but seperate due to different release times) | Crew (21.00):
N/A | N/A | Loading screen into event leaked on consoles |  |  | In the past we would leak loading screen tooltips because consoles were not encrypted but they should be encrypted now |  | Low |  | Pilot Outfits? | Pickaxe_ID_811_ArmadilloMale | Removal from 20.40 Confirmed | Blacklist and spot check 20.40 cooks
N/A | N/A | Playlist text containing spoilers |  |  | Should be safe until noon on event day |  | Low |  |  | LSID_442_Armadillo_Heartache | Removal from 20.40 Confirmed | Blacklist and spot check 20.40 cooks
N/A | N/A | UA ads going out ahead of embargo | Scott N, Kyle G |  | -Hyper caution/pushing on partners |  | High |  |  | EID_ArmadilloRobot | Removal from 20.40 Confirmed | Blacklist and spot check 20.40 cooks
N/A | N/A | 1P breaking embargo with assets | Craig Evans |  | Meeting with 1P this week (some today, some next week) Running them through plan |  | High |  |  | BRS20_Armadillo_Heartache | Removal from 20.40 Confirmed | Blacklist and spot check 20.40 cooks
N/A | N/A | Quest lines not encrypted / accessible in patch before |  |  | -Follow up with REGS on audit of plan -Meeting booked for Thurs. 5/5 |  | Medium
N/A | N/A | Lobby background phases not encrypted / accessible early |  |  | -Sean knows the drill! |  | Low |  |  | Pilot Outfits and Built In Emote (20.40):
N/A | N/A | Vader leaks early |  |  | 21.00 Vader was duplicated into an event/20.40 specific CID that is encrypted in the Armadillo plugin that does not get decrypted until seconds before event kickoff |  | Low |  |  | CID_A_417_Athena_Commando_F_Armadillo | Encryption Confirmed | Final encryption config incoming
N/A | N/A | Obi Wan leaks early |  |  | Obi Wan releases to public in 20.40, not sure of exact date. -Encrypted until needed -follow up on 20.30 quests -Still 2 versions of CIDs in the build(cine one and normal one), SteveA to make sure we are all good here. UPDATE: RoS line item for pencils down added for extra sanity check with EthanP and SteveA. |  | Low |  |  | CID_A_416_Athena_Commando_M_Armadillo | Encryption Confirmed | Final encryption config incoming
N/A | N/A | Doggus Crew Outfit leaks early |  |  | See RoS lines below for breakout of assets |  | Medium |  |  | EID_Armadillo | Encryption Confirmed | Pulled into encryption automatically with outfits
N/A | N/A | Doggus Pickaxe and Heartbreak Emote leaks ahead of event |  |  | See RoS lines below for breakout of assets |  | Low
N/A | N/A | Internal Actors leaks to an Influencer | Bruce |  |  | Private SH | Low |  |  | Attendance Rewards (20.40):
N/A | N/A | Pilot Outfits Encryption? |  |  | Confirmed they should be encrypted until they hit the item shop. They also include a built in emote. See RoS line for more details. |  | Low |  |  | MusicPack_133_Armadillo | Encryption Confirmed | Final encryption config incoming
N/A | N/A | Gameplay tags cleanup | Ethan |  | Aaron and Ethan have done several passes. Final pass added to RoS |  | Low |  |  | LSID_438_Armadillo | Encryption Confirmed | Final encryption config incoming
N/A | N/A | Reward Grant Giftbox text |  |  | We can use placeholder text, then hotfix it to the real text right before the grant happens. |  | Low |  |  | Giftbox Text: Title: Collision Body: We've got your back! | OK Doing Nothing Confirmed | Might leave alone as not sensitive - Joe to follow up with Event Directors
N/A | N/A | Making sure all cosmetic reward grants are encrypted |  |  | -Quick zoom to finalize plan |  | High
N/A | N/A | Discovery testing concerns: -"As long as the playlist itself isn't in the live build, you are safe to put the playlist in Discovery" -"CMS in particular is also important, don't put anything in CMS concerning the playlist (description, title, images) until this actually needs to go live. Uses images and text that wouldn't be leaking anything if they escape." |  |  | SeanM from community has ack'd this warning from Paul Moore. |  | Low |  |  | Playlist Loading Screen Text: Weapons Team to battle stations. Today, we’re gonna put an end to the Imagined Order. For Good. | Encryption Confirmed | Encrypted by default until seconds before showtime in the Armadillo Event Plugin. In the past this could still leak on consoles but now we have console encryption.
Armadillo Actions
Early Planning | [9 empty] | 2 Set Names (Mecha Weapons Team and Collision) will be obfuscated requiring hotfix | Placeholder Text Confirmed | Need two manual hotfix lines before each Set Name (Crew and Pilots). SteveA/Christian to own obfuscation.
2022-04-26 | 10:00 | Communicate event timing with 1st Parties, CDNs and ISPs. Include CCU projections where appropriate. | Release Team (Hilda Cruz), 1P Team (Craig Evans) | Release Team (Stan Hormell) 1P Team (Ryan Broseker) |  |  | High
2022-05-09 | 10:00 | Rotate Night Night encryption key | Evan Kinney | Cody Haskell | Important Note: should NOT send the new key anywhere after rotation and will impact testing approach after this time. |  | Low |  |  | Quest Text | Encryption Confirmed | Weeks 1 and 2 will not be encrypted and datamineable when 20.40 launches. Week 3 will be encrypted until the quests go live on 5/31. This plan was approved by Event Direction.
2022-05-09 | 10:00 | Review pass on gameplay tags for leak concerns | Ethan Podczerwinski | Aaron Johnson |  |  | Low
2022-05-17 | 4:00 | 20.40 Releases | Release Team (Hilda Cruz) | Release Team (Stan Hormell) |  |  | High |  |  | Realm (Vader) | Encryption Confirmed
2022-05-17 | 4:00 | Giftbox text for pre-event attendance rewards is datamineable: Title: Collision Body: We've got your back! | Laura Stone | Emu Servais | Text isn't overly concerning but we are still discussing potentially using placeholder text and hotfixes to keep it hidden until grant time. |  | Low
2022-05-17 | 9:00 | Quest Pt. 1 | Marshall Harlan | Matt Argueta | Dedicated Quest Text Audit Meeting - Thurs. 5/5 2pm ET |  | Low |  |  | Noble (Obi Wan) | Encryption Confirmed
2022-05-19 | 9:00 | MTL Lobby Background 1 | Community (Sean McIntosh) | Community (Catherine Pope) | manual upload and publish, we won't touch this til 5min beforehand | :confused_dog: :imposter: :sus: | Low
2022-05-20 | 9:00 | Build Up Phase | Nick Meili | Ethan Podczerwinski | -Doomsday tower buildup in Core BR, usual map calendar events that drive this |  | Low
2022-05-24 | 9:00 | Quest Pt. 2 | Marshall Harlan | Matt Argueta | Dedicated Quest Text Audit Meeting - Thurs. 5/5 2pm ET |  | Low
2022-05-24 | 9:00 | MTL Lobby Background 2 | Community (Sean McIntosh) | Community (Catherine Pope) | manual upload and publish, we won't touch this til 5min beforehand | :confused_dog: :imposter: :sus: | Low
2022-05-24 | 9:00 | Cinematic Teaser Part 1 | Laura Stone | Paris Nourmohammadi | Hyper caution around it getting published too early? |  | Medium
2022-05-26 | 9:00 | In-game and Lobby Timer (20.40) | Nick Meili | Ethan Podczerwinski |  |  | Medium
2022-05-26 | 9:00 | Appointment Set MOTD with "RSVP" | PLM Team (Aaron Reed) | PLM Team (David Hook) |  |  | Medium
2022-05-26 | 9:00 | Appointment Set Owned Channels with "RSVP" | 1P Team (Ryan Broseker) | 1P Team (Craig Evans) |  |  | Medium
2022-05-26 | 9:00 | Appointment Set (Blog, Key Art, Social) | Laura Stone | Paris Nourmohammadi |  |  | Medium
2022-05-26 | 9:00 | Post blog announcing event | Community (Sean McIntosh) | Community (Catherine Pope) | blog will be set to "In Development" and will not be scheduled, requiring manual publishing to an environment | unpublish blog if published early. Consult Laura/Paris on new timing if word is spread to stay ahead of the curve | Medium
2022-05-26 | 9:00 | Publish socialevents page in CMS with event Name and Time | Community (Sean McIntosh) | Community (Catherine Pope) |  |  | Medium
2022-05-26 | 9:00 | Send assets to console partners | Mikey Noon | Scott Nellessen |  |  | Medium
2022-05-26 | 9:00 | Paid Media goes live promoting event | Kyle Gaunt | Scott Nellessen |  |  | Medium
2022-05-26 | 9:00 | Like to Remind Twitter campaign | Clinton Butler | Kellen Judy |  |  | Medium
2022-05-28 | 10:00 | Cinematic Teaser Part 2 | Laura Stone | Paris Nourmohammadi |  |  | Medium
2022-05-28 | 9:00 | MTL Lobby Background 3 | Community (Sean McIntosh) | Community (Catherine Pope) | manual upload and publish, we won't touch this til 5min beforehand | :confused_dog: :imposter: :sus: | Low
2022-05-29 | Various | Doggus/Mech Blueprint puzzle piece scavenger event starts | Laura Stone / Drabek | Paris Nourmohammadi | Most of the imagery would have already been live |  | Low
Event Week
2022-05-31 | 9:00 | Quest Pt. 3 | Marshall Harlan | Matt Argueta | Dedicated Quest Text Audit Meeting - Thurs. 5/5 2pm ET |  | Low
2022-05-31 | 9:00 | MTL Lobby Background 4 | Community (Sean McIntosh) | Community (Catherine Pope) | manual upload and publish, we won't touch this til 5min beforehand | :confused_dog: :imposter: :sus: | Low
2022-05-31 | 10:00 | Fortnite Crew Announcement | Danny Orihuela | Laura Stone |  |  | Medium
2022-05-31 | 10:15 | Push manual decryption key(s) for Fortnite Crew pending confirmation of 10am announcement above | Steve Allison | Evan Kinney, Eryc Kelly | WIll make sure we confirm blog is live and all good first |  | Medium
2022-05-31 | 20:00 | Fortnite Crew Doggus Immediately includes: 1. CID_A_418_Athena_Commando_M_ArmadilloRobot 2. BID_A_018_ArmadilloMale 3. Wrap_479_Armadillo Delayed until 21.00 build: 1. Pickaxe_ID_811_ArmadilloMale 2. LSID_442_Armadillo_Heartache (Blueprint Promoshot) 3. EID_ArmadilloRobot 4. BRS20_Armadillo_Heartache | Danny Orihuela | Laura Stone | MCP rollover to deliver items |  | Medium
2022-06-01 | 10:00 | Launcher Toast Notification | PLM Team (Aaron Reed) | PLM Team (David Hook) |  |  | Low
2022-06-02 | 10:00 | Event is soon MOTD with "RSVP" | PLM Team (Aaron Reed) | PLM Team (David Hook) |  |  | Low
2022-06-02 | 10:00 | Push Notification - Schedule Set | PLM Team (Aaron Reed) | PLM Team (David Hook) |  |  | Low
2022-06-02 | 10:00 | Full Cinematic Teaser Trailer | Laura Stone | Paris Nourmohammadi |  |  | Medium
2022-06-03 | 20:00 | Pilot outfits with built in posing emotes hit the Item Shop | Christian Graham | Steve Allison | Confirmed we want these encrypted until shop rollover time. Decryption via calendar/MCP at time of shop rollover. |  | Medium
2022-06-03 | 20:00 | Push manual decryption key(s) for Key Art Loading Screen and Lobby Music Track | Steve Allison | Evan Kinney, Eryc Kelly | Need to make sure implementation of the grant and decryption is being tracked. |  | Medium
2022-06-03 | 21:00 | Cosmetic Reward Grants: 1. MusicPack_133_Armadillo 2. LSID_438_Armadillo (KeyArt) | Marshall Harlan | Matt Argueta |  |  | Medium
2022-06-03 | 21:00 | Lobby Track Video (Social) | Kellan Judy | Clinton Butler |  |  | Medium
Event Weekend - Saturday
2022-06-04 | 10:00 | Update image for event playlist tile | Community (Sean McIntosh) | Community (Catherine Pope) | Will be a cut down version of the doggus blueprint loading screen. Needs to be after announcement, but before event. Can be same day. Align on expectation of exact timing. |  | Low
2022-06-04 | 12:00 | Add Event LTM to default playlists / Event plugin is available/decrypted (which allows the calander to trigger them on) | Release (Hilda Cruz, Matthew Newton) | Release (Stan Hormell, Eryc Kelly) | We have used this same approach and timing in past events |  | Low
2022-06-04 | 14:00 | Add Event playlist to Discovery | Release (Hilda Cruz, Matthew Newton) | Release (Stan Hormell, Eryc Kelly) |  |  | Low
2022-06-04 | 14:00 | Push Notification - event live soon | PLM Team (Aaron Reed) | PLM Team (David Hook) |  |  | Low
2022-06-04 | 15:00 | Social Promotion | Kellen J | Clinton B |  |  | Medium
2022-06-04 | 15:30 | Add NightNight plugin encryption keypair to mesh for distribution to lobby clients | Cody Haskell | Evan Kinney |  |  | Low
2022-06-04 | 16:09 | Event content plugin gets decrypted (about 15 seconds before the show kicks off) This includes Realm (Vader) event specific CID | Cody Haskell | Evan Kinney | Same approach and timing we have used in past events |  | Low
2022-06-04 | 16:20 | Players enter NightNight ("Vibin" UI to tease season 21). There will not be an explicit countdown timer but we will have "To be continued..." | Aaron Johnson | Ethan Podczerwinski | Music Controller and Night Night widget will be in the NightNightMode plugin for automatic encryption |  | Low
2022-06-04 | 16:30 | Event VOD posted and Night Night streaming begins (Twitch, YouTube) | Mana Drake | Clinton Butler |  |  | Low
2022-06-04 | 17:00 | Start 21.00 MCP Deploy to get a jump on player migrations | Release Team (Hilda Cruz) | Release Team (Stan Hormell) | Grab list of what could potentially leak here. Shouldn't have visuals, just calendar events etc. Joe to still follow up here. |  | Low
Event Weekend - Sunday
2022-06-05 | 2:50 | Release BP trailer and Overview Video on YT (To get ahead of dataminers/leakers) | Mana Drake | Clinton Butler | These are the ones that usually leak early via some 3rd party |  | High
2022-06-05 | 3:00 | 21.00 clients are released on all platforms. Season 21 datamining/leaks will begin. | Release Team (Stan Hormell) | Release Team (Joseph Sozio) |  |  | Low
2022-06-05 | 7:00 | Crew members receive the following delayed items from initial June batch: 1. Pickaxe_ID_811_ArmadilloMale 2. LSID_442_Armadillo_Heartache (Blueprint Promoshot) 3. EID_ArmadilloRobot 4. BRS20_Armadillo_Heartache | Emu Servais | Alex Conner | Will not be included in the 20.40 build and are granted immediately upon launch of 21.00 |  | Low

## Guava Run of Show (hidden)
Guava --> Coconut --> Pumpkin
|  | Validation | Deployment Type | Time | Date | Description | Owner | Status | Jira (If Applicable) | Notes
[5 empty] | Ongoing | Dry run of show | Release QA | Done
[6 empty] | Update first parties with event date & higher player count | Ryan Broseker | Done
RELEASE DETAILS |  |  |  | Anytime |  | Playlist Setup | Game Team (Ben Saponaro . Ethan P) | Done |  | Reach out to Ethan P for playlist info. Core BR modes only (match Buffet behavior)
Guava | [5 empty] | Marketing Two Week Leadup | Alec Shobin / Paris N | Done
Release Version | 18.40 |  |  | {Tentative} | 18.40.1 Deploy | Validate "unforced" patching on XB/PS/Switch | Release Team | Not Needed |  | https://epic.slack.com/archives/C02GNP21LS1/p1634052333097500
Hard Lock Date | 2021-11-04 |  |  |  |  | Tech to trigger Pumpkin from nitenite | Evan Kinney | Done |  | Works
Pencils Down | 2021-11-08 |  |  |  |  | Tech to deliver encryption key | Evan Kinney | Done
Cert Sub | 2021-11-11 |  |  |  |  | Tech to deliver encryption key AND trigger pumpkin just for QA | Evan Kinney | Done | FORT-432663 | Evan - Need to whitelist RelQA for Live Whiteglove of 19.00 - They use Shipping Clients
Event Live Date | 2021-12-04 |  |  |  |  | Jitter for MMS into pumpkin | Evan Kinney | Done
Live Time (Eastern) | 16:00 |  |  |  |  | RTCoconut (so clients in coconut in 19.00 and experience an error don't RTMM) | Riley Halligan | Done
[6 empty] | Test and API audit 18.40 and 19.00 nitenite | Riley Halligan | Done
Pumpkin | [5 empty] | Retool of nitenite to make sure login/profile Migration happens | Owner? | Done
Release Version | 19 |  |  |  |  | Version and update checking | Eric Newman | Done
Hard Lock Date | 2021-11-11 |  |  |  |  | --how do we inform/force an 18.40 client out to get new patch from nitenite | Evan Kinney | Done
Pencils Down | 2021-11-17 |  |  |  |  | --need to tell everyone they CAN update the client in the "not forced" time | Evan Kinney | Done | FORT-419163 | How do we want to display this to players? Re-do dialogue box. FORT-419163
Cert Sub | 2021-12-01 |  |  |  | 2021-11-16 | 18.40 Build is Live | Release Team (Nat Parkinson) | Done
Event Live Date | 2021-12-04 |  | 18.40 Release | 0:00 | 2021-11-16 | Build Up - Phase 1 | Ethan Podczerwinski (High Voltage) / Nick Meili | Done
Live Time (Eastern) | 10:00 |  | Calendar Event | 0:00 | 2021-11-23 | Build Up - Phase 2 | Ethan Podczerwinski (High Voltage) / Nick Meili | Done
|  |  |  | 10:00 | 2021-11-24 | Update in-game and web season end date to 12/4 | Marshal Harlan / Justin Shelton | Done
|  |  |  | 10:00 | 2021-11-24 | Publish socialevents page in CMS with event Name and Time | Community (Michael house) | Done
|  |  | Calendar Event | 10:00 | 2021-11-24 | In-game and Lobby Timer (18.40) | Ethan Podczerwinski (High Voltage) / Nick Meili | Done |  | Calendar event
|  |  |  | 10:00 | 2021-11-24 | Post blog announcing event | Community (Michael Sokolkov) | Done |  | All appointments are added as line-items
|  |  |  | 10:05 | 2021-11-24 | Appointment Set MOTD with "RSVP" | PLM Team (Aaron Reed / David H) | Done |  | Will be a scheduled launch
|  |  |  | 10:05 | 2021-11-24 | Paid Media goes live promoting 'The End' Event | Kyle G | Done
RESOURCES |  |  | Email | 10:00 | 2021-11-26 | Cancel/Reschedule Weekend Horde & P4 Maintenance | Release Team (Stan Hormell) | Done |  | Ryan Durand limited Horde maintenance to only 2-2"15am ET on Sun. 12/5
Working Channel | #fn-guava-event |  |  |  | 11/29/2021* | Triple size of MCP fleet | Online (Pete Axt) | Done |  | Need to sort this date with the online team
WarRoom Channel | #fn-guava-event |  | Calendar Event | 0:00 | 2021-11-30 | Build Up - Phase 3 | Ethan Podczerwinski (High Voltage) / Nick Meili | Done
Design Doc |  |  |  | 10:00 | 2021-12-01 | Launcher Toast Notification | PLM Team (Aaron Reed / David H) | Done
Tech Beats Doc |  |  |  | 10:00 | 2021-12-01 | Configure "oldmain" Live cohort to include only Mesh related deployments | Jake Champlin / DS Team | Done
Game Config Sheet | Link |  |  | 11:00 | 2021-12-01 | Update prod fortnite catalog item | Patrick Sun/James Calentino | Done | DISTRO-2506 | add undo at some point?
|  |  |  | 12:00 | 2021-12-01 | Deliver Island Flip Video to TikTok for 12/5 Takeover units | Kyle G / Jen S | Done
|  |  |  | 10:00 | 2021-12-02 | Guava is soon MOTD with "RSVP" | PLM Team (Aaron Reed / David H) | Done
POINTS OF CONTACT |  |  |  | 10:00 | 2021-12-02 | Push Notification - Schedule Set | PLM Team (Aaron Reed / David H) | Done
Design | Billy Rivers |  |  | 10:00 | 2021-12-02 | Deploy only Mesh related deployments of final 18.40 event server to "oldmain" Live cohort | Release Team (Stan Hormell) | Done
|  |  |  | 14:00 | 2021-12-02 | Disable Third Party AntiCheat for Guava\Coconut\Pumpkin Playlists | Anticheat (Charlie Nomides) | Done |  | We will disable EAC and BE for the Guava playlist via Nobus.
Production | Jess Ammerman |  |  | 12:00 | 2021-12-03 | Verify mesh network is scaled appropriately Verify base NightNightFrontend metadata is present in mesh | Online-OGS (Evan) | Done |  | { "NightNightFrontend": { "AreWeGettingSleepy": "VeryVerySleepyUwU", "HasDaddyTuckedUsIn": false, "Splines": [] } }
| Jason Glatz |  |  |  |  | Launch Weekend Fun Starts |  | Done
| Michael Carlock |  |  | 9:00 | 2021-12-04 | Push manual decryption key(s) for 10am ET event "S18 GuavaDay Cosmetic Reward Grant" | Steve Allison (Backups: EvanK/ErycK) | Done |  | Wrap: Wrap_417_Guava_7J7EW Loading Screen: LSID_375_GuavaEvent_9GXE3 FORT-415158 FORT-425972 Slack Thread
| Robert Knorr |  |  | 10:00 | 2021-12-04 | Change image for playlist tile | Community (Sean M) | Done |  | Needs to be after announcement, but before event. Can be same day.
| Keith Hladik (HVS) |  |  | 10:00 | 2021-12-04 | Post heads-up messaging on social about when things will be disabled. | Community (Sean M) | Done
| Jessa Carlson (HVS) |  |  | 10:00 | 2021-12-04 | Publish heads-up messaging in-game for Creative and STW. | Community (Sean M) | Done |  | StW will be in Discovery. Has StW messaging changed?
|  |  | Hotfix | 10:00 | 2021-12-04 | Deploy hotfixes: StW Auto Complete to trigger at 2:15pm Creative server shutdown time to 2 hours | Release Team (Stan Hormell/Eryc K) | Done |  | Syntax Source of Truth is in the Game Config Sheet
|  |  |  | 12:00 | 2021-12-04 | Scale OldMain Mesh Fleet | Liveops (JonS) | Done
|  |  |  | 12:00 | 2021-12-04 | Server Scaling in preparation for event | Liveops (JonS) | Done |  | 4 hours before the event goes live (4 pm EST)
|  |  | Hotfix | 12:00 | 2021-12-04 | Add Event LTM to default playlists (which allows the calander to trigger them on) | Release Team (Stan Hormell/Eryc K) | Done |  | Morning of.
Dev QA | Dara Potocska |  | Hotfix | 12:00 | 2021-12-04 | Disable Mobile Guided Tutorial | Release Team (Stan Hormell/Eryc K) | Done
|  |  |  | 12:00 | 2021-12-04 | Verify waiting room configuration in admin portal to 750 (Fortnite) and 500 (mobile) | Liveops (JonS and Pete Axt)) | Done |  | Day of.
IT-Perforce on-call | Kevin White |  |  | 12:00 | 2021-12-04 | Verify Guava Playlist key in keychain | Steve Allison (Backups: EvanK/Eryc K) | Done
|  |  | Discovery (DAD) | 14:00 | 2021-12-04 | Add Event playlist to Discovery | Release Team (Stan Hormell/Eryc K) | Done |  | Reach out to Tristan
|  |  | Discovery (DAD) | 14:00 | 2021-12-04 | Deploy Discovery V2 setup to disable Featured island via DAD | Release Team (Stan Hormell/Eryc K) | Done |  | Reach out to Tristan
|  |  | Calendar | 14:00 | 2021-12-04 | Disable BattleLab, Playgrounds, Party Island, and Creative modes | BR Game Team (Ben Saponaro / Ethan P) | Done |  | Needs to be 2 hours before event starts
|  |  |  | 14:00 | 2021-12-04 | In-game messaging: BattleLab, Creative, and Party Island and Customs have been disabled. | Community (Sean M) | Done |  | Right after we disable.
|  |  | Hotfix | 14:00 | 2021-12-04 | Deploying HF for online resiliency during event (From Online Ops Team) | Release Team (Stan Hormell/Eryc K) | Done |  | Needs to be 2 hours before event starts.
|  |  | Hotfix | 14:00 | 2021-12-04 | Hotfix to allow players to go NightNight and Enable mesh network connectivity on clients in lobby | Release Team (Stan Hormell/Eryc K) | Done |  | Syntax Source of Truth is in the Game Config Sheet
|  |  | Hotfix | 14:00 | 2021-12-04 | Set mole server shutdown time to 30 Mins | Release Team (Stan Hormell/Eryc K) | Done |  | https://epic.slack.com/archives/CB1EDDKDK/p1629814647369900?thread_ts=1629750923.354800&cid=CB1EDDKDK | Float in sec
|  |  | Hotfix | 14:00 | 2021-12-04 | Disable Creative playlist, and remove My Library, Create, and Code tabs in Discovery | Release Team (Stan Hormell/Eryc K) | Done
|  |  |  | 14:00 | 2021-12-04 | Verify mesh network service health after client enable Verify client connectivity via PlayerContext canary | Online-OGS (Evan) | Done
|  |  |  | 14:00 | 2021-12-04 | Push Notification - event live soon | PLM Team (Aaron Reed / David H) | Done
|  |  | Calendar | 14:00 | 2021-12-04 | Players will be kicked from the StW frontend and to the mode select screen. | Release QA (Eryc K) | Done | FORT-426537 | The new flow goes in during 18.40, will likely be tested fairly late. Need Calendar Event | dev online bug. Not needed for the live game.
|  |  | Reminder | 14:15 | 2021-12-04 | Auto-win players in-game and send to the StW frontend. (Hotfix Syntax dictates the time it fires - Deployed with Hotfix Deploy 1) | Release QA (Eryc K) | Done |  | Confirm that this works at that time
|  |  |  | 15:00 | 2021-12-04 | Turn off Arena | Competitive (Nathaniel Garrett) | Done |  | This can be done automatically with Arena Blackout windows
|  |  |  | 15:00 | 2021-12-04 | Emergency messaging updated:: Arena disabled | Community (Sean M) | Done
|  |  |  | 15:00 | 2021-12-04 | Social Promotion | Emily N | Done |  | 1 hour before event
|  |  |  | 15:15 | 2021-12-04 | Undo Playlist blocking via MMS | Evan Kinney | Done |  | 35 minutes before showtime
|  |  |  | 15:30 | 2021-12-04 | Mesh command to warm the CDNs | Chris Adams | Done |  | ke * RootStartWarming RiskyReels 1 1 "0.5 0.5" - | MAKE SURE YOU CHECK THE SYNTAX FOR THIS MESH COMMAND
|  |  | Calendar | 15:25 | 2021-12-04 | Enable Event playlist, Disable all other playlists in core including Mole (ROW ONLY) | Release QA (Mitchell H) | Done | FORT-426539 | 35 minutes before showtime (include in JIRA). Verify that this works at that tinme Make sure we have a calendar task.
|  |  |  | 15:25 | 2021-12-04 | Emergency messaging: Modes disabled and playlist open | Community (Sean M) | Done
|  |  |  | 15:25 | 2021-12-04 | Disable cloud banhammer actioning | Anticheat - Charlie Nomides/ Joe Barrett | Done
|  |  |  | 15:30 | 2021-12-04 | Add NightNight plugin encryption keypair to mesh for distribution to lobby clients | Online-OGS (EvanK) | Done
|  |  |  | 16:00 | 2021-12-04 | Event Showtime | BR Game Team (Billy Rivers) | Done
|  |  |  | 16:05 | 2021-12-04 | Event Triggered | BR Game Team (Billy Rivers) | Done |  | Syntax on Game Config
|  |  | Admin Portal | 4:10:00 PM (midway-ish through event) | 2021-12-04 | NightNight Hotfix (live edit the system file directly to avoid Horde delay) Pick up anyone that missed the mesh trigger slash mesh trigger fallback | Release Team (Stan Hormell/Eryc Kelly) | Done
|  |  |  | 4:10 PM (before end) | 2021-12-04 | Change mesh network metadata to trigger NightNight mode immediately for anyone still in lobby | Online-OGS (Evan Kinney) | Done
|  |  |  | 4:10 PM (before end) | 2021-12-04 | Add 18.40 netCL to MMS blocklist in MCP Add NightNight key to MCP keychain | Online-OGS (Evan Kinney) | Done
|  |  |  | 16:15 | 2021-12-04 | Players enter Coconut experience in 18.40 | BR Game Team (Billy Rivers) | Done |  | automatic after guava event concludes w/ tidal wave
|  |  |  | 16:30 | 2021-12-04 | TV Spot begins airing | ParisN | Done
|  |  |  | 16:30 | 2021-12-04 | Digital paid media goes live | Kyle Gaunt | Done
|  |  |  | 17:00 | 2021-12-04 | Clear emergency messaging | Sean McIntosh | Done
|  |  |  | 17:00 | 2021-12-04 | Scale down "main" cohort completely and just leave Mesh related deployments on "oldmain" | Live Ops (Jon Sredl) | Done
[6 empty] | Pumpkin and 19.00 |  | Done
|  |  |  | 18:00 | 2021-12-04 | Deploy 19.00 MCP - 25% | Release Team (Stan Hormell/Mitchell H) | Done
|  |  |  | 21:30 | 2021-12-04 | Resiliency Hotfixes along with regular go live 19.00 hotfix config (Note: We need to make sure the hotfix bundle is out before clients start updating. Because of coconut, 19.00 clients will only get hotfixes once.) | PeteA/Release | Done
|  |  |  | 22:00 | 2021-12-04 | 19.00 Deploys Part 1 (No downtime and unforced): PS4/PS5/XB1/XSX Clients Server (All Fleets needed for whiteglove) to "main" cohort | Release Team (Stan Hormell/Mitchell H) | Done
|  |  |  | 23:00 | 2021-12-04 | Consider activating "Game Update Available" in game UI toast for PS4/PS5/XB1/XSX RelQA NightNight WhiteListing | EvanK/Release | Not Needed
|  |  |  | 3:50 | 2021-12-05 | Release BP trailer and Overview Video on YT (To Combat Leakers) | ManaD/ClintonB | Done
|  |  |  | 4:00 | 2021-12-05 | 19.00 Deploys Part 2 (No downtime and unforced): PC/Android/Switch Clients are released (staggered to delay leak window, pc last) | Release Team (Joe Sozio/Mitchell H) | Done |  | Clarify expectations for leaks: e.g. battle pass, etc.
|  |  |  | 5:00 | 2021-12-05 | Consider activating "Game Update Available" in game UI toast for PC/Android/Switch | EvanK/Release | Not Needed
|  |  | Admin Portal | 6:00 | 2021-12-05 | Force all 18.40 Players to update to 19.00* | Release Team (Joe Sozio/Mitchell H) | Done |  | Need a hard cut-off time.
|  |  | Hotfix | 11:00 | 2021-12-05 | Clean 18.40 Hotfixes | Release Team (Joe Sozio/Grant M) | Done |  | Holding until after pumpkin settles down
|  |  |  | 8:00 | 2021-12-05 | 19.00 Server balancing/scale up on "main" cohort and 18.40 scale down/removal of "oldmain" cohort | Live Ops (Jon Sredl) | Done
|  |  |  | 9:45 | 2021-12-05 | Push key for Pumpkin plugin & Artemis_Terrain to MCP/Mesh Consider changing MatchmakingStartTime if needed | Evan Kinney | Done |  | If MatchmakingStartTime is changed via the mesh network and the current hotfixed MatchmakingStartTime has already passed/will pass soon: make sure to hotfix the new value as well
|  |  | Hotfix | 10:00 | 2021-12-05 | Deploy to enable pumpkin start | Evan Kinney | Done |  | Exit Pumpkin into BattlePass FTUE (+/- 5 mins of stagger to ease service load)
|  |  |  | 10:03 | 2021-12-05 | Exit Pumpkin into Battle Pass FTUE |  | Done
|  |  |  | 12:00 | 2021-12-05 | Jump In now messaging on social | Clinton Butler / Mana Drake | Done |  | Began at 315 pm EST
|  |  |  | 10:15 | 2021-12-05 | Paid media jump in now | Kyle Gaunt | Done
|  |  |  | ~11:00:00 AM | 2021-12-06 | Start Side Bar and Social Profile Roll Out | Matthew Coleman/Darin Devine | Done |  | Moved to 12/6
|  |  |  | 21:00 | 2021-12-05 | Revert Resiliency Hotfixes | PeteA/Release | Done |  | https://epic.slack.com/archives/C02EL6W1YGP/p1638736295228600 leaving the payout disable in defaultruntimeoptions for another day or so per Pete Axt feedback
Formulas:
Date = [Date, row above]

## Deprecated v1 (hidden)
Armadillo
|  | Validation | Deployment Type | Time | Date | Description | Owner | Status | Jira (If Applicable) | Notes
[5 empty] | Ongoing | Dry run of show | Release QA | Not Started
[6 empty] | Update first parties with event date & higher player count | Ryan Broseker | Not Started
RELEASE DETAILS |  |  |  | Anytime |  | Playlist Setup | Game Team (Ben Saponaro . Ethan P) | Not Started |  | Reach out to Ethan P for playlist info. Core BR modes only (match Buffet behavior)
Release Version | 20.50 |  |  |  |  | Marketing Two Week Leadup | Alec Shobin / Paris N | Not Started
[6 empty] | Validate "unforced" patching on XB/PS | Release Team | Not Started |  | https://epic.slack.com/archives/C02GNP21LS1/p1634052333097500
Hard Lock Date | 2021-11-04 |  |  |  |  | 18.30 Rolling Deploy Test | Release Team | Not Started |  | Casey Spencer & David Hamm have some migrations that we want to use to validate the Rolling Deploy https://epic.slack.com/archives/C02GNP21LS1/p1634054352108800
Pencils Down | 2021-11-08
Cert Sub | 2021-11-11
Event Live Date | 2021-12-04 |  |  |  |  | Tech to trigger Pumpkin from nitenite |  | Done |  | Works
Live Time (Eastern) | 16:00 |  |  |  |  | Tech to deliver encryption key
[6 empty] | Tech to deliver encryption key AND trigger pumpkin just for QA |  | Blocked |  | Evan - Need to whitelist RelQA for Live Whiteglove of 19.00 - They use Shipping Clients
Downtime (Eastern) | 2:00 |  |  |  |  | Jitter for MMS into pumpkin |  | Done
19.00 Uptime (Eastern) | 5:00 |  |  |  |  | RTCocnut (so clients in coconut in 19.00 and experience an error don't RTMM) | Riley Halligan
[6 empty] | Test and API audit 18.40 and 19.00 nitenite | Riley Halligan | Done
Release Version | 19 |  |  |  |  | Retool of nitenite to make sure login/profile Migration happens |  | Done
Version and update checking
Hard Lock Date | 2021-11-10 |  |  |  | 2021-12-04 | --how do we inform/force an 18.40 client out to get new patch from nitenite | Evan Kinney | In Progress
Pencils Down | 2021-11-17 |  |  | 2:10 AM* | 2021-12-04 | --need to tell everyone they CAN update the client in the "not forced" time | Evan Kinney | Not Started |  | How do we want to display this to players? Re-do dialogue box.
Cert Sub | 2021-12-01 |  |  |  | 11/29/2021* | Triple size of MCP fleet | Online (Pete Axt) | Not Started |  | Need to sort this date with the online team
Event Live Date | 2021-12-04 |  |  |  | 2021-11-16 | 18.40 Build is Live | Release Team (Stan Hormell) | Not Started
Live Time (Eastern) | 10:00
|  |  |  | 10:00 |  | Publish socialevents page in CMS with event Name and Time | Michael House | Not Started
RESOURCES |  |  | Calendar Event | 10:00 | 2021-11-26 | In-game and Lobby Timer (18.40) | Ethan Podczerwinski (High Voltage) / Nick Meili | Not Started |  | Calendar event
Working Channel | #fn-guava-event |  |  | 10:00 |  | Clarify Marketing Appointment set | Alec Shobin | Not Started |  | All appointments are added as line-items
WarRoom Channel | #fn-guava-ros |  |  | 10:05 |  | CMS Event Config rolled out | Michael House (CMS) | Blocked |  | Social Pod owning functionality - Darin Devine producing
Design Doc |  |  |  | 10:05 |  | CMS Event Config rolled out | PLM Team (Kendra K / David H) | Blocked
Tech Beats Doc |  |  |  | 10:00 |  | Event Tease 1 / "RSVP" MOTD | PLM Team (Kendra K / David H) | Blocked
Game Config Sheet | Link
|  |  |  | 10:00 |  | Push Notification - Schedule Set | PLM (Jameson B / David H) | Blocked
|  |  |  | 10:00 |  | Launcher Toast Notification | PLM (Jameson B / David H) | Blocked
POINTS OF CONTACT
Design | Billy Rivers |  |  | 10:00 |  | Event Tease 2 / "RSVP" MOTD | PLM Team (Kendra K / David H) | Blocked
|  |  |  | 10:00 | 2021-11-26 | Cancel/Reschedule Weekend Horde & P4 Maintenance | Release Team (Stan Hormell) | Not Started |  | Buffet Hotfixes were blocked by Horde maintenance
|  |  |  | 14:00 | 2021-12-03 | Disable Third Party AntiCheat for Guava\Coconut\Pumpkin Playlists | Anticheat (Charlie Nomides) | Not Started |  | We will disable EAC and BE for the Guava playlist via Nobus.
Production | Jess Ammerman |  |  | 10:00 |  | Event Audio Log / "RSVP" MOTD | PLM Team (Kendra K / David H) | Blocked
Jason Glatz
| Michael Carlock |  |  | 14:00 |  | Push Notification - event live soon | PLM (Cameron R / David H) | Blocked
| Robert Knorr |  |  | 10:00 |  | Change image for playlist tile | Community (Michael House) | Not Started |  | Needs to be after announcement, but before event. Can be same day.
| Keith Hladik (HVS) |  |  | 10:00 |  | Post heads-up messaging on social about when things will be disabled. | Community (Michael House) | Not Started
| Jessa Carlson (HVS) |  |  | 10:00 |  | Publish heads-up messaging in-game for Creative and STW. | Community (Michael House) | Blocked |  | StW will be in Discovery. Has StW messaging changed?
|  |  |  | 12:00 | 2021-12-04 | Server Scaling in preparation for event | Liveops (JonS) | Not Started |  | 4 hours before the event goes live (4 pm EST)
Dev QA | Dara Potocska |  |  | 12:00 | 2021-12-03 | Verify mesh network is scaled appropriately Verify base NightNightFrontend metadata is present in mesh | Online-OGS (Paul and Evan) | Not Started |  | { "NightNightFrontend": { "AreWeGettingSleepy": "VeryVerySleepyUwU", "HasDaddyTuckedUsIn": false, "Splines": [] } }
|  |  |  | 12:00 | 2021-12-04 | Add Event LTM to default playlists (which allows the calander to trigger them on) | Release Team (Stan Hormell/Eryc Kelly) | Not Started |  | Morning of.
|  |  |  | 12:00 | 2021-12-04 | Disable Mobile Guided Tutorial | Release Team (Stan Hormell/Eryc Kelly) | Not Started
|  |  |  | 12:00 | 2021-12-04 | Deploy StW Auto Complete Hotfix | Release Team (Stan Hormell/Eryc Kelly) | Not Started |  | Syntax Source of Truth is in the Game Config Sheet
|  |  |  | 14:00 | 2021-12-04 | Disable BattleLab, Playgrounds, Party Island, and Creative modes | BR Game Team (Ben Saponaro / Ethan P) | Not Started |  | Needs to be 2 hours before event starts
|  |  |  | 12:00 | 2021-12-04 | In-game messaging: BattleLab, Creative, and Party Island have been disabled. | Community (Michael House) | Not Started |  | Right after we disable.
|  |  |  | 13:00 | 2021-12-04 | Add Event playlist to DAD | Release Team (Stan Hormell/Eryc Kelly) | Not Started
|  |  |  | 13:45 | 2021-12-04 | Deploy Discovery V2 setup to disable Featured island via DAD | Release Team (Stan Hormell/Eryc Kelly) | Not Started
|  |  |  | 14:00 | 2021-12-04 | Deploying HF for online resiliency during event (From Online Ops Team) | Release Team (Stan Hormell/Eryc Kelly) | Not Started |  | Needs to be 2 hours before event starts.
|  |  |  | 14:00 | 2021-12-04 | Hotfix to allow players to go NightNight and Enable mesh network connectivity on clients in lobby | Release Team (Stan Hormell/Eryc Kelly) | Not Started |  | Syntax Source of Truth is in the Game Config Sheet
|  |  |  | 14:00 | 2021-12-04 | Set mole server shutdown time to 30 Mins | Release Team (Stan Hormell/Eryc Kelly) | Not Started |  | https://epic.slack.com/archives/CB1EDDKDK/p1629814647369900?thread_ts=1629750923.354800&cid=CB1EDDKDK | Float in sec
|  |  |  | 14:00 | 2021-12-04 | Emergency messaging updated: Customs disabled | Community (Michael House) | Not Started
|  |  |  | 14:00 | 2021-12-04 | Verify mesh network service health after client enable Verify client connectivity via PlayerContext canary | Online-OGS (Paul and Evan) | Not Started
|  |  |  | 12:00 | 2021-12-04 | Verify waiting room configuration in admin portal to 750 (Fortnite) and 500 (mobile) | Liveops (JonS and Pete Axt)) | Not Started
|  |  |  | 15:00 | 2021-12-04 | Turn off Arena | Competitive (Nathaniel Garrett) | Not Started |  | This can be done automatically with Arena Blackout windows
|  |  |  | 15:00 | 2021-12-04 | Emergency messaging updated:: Arena disabled | Community (Michael House) | Not Started
|  |  |  | 15:00 | 2021-12-04 | Social Promotion (IG Story Videos, Wallpaper, etc) | Emily N | Not Started |  | 1 hour before event
|  |  |  | 15:00 | 2021-12-04 | Players will be kicked from the StW frontend and to the mode select screen. | Release QA (Eryc) | Blocked |  | The new flow goes in during 18.40, will likely be tested fairly late. | dev online bug. Not needed for the live game.
|  |  |  | 15:15 | 2021-12-04 | Undo Playlist blocking via MMS | Evan Kinney | Not Started |  | 35 minutes before showtime
|  |  |  | 15:15 | 2021-12-04 | Auto-win players in-game and send to the StW frontend. (Hotfix Syntax dictates the time it fires - Deployed with Hotfix Deploy 1) | Release QA (Eryc) | Not Started |  | Confirm that this works at that time
|  |  |  | 15:25 | 2021-12-04 | Enable Event playlist, Disable all other playlists in core including Mole (ROW ONLY) | Release QA (Mitchell H) | Not Started |  | 35 minutes before showtime (include in JIRA). Verify that this works at that tinme
|  |  |  | 15:25 | 2021-12-04 | Emergency messaging: Modes disabled and playlist open | Community (Michael House) | Not Started
|  |  |  | 15:25 | 2021-12-04 | Disable cloud banhammer actioning | Anticheat - Charlie Nomides/ Joe Barrett | Not Started
|  |  |  | 15:30 | 2021-12-04 | Add NightNight plugin encryption keypair to mesh for distribution to lobby clients | Online-OGS (EvanK) | Not Started
|  |  |  | 16:00 | 2021-12-04 | Event Showtime | BR Game Team (Billy Rivers) | Not Started |  | Link to Game Client Mesh Network Connectivity Dashboard
|  |  |  | 16:05 | 2021-12-04 | Event Triggered | BR Game Team (Billy Rivers) | Not Started |  | Syntax on Game Config
|  |  |  | 4:10:00 PM (midway-ish through event) | 2021-12-04 | NightNight Hotfix (live edit the system file directly to avoid Horde delay) Pick up anyone that missed the mesh trigger slash mesh trigger fallback | Release Team (Stan Hormell/Eryc Kelly) | Not Started
|  |  |  | 4:10 PM (before end) | 2021-12-04 | Change mesh network metadata to trigger NightNight mode immediately for anyone still in lobby | Online-OGS (Evan Kinney) | Not Started
|  |  |  | 4:10 PM (before end) | 2021-12-04 | Add 18.40 netCL to MMS blocklist in MCP Add NightNight key to MCP keychain | Online-OGS (Evan Kinney) | Not Started
|  |  |  | 16:15 | 2021-12-04 | Players enter Coconut experience in 18.40 | BR Game Team (Billy Rivers) | Not Started |  | Mesh command or entirely random?
[6 empty] | Debris in sequence | Cody Haskel | Not Started |  | Calendar events will drive debris.
[6 empty] | Camera Descent toward player | Billy Rivers | Not Started |  | Calendar events will drive this.
|  |  |  | 22:00 | 2021-12-04 | 19.00 Clients, Server, MPC, Hotfix Config are released |  | Not Started
[5 empty] | 2021-12-05 | Pumpkin and 19.00
|  |  | Calendar | 6:00 | 2021-12-05 | Force all 18.40 Players to update to 19.00* |  | Blocked |  | Need a hard cut-off time.
[5 empty] | 2021-12-05 | Camera shift to Artemis island (needs to live in 19.00) | Billy Rivers | Not Started |  | End of Coconut / Matchmake into Pumpkin (+/- 30 mins of stagger to ease service load)
|  |  |  | 8:00 | 2021-12-05 | Server balancing for 19.00 | Live Ops (Jon Sredl) | Not Started
|  |  |  | 10:00 | 2021-12-05 | Deploy to enable pumpkin start |  | Blocked |  | Exit Pumpkin into BattlePass FTUE (+/- 30 mins of stagger to ease service load)
|  |  |  | 10:00 | 2021-12-05 | Exit Pumpkin into Battle Pass FTUE |  | Not Started
China RoS
|  |  |  | 4:00 |  | Disable BattleLab, Playgrounds, Party Island, and Creative modes | Keaton Stewart | Not Started
|  |  |  | 4:00 |  | Emergency messaging: BattleLab, Creative, Party Island, and Playgrounds have been disabled. (Note that Playground is part of Creative, so no need to call out Playground specifically in the messaging.) | Jiaming Lu
|  |  |  | 7:00 |  | Add Event LTM to default playlists (which allows the calander to trigger them on) | Stan Hormell | Not Started
|  |  |  | 7:00 |  | Change name and image for playlist | Jiaming Lu | Not Started
|  |  |  | 7:00 |  | Push key to keychain in admin portal | Stan Hormell | Not Started |  | DefaultRuntimeOptions.ini [/Script/FortniteGame.FortRuntimeOptions] bShouldAllowNightNightMode=true
|  |  |  | 7:00 |  | Hotfix to allow players to go NightNight | Stan Hormell | Not Started
|  |  |  | 7:25 |  | Enable Event playlist, Disable all other playlists | BR Game Team (Ben Saponaro) | Not Started
|  |  |  | 7:25 |  | Emergency messaging: Modes disabled Social Messaging also required. | Jiaming Lu | Not Started
|  |  |  | 8:10 AM (ET) |  | Event Showtime in China | BR Game Team | Not Started |  | DefaultRuntimeOptions.ini [/Script/FortniteGame.FortRuntimeOptions] bForceEverybodyToGoNightNight=true bAllowSubgameSelectToGoNightNight=true bAllowAthenaFrontendToGoNightNight=true bAllowCampaignFrontendToGoNightNight=true
|  |  |  | 8:15 AM (ET) (after event start) |  | Hotfix: force players into NightNight | Stan Hormell | Not Started
Formulas:
Date = [Date, row above]

## Playlist Setup (hidden)
DESIRED CALENDAR STATES - ROW
12/4/2021 (ALL TIMES ET) | 18.4 | Pre Event - 12:00PM | Event - 3:25PM | Post Event (4:15PM) | Post Event (4:30PM)
Live Event Playlist | OFF | OFF | ON | ON (in case of delay) | OFF
Regular Solo | ON | ON | OFF | ON | ON
Regular Duo | ON | ON | OFF | ON | ON
Regular Squad | ON | ON | OFF | ON | ON
Team Rumble | ON | ON | OFF | ON | ON
(LTM) | ON | ON | OFF | ON | ON
Playgrounds | ON | OFF | OFF | ON | ON
Creative | ON | OFF | OFF | ON | ON
DESIRED CALENDAR STATES - FNCN
Dec 1 (ALL TIMES ET) | 14.6 | Pre Event - 12:00AM | Event - 3:25AM | Post Event (4:15AM) | Post Event (4:30AM)
Live Event Playlist | OFF | OFF | ON | ON (in case of delay) | OFF
Regular Solo | ON | ON | OFF | ON | ON
Regular Duo | ON | ON | OFF | ON | ON
Regular Squad | ON | ON | OFF | ON | ON
Rumble | ON | ON | OFF | ON | ON
Fortnite Playlist | ON | ON | OFF | ON | ON
Playgrounds | ON | OFF | OFF | ON | ON
Creative | ON | OFF | OFF | ON | ON

## Publishing Run of Show
Filter Be mindful of others using the sheet at the same time | [PROJECT NAME] RUN OF SHOW |  | Mkt & Prod Leads: | Publishing Owners: Ecosystem LEGO FN: Rocket Racing: Festival: FNBR: |  |  | Launch Room Zoom Link | Launch channel: Deploy channel: Ecosystem channel: LEGO FN channel: Festival channel: FN channel:
Product | Status | Team | Date | Time ET (Raleigh/Cary) | Time PT (Los Angeles) | Time BST (UK) | Time JST/KST (Yokohama/Seoul) | Checklist Item | Scheduled / Automated | Owner | Backup Owner | Notes & Flags
2025-01-01
FNBR | FALSE | Publishing - PLM | 2025-01-01 | 2025-01-01 | 2024-12-31 21:00 | 2025-01-01 05:00 | 2025-01-01 14:00
LEGO FN | FALSE | Publishing - Community | 2025-01-01 | 2025-01-01 10:00 | 2025-01-01 07:00 | 2025-01-01 15:00 | 2025-01-02
Rocket Racing | FALSE | Publishing - Social | 2025-01-01 | 2025-01-01 12:00 | 2025-01-01 09:00 | 2025-01-01 17:00 | 2025-01-02 02:00
Eco | FALSE | Publishing - Influencer | 2025-01-01 | 2025-01-01 14:00 | 2025-01-01 11:00 | 2025-01-01 19:00 | 2025-01-02 04:00
Rocket Racing | FALSE | Publishing - Marketing | 2025-01-01 | 2025-01-01 16:00 | 2025-01-01 13:00 | 2025-01-01 21:00 | 2025-01-02 06:00
Eco | FALSE | Publishing - Comms / Editorial | 2025-01-01 | 2025-01-01 18:00 | 2025-01-01 15:00 | 2025-01-01 23:00 | 2025-01-02 08:00
Eco | FALSE | Release Team | 2025-01-01 | 2025-01-01 20:00 | 2025-01-01 17:00 | 2025-01-02 01:00 | 2025-01-02 10:00
Epic Games Store | FALSE | Dev - Special Projects | 2025-01-01 | 2025-01-01 22:00 | 2025-01-01 19:00 | 2025-01-02 03:00 | 2025-01-02 12:00
Festival | FALSE | Partner Activity | 2025-01-01 | 2025-01-01 12:00 | 2025-01-01 09:00 | 2025-01-01 17:00 | 2025-01-02 02:00
| 🌟 | 2024-01-01
Eco | FALSE | Online - Web | 2024-01-01 | 2024-01-01 02:00 | 2023-12-31 23:00 | 2024-01-01 07:00 | 2024-01-01 16:00 | Web Page is published
Eco | FALSE | Release Team | 2024-01-01 | 2024-01-01 02:00 | 2023-12-31 23:00 | 2024-01-01 07:00 | 2024-01-01 16:00 | Launch video live on YouTube / Social
Eco | FALSE | Publishing - Paid Media | 2024-01-01 | 2024-01-01 02:00 | 2023-12-31 23:00 | 2024-01-01 07:00 | 2024-01-01 16:00 | Competitive Details blog post is published
Eco | FALSE | Release Team | 2024-01-01 | 2024-01-01 02:00 | 2023-12-31 23:00 | 2024-01-01 07:00 | 2024-01-01 16:00 | Blog Post is published
Eco | FALSE | Fortnite - Dev Team | 2024-01-01 | 2024-01-01 02:00 | 2023-12-31 23:00 | 2024-01-01 07:00 | 2024-01-01 16:00 | Light Switch Down / Downtime Begins / Leaks Begin
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 02:00 | 2023-12-31 23:00 | 2024-01-01 07:00 | 2024-01-01 16:00 | Web header live
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 02:00 | 2023-12-31 23:00 | 2024-01-01 07:00 | 2024-01-01 16:00 | Media Alert Live w/ link to blog
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 02:00 | 2023-12-31 23:00 | 2024-01-01 07:00 | 2024-01-01 16:00 | Discover Playlist Tiles; main Lobby Background +Stage FX; BR, ZB VUIDs. Island pages updated w/ stills & videos (Battle Royale + Zero Build). Tournament Settings playlists updated. BR/ZB Ranked Tiles.
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 02:00 | 2023-12-31 23:00 | 2024-01-01 07:00 | 2024-01-01 16:00 | Social, Streaming and community channels updated
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 02:00 | 2023-12-31 23:00 | 2024-01-01 07:00 | 2024-01-01 16:00 | FTUE updated with new content
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 02:00 | 2023-12-31 23:00 | 2024-01-01 07:00 | 2024-01-01 16:00 | Update the Crew/Pass Upsell in FTUE to show Battle Pass
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 02:00 | 2023-12-31 23:00 | 2024-01-01 07:00 | 2024-01-01 16:00 | Update Platform Metadata & Art for ____ (MSFT, Sony, Luna)
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 02:00 | 2023-12-31 23:00 | 2024-01-01 07:00 | 2024-01-01 16:00 | Update Platform Metadata & Art for Fortnite Ecosystem (MSFT, Sony, Luna, Nintendo) Update Screenshots for FN Ecosystem with ____ (MSFT, Sony, Luna & NTDO)
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 02:00 | 2023-12-31 23:00 | 2024-01-01 07:00 | 2024-01-01 16:00 | Epic Games Store image/copy is updated.
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 02:00 | 2023-12-31 23:00 | 2024-01-01 07:00 | 2024-01-01 16:00 | [EGS App] Copy and Screenshots are updated
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 02:00 | 2023-12-31 23:00 | 2024-01-01 07:00 | 2024-01-01 16:00 | Headers - PS5 Activity Tiles, Xbox Club Art
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 02:00 | 2023-12-31 23:00 | 2024-01-01 07:00 | 2024-01-01 16:00 | Influencer Asset Pack uploaded to Box.com
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 02:00 | 2023-12-31 23:00 | 2024-01-01 07:00 | 2024-01-01 16:00 | MOTDs published during downtime
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 07:00 | 2024-01-01 04:00 | 2024-01-01 12:00 | 2024-01-01 21:00 | Light Switch Up / Downtime Ends
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 08:00 | 2024-01-01 05:00 | 2024-01-01 13:00 | 2024-01-01 22:00 | Ecosystem Boot Up Flow Updated w/ ___ Art
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 08:00 | 2024-01-01 05:00 | 2024-01-01 13:00 | 2024-01-01 22:00 | Owned 1st Party News Posts - PS Official News, PS/Xbox Event, Xbox Club, Nintendo Switch News
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 08:00 | 2024-01-01 05:00 | 2024-01-01 13:00 | 2024-01-01 22:00 | 1st Party "Live Now" Embargo Lifts
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 08:00 | 2024-01-01 05:00 | 2024-01-01 13:00 | 2024-01-01 22:00 | "Game is live!" social post
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 08:00 | 2024-01-01 05:00 | 2024-01-01 13:00 | 2024-01-01 22:00 | Console Paid Media Live
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 08:00 | 2024-01-01 05:00 | 2024-01-01 13:00 | 2024-01-01 22:00 | Paid Media Rolling Launch - YouTube, TikTok, Instagram
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 08:00 | 2024-01-01 05:00 | 2024-01-01 13:00 | 2024-01-01 22:00 | Discord Quest Live Globally
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 08:00 | 2024-01-01 05:00 | 2024-01-01 13:00 | 2024-01-01 22:00 | Push Notification
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 08:00 | 2024-01-01 05:00 | 2024-01-01 13:00 | 2024-01-01 22:00 | Fortnite Newsletter Email
Eco | FALSE | Publishing - | 2024-01-01 | 2024-01-01 08:00 | 2024-01-01 05:00 | 2024-01-01 13:00 | 2024-01-01 22:00 | Endemic Online Media Campaign Starts
2024-01-02
FNBR | FALSE | Publishing - First Party | 2024-01-02 | 2024-01-02 09:00 | 2024-01-02 06:00 | 2024-01-02 14:00 | 2024-01-02 23:00
FNBR | FALSE | Publishing - LATAM | 2024-01-02
FNBR | FALSE | Publishing - EMEA | 2024-01-02
FNBR | FALSE | Publishing - JAPAN
Formulas:
Time ET (Raleigh/Cary) = [Date]+time(0,0,0)
Time PT (Los Angeles) = [Time ET (Raleigh/Cary)]-time(3,0,0)
Time BST (UK) = [Time ET (Raleigh/Cary)]+time(5,0,0)
Time JST/KST (Yokohama/Seoul) = [Time ET (Raleigh/Cary)]+time(14,0,0)

## Publishing On Call
[PROJECT NAME] ON-CALL
ALL TIMES ET | Marketing | Pub Producer | CS Producer | Community | Social | First Party | Video | Web | PLM | Loc | Influencer Marketing | Comms / PR | CS Designer | Creative/UEFN Community | Player Experience | Monetization | Engagement
Day
12:00am - 2:00am
2:00am - 4:00am
4:00am - 6:00am
6:00am - 8:00am
8:00am - 10:00am
10:00am-12:00pm
12:00pm - 2:00pm
2:00pm - 4:00pm
4:00pm - 6:00pm
6:00pm - 8:00pm
8:00pm - 10:00pm
10:00pm - 12:00am
Day
12:00am - 2:00am
2:00am - 4:00am
4:00am - 6:00am
6:00am - 8:00am
8:00am - 10:00am
10:00am-12:00pm
12:00pm - 2:00pm
2:00pm - 4:00pm
4:00pm - 6:00pm
6:00pm - 8:00pm
8:00pm - 10:00pm
10:00pm - 12:00am
Day
12:00am - 2:00am
2:00am - 4:00am
4:00am - 6:00am
6:00am - 8:00am
8:00am - 10:00am
10:00am-12:00pm
12:00pm - 2:00pm
2:00pm - 4:00pm
4:00pm - 6:00pm
6:00pm - 8:00pm
8:00pm - 10:00pm
10:00pm - 12:00am